Standard Bidding Documents

for

National and International Competitive Bidding

Design and Build of Construction Works

FEBRUARY 2025

# Invitation for bidders

## INVITATION FOR BIDDERS

- SECTION I: INVITATION FOR BIDDERS

- [Insert Name of Procuring Entity]

- [Insert Logo]

- Bid No.[insert Bid Number reference number from the Procurement Plan][insert title or brief description of the Works]

- Invitation for Bidders

- Date:

- 1.	This Invitation for Bidders follows the General Procurement Notice for this Project which appeared in the Electronic Procurement System (E-Proz) dated [insert dates of publication of GPN].

- 2.	The Revolutionary Government of Zanzibar has set aside funds for the operation of the [insert the name PE] during the financial year (insert the year under financing). It is intended that part of the proceeds of the fund will be used to cover eligible payment under the contract for the [insert the name of the contract]

- or

- The [insert name of PE] has received/has applied for/intends to apply for a [loan/credit /grant] from the [name of financing institution] towards the cost of [insert name of project], and it intends to apply part of the proceeds of this [loan/credit/grant] to cover eligible payments under the contract for [insert name. of the contract].

- 3.	The [insert name of PE] now invites Bidders from the following pre-qualified Bidders for [insert brief description of WorksDesign and Build]1.

- [Insert names of pre-qualifiedBidders]

- 4.	Bidding will be conducted through the [insert method of procurement] specified in the Public Procurement Regulations and is open to all pre-qualified Bidders...

- 5.	Invited Bidders may obtain further information from and inspect the Bid document provided on E-Proz.

- 6.	A complete set of Biding Document(s) in [insert language of the Bid document] may be obtained or downloaded through E-Proz.

- 7.	Bidders are required to register on the E-Proz and pay Bid participation fees indicated in the E-Proz to able to participate in this Biding process.

- 8.	The Bid will consist of (i) the Technical Part, without any reference to prices; and (ii) the Financial Part, as detailed in the Bid document..

- 9.	The Bid consisting of both the Technical Part and the Financial Part, must be delivered through E-Proz at or before [insert time and date].

- 10.	The Technical Part will be opened promptly thereafter on E-Proz dashboard and Bidders may participate in the opening by logging into the E-Proz. The Financial Part shall remain unopened until the second public opening of the Financial Part, following the evaluation of the Technical Part of the Bid.

- 11.	All Bids must be accompanied by a Bid Security [if Bid security is required] in an acceptable form in the amount of [insert the amount in local currency] or freely convertible currencies.

- 12.	If you do not intend to submit a Bid, we would appreciate being so notified through E-Proz at your earliest opportunity.

- 13.	Bids not received or opened through E-Proz shall not be accepted for evaluation irrespective of the circumstances.

- [Insert the title of the Accounting Officer and address of the PE]

PART I

BIDDING PROCEDURE

# Section I

# Instructions to bidders

# (ITB)

Table of Contents

Sec. II

- Introduction	8

1. 	Scope of Bid 	8

2.	Source of Funds 	8

3.	Eligibility of Bidders	8

4.	Conflict of Interest

5.	One Bid per Bidder	9

6.	Cost of Biddering 	9

7.	Site Visit and Pre-Bid Meeting	10

- Bidding Documents	10

8.	Content of Bidding Documents	10

9.	Clarification of Bidding Documents	11

10.	Amendment of Bidding Documents	11

- Preparation of Bids	12

- Language of Bid	12

- Documents Constituting the Bid	12

- Documents Establishing Eligibility and Qualifications of the Bidder	12

- Documents Comprising the Technical Offer	16

- Forms of Bid	16

- Bid Prices	16

- Bid Currencies	17

- Bid Validity Period	17

19	Bid Security	17

20	Alternative Bids by Bidders	19

- Format and Signing of Bid	19

- Submission of Bids	20

22. Sealing and Marking of Bids	20

23. Deadline for Submission of Bids 	21

24. Late Bids 	21

25. Modification and Withdrawal of Bids 	21

- Opening and Evaluation of Bid	22

26.	Opening of Bids	22

27.	Confidentiality	23

28.	Clarification of Bids	23

29.	Preliminary Examination of Bids	23

30.	Correction of Errors	25

31.	Conversion to Single Currency	25

32.	Comparison of Bids	26

33.	National Preference	27

34.	Determination of Lowest Evaluated Price Proposal	28

35.	Post-qualification of Bidders	28

- Award of Contract	29

36.	Criteria of Award 	29

37.	Negotiations	29

38.	Procuring Entity’s Right to Accept any Bid and to Reject any or all Bids	30

39.	Procuring Entity’s Right to Vary Quantities at the Time of Award	30

40.	Notification of Award	30

41.	Signing of Contract	31

42.	Performances Security	31

43.	Advance Payment	32

44.	Adjudicator	32

45.	Fraud and Corruption	32

- Review of Procurement Decisions	33

46.	Right to review	33

##### A. Introduction

| 1. | Scope of Bid | 1.1 | The Procuring Entity as indicated in the Bid Data Sheet invites Bids for the design and construction of works, as described in the Employer’s Requirements. The name and identification number of the Contract is provided in the Special Conditions of Contract. |
| --- | --- | --- | --- |
|  |  | 1.2 | The successful Bidder will be selected according to Competitive Biding procedures as set out in the Public Procurement Act No 2 of 2025 in accordance with the evaluation criteria specified in the document. |
| 2. | Source of Funds | 2.1 | The Procuring Entity has funds for the Works specified in the Bid Data Sheet during the financial year specified in the Bid Data Sheet. It is intended that part of the proceeds of the funds will be applied to cover eligible payments under the contract for the works as described in the Bid Data Sheet. |
|  |  | 2.2 | Payments will be made directly by the Procuring Entity (or by financing institution specified in the Bid Data Sheet upon request of the Procuring Entity to so pay) and will be subject in all respects to the terms and conditions of the resulting contract placed by the Procuring Entity. |
| 3. | Eligibility of Bidders | 3.1 | A Bidder may be a natural person, Private Entity, Government-owned Entity, subject to ITB 4.1 or any combination of them with a formal intent to enter into an agreement or under an existing agreement in the form of a joint venture, consortium, or association. In the case of a joint venture, consortium, or association, unless otherwise specified in the Bid Data Sheet, all parties shall be jointly and severally liable. The joint venture, consortium or association shall nominate a representative who shall have the authority to conduct all business for and on behalf of any and all the partners of the joint venture, consortium or association during the Biding process and in the event the joint venture, consortium or association is awarded the Contract, during contract execution. |
|  |  | 3.2 | The invitation for Bids is open to all Bidders as defined in the Public Procurement Act No 2 of 2025. |

|  |  | 3.3 | - National Bidders shall satisfy all relevant licensing and/or registration requirements with the appropriate statutory bodies in Zanzibar. Foreign Bidders are exempted from this requirement but where selected as having submitted the lowest evaluated Bid the successful Bidder shall register with the appropriate statutory body and shall be required to submit evidence of registration as an approved contractor in T before signing the contract |
| --- | --- | --- | --- |
| - 4. | - Conflict of Interest | 4.1 | A Bid shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this Biding process, if they: - Are associated or have been associated in the past, directly or indirectly with a firm or any of its affiliates which have been engaged by the Procuring Entity to provide consulting services for the preparation of the specifications and other documents to be used for the procurement of the works to be purchased under this Invitation for Bids. - have controlling shareholders in common; or - receive or have received any direct or indirect subsidy from any of them; or - have the same legal representative for purposes of this Bid; or - have a relationship with each other, directly or through common third parties, that puts them in a position to have access to information about or influence on the Bid of another Bidder, or influence the decisions of the Procuring Entity regarding this Biding process; or - submit more than one Bid in this Biding process, However, this does not limit the participation of subcontractors in more than one Bid, or as Bidders and subcontractors simultaneously; or Participated as a consultant in the preparation of the technical specifications of the goods and related services that are the subject of the Bid. |
|  |  | 4.2 | - Tend Bidders shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Revolution Government Zanzibar in accordance with ITB 45.1 |
|  |  | 4.3 | Government owned enterprises in the United Republic of Tanzania may participate only if they can establish that they (i) are legally and financially autonomous; and (ii) operate under commercial law. No dependent agency of the Public Authority under public financed project shall be permitted to Bid or submit a proposal for the procurement of goods or works under the project. |
|  |  | 4.4 | Bidders shall provide such evidence of their continued eligibility satisfactory to the Procuring Entity, as the Procuring Entity shall reasonably request. |
| 5. | One Bid per Bidder | 5.1 | A firm shall submit only one Bid, in the same Biding process, either individually as a Bidder or as a partner in a joint venture. |
|  |  | 5.2 | No firm can be a subcontractor while submitting a Bid individually or as a partner of a joint venture in the same Biding process. |
|  |  | 5.3 | A firm, if acting in the capacity of subcontractor in any Bid, may participate in more than one Bid but only in that capacity. |
|  |  | 5.4 | A Bidder who submits or participates in more than one Bid (other than as a subcontractor or incases of alternatives that have been permitted or requested) will cause all the proposals in which the Bidder has participated to be disqualified. |
| 6. | Cost of Biding | 6.1 | The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Procuring Entity shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the Biding process . |
| 7. | Site Visit and Pre-Bid Meeting | 7.1 | The Bidder, at the Bidder's own responsibility and risk, shall visit 'and examine the Site of Works and its surroundings and obtain for itself all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder's own expense. |
|  |  | 7.2 | The Procuring Entity may conduct a site visit and a pre-Bid meeting whose purpose shall be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  |  | 7.3 | The Bidder's designated representative is invited to attend a site visit and pre-Bid meeting which, will take place at the venue and time stipulated in the Bid Data Sheet. |
|  |  | 7.4 | The Bidder is requested as far as possible, to submit any questions in writing or by cable, to reach the Procuring Entity before pre-Bid meeting. It may not be practicable at the meeting to answer all questions, but questions and responses will be transmitted in accordance with ITB 7.5. |
|  |  | 7.5 | Minutes of the pre-Bid meeting, including the text of the questions raised and the responses given together with any responses prepared after the pre-Bid meeting, will be transmitted within the time stated in the Bid Data Sheet to all purchasers of the Biding documents. Any modification of the Biding Documents listed in ITB 8.1 that may become necessary as a result of the pre-Bid meeting shall be made by the Procuring Entity exclusively through the issue of an Addendum pursuant to ITB 10.2 and not through the minutes of the pre-Bid meeting. |
|  |  | 7.6 | Non-attendance during the site visit or pre-Bid meeting will not be a cause for disqualification of a Bidder. |

B. Biding Documents

| 8. | Content of Biding Documents | 8.1 | The Biding documents which should be read in conjunction with any addenda issued in accordance with ITB 10.2 include: Volume 1: Part I – Biding Procedures - Section I – Instructions to Bidders (ITB) - Section II – Bid Data Sheet (BDS) - Section III – Evaluation and Qualification Criteria - Section IV – Bid Submission Forms Part II – Conditions of Contract - Section V – General Conditions of Contract (GCC) - Section VI – Special Conditions of Contract (SCC) - Section VII – Forms of Security Part III – Works Requirements - Section VIII –Price Offer Form - Section IX – Specifications - Section X – Employer’s Requirements Part IV – Forms of Integrity - Section XII – Forms of Integrity. Volume 2: - Survey Plan / Plot Recovery - Topographic Map - International Coordinates - Environmental and Social Impact Assessment (ESIA) Report - Soil Investigation Report - National Building Control Bill 2000- (Building Code) Volume 3: - Structural Design Requirements - Fire Act/Regulations, 2007 - Sample Bill of Quantities |
| --- | --- | --- | --- |
|  |  | 8.2 | The number of copies to be completed and returned with the Bid is specified in the Bid Data Sheet. |
|  |  | 8.3 | The Invitation for Bids issued by the Procuring Entity is not part of the Biding Documents. In case of discrepancies between the Invitation for Bid and the Biding Documents listed in ITB 8.1 above, said Biding Documents will take precedence. |
|  |  | 8.4 | The Procuring Entity is not responsible for the completeness of the Biding Documents and their addenda, if they were not obtained directly from the Procuring Entity. |
|  |  | 8.5 | The Bidder is expected to examine all instructions, forms, terms and specifications in the Biding Documents. Failure to furnish all information required by the Biding Documents or to submit a Bid substantially responsive to the Biding documents in every respect will be at the Bidder’s risk and may result in the rejection of its Bid. |
| 9. | Clarification of Biding Documents | 9.1 | A prospective Bidder requiring any clarification of the Biding documents may notify the Procuring Entity in writing or electronic mail, telex and facsimile at the Procuring Entity's address indicated in the Bid Data Sheet. |
|  |  | 9.2 | The Procuring Entity will within the period stated in the Bid Data Sheet respond in writing to any request for clarification provided that such request is received or clarification issued no later than the period indicated in the Bid Data Sheet prior to the deadline for the submission of Bids prescribed in ITB 23.1. |
|  |  | 9.3 | Copies of the Procuring Entity's response will be forwarded to all Purchasers of the Biding documents, including a description of the inquiry, but without identifying its source. |
|  |  | 9.4 | Should the Procuring Entity deem it necessary to amend the Biding documents as a result of a clarification, it shall do so following the procedure under ITB 10. |
| 10. | Amendment of Biding Documents | 10.1 | Before the deadline for submission of Bids, The Procuring Entity for any reason, whether at its own initiative or in response to a clarification requested by a prospective Bidder, the Procuring Entity may modify the Biding documents by issuing addenda. Such clarification shall be sought or issued not later that the number of days stated in ITB 9.2 before the closing date or deadline for the submission of Bids. |
|  |  | 10.2 | Any addendum issued shall be part of the Bid documents pursuant to ITB 8.1 and shall be communicated in writing or electronic mail, facsimile to all who have obtained the Biding documents directly from the Procuring Entity. |
|  |  | 10.3 | In order to allow prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Procuring Entity at its discretion shall extend, as necessary, the deadline for submission of Bids, in accordance with ITB 23.2. |

C. Preparation of Bids

| 11. | Language of Bid | 11.1 | The Bid, and all correspondence and documents related to the Bid exchanged by the Bidder and the Procuring Entity, shall be written in the Bid language stipulated in the Bid Data Sheet. Supporting documents and printed literature furnished by the Bidder may be in another language provided they are accompanied by an accurate translation of the relevant passages in the above stated language, in which case, for purposes of interpretation of the Bid, the translation shall prevail. |
| --- | --- | --- | --- |
| 12. | Documents Constituting the Bid | 12.1 | The Bid shall comprise the following: - Form of Letter of Bid and Appendix to Bid; - completed forms and schedules as required, including Price Offer Form, in accordance with ITB 13 and 16; - Bid Security, in accordance with ITB 19; - alternative Bids, if permissible, in accordance with ITB 20; - g) Written Power of Attorney authorizing confirmation of signatory of the Bid to commit the Bidder in accordance with Instructions to Bidders ITB 21;documentary evidence in accordance with ITB 13 establishing the Bidder’s qualifications to perform the Contract if its Bid is accepted; - Technical Proposal (including Design Proposal) in accordance with ITB 14; - Financial Offer, in accordance with ITB 16; - completed forms and schedules as required, in accordance with ITB 13 and 16; - in the case of a Bid submitted by a joint venture or other consortium, a description indicating at least the parts of the design and construction of the Works to be executed by the respective members of the joint venture or consortium; and - any other document required in the TDS. |
|  |  | 12.2 | In addition to the requirements under ITB 12.1, Bids submitted by a joint venture or other consortium shall include a copy of the joint venture/consortium agreement entered into by all members. Alternatively, a letter of intent or similar instrument to execute a joint venture/consortium agreement in the event of a successful Bid shall be signed by all members and submitted with the Bid, together with a copy of the proposed joint venture/consortium agreement. |
| 13. | Documents Establishing Eligibility and Qualifications of the Bidder | 13.1 | Pursuant to ITB 12, the Bidder shall furnish, as part of its Bid, documents establishing the Bidder’s eligibility to Bid and its qualifications to perform the contract if its Bid is accepted. |
|  |  | 13.2 | In the event that pre-qualification of potential Bidders has been undertaken, only Bids from pre-qualified Bidders will be considered for award of Contract. These qualified Bidders should submit with their Bids any information updating their original pre-qualification applications or, alternatively, confirm in their Bids that the originally submitted pre-qualification information remains essentially correct as of the date of Bid submission. The update or confirmation should be provided in Section IV Bid Submission Forms. |
|  |  | 13.3 | If the Procuring Entity has not undertaken pre-qualification of potential Bidders, all Bidders shall include the following information and documents with their Bids in Section IV Bid Submission Forms, unless otherwise stated in the Bid Data Sheet: - copies of original documents defining the constitution or legal status, place of registration, and principal, place of business; written power of attorney authorizing the signatory of the Bid to commit the Bidder; - total monetary value of construction work performed for each of the number of years specified in the Bid Data Sheet; - experience in design and construction of works of a similar size for each of the number of years specified in the Bid Data Sheet, and details of work under way or contractually committed; and clients who may be contacted for further information on those Contracts; - major items of construction equipment proposed to carry out the Contract as listed in the Bid Data Sheet; - qualification and experience of key personnel for designing; - qualifications and experience of key site management and technical personnel proposed for the Contract; - reports on the financial standing of the Bidder, such as profit and loss statements and auditor's reports for the past three years; - evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources); - authority to seek references from the Bidder's bankers; - information regarding any litigation, current or during the last number of years specified in the Bid Data Sheet, in which the Bidder is involved, the parties concerned, and disputed amount; - information regarding labour, occupational health and safety records of the company for the past number of years specified in the Bid Data Sheet; and - Proposals for subcontracting components of the Works amounting to more than the percentage specified in the Bid Data Sheet of the Contract Price. |
|  |  | 13.4 | Bids submitted by a joint venture of two or more firms as partners shall comply with the following requirements, unless otherwise stated in the Bid Data Sheet: - the Bid shall include all the information listed in ITB 13.3 above for each joint venture partner; - the Bid shall be signed so as to be legally binding on all partners; - one of the partners will be nominated as being in charge, and this authorization shall be evidenced by submitting a power of attorney signed by legally authorized signatories of all the partners; - the partner in charge shall be authorized to incur liabilities and receive instructions for and on behalf of any and all partners of a joint venture and the entire execution of the Contract, including payment, shall be done exclusively with the partner in charge; - all partners of the joint venture shall be liable jointly and severally for the execution of the Contract in accordance with the Contract terms and a statement to this effect shall be included in the authorization mentioned under (c) above as well as in the Bid and in the Agreement (in case of a successful Bid); - a copy of the joint venture agreement entered into by all partners shall be submitted with the Bid. Alternatively, a Letter of Intent to execute a joint venture agreement in the event of a successful Bid shall be signed by all partners and submitted with the Bid, together with a copy of the proposed Agreement; and - the Bid security or Bid securing declaration as stated in accordance with ITB 19, and in case of a successful Bid, the Agreement, shall be signed so as to be legally binding on all partners. |
|  |  | 13.5 | To qualify for award of the Contract, Bidders shall meet the following minimum qualifying criteria:- - annual volume of construction work over a period and of at least the amount specified in the Bid Data Sheet; - experience as prime contractor in the construction of works of a nature and complexity equivalent to the Works over the period specified in the Bid Data Sheet (to comply with this requirement, works cited should be at least 70 per cent complete); - design experience in works of a nature and complexity equivalent to the Works over the period specified in the Bid Data Sheet; - experience as prime contractor, sub-contractor in at least a number of Contracts shown in the Bid Data Sheet within the period shown in the Bid Data Sheet, each with a minimum value shown in the Bid Data Sheet that have been successfully and substantially completed and that are similar to the proposed works; - Proposals for the timely acquisition (own, lease, hire, etc.) of the essential equipment listed in the Bid Data Sheet; - a Contract Manager with the experience of the duration specified in the Bid Data Sheet in works of an equivalent nature and volume; - liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than the amount specified in the Bid Data Sheet; - A consistent history of litigation or arbitration awards against the Bidder or any partner of a Joint Venture may result in disqualification; and - A consistent abuse of occupational health and safety requirements by the Bidder may result in disqualification. |
|  |  | 13.6 | The figures for each of the partners of a joint venture shall be added together to determine the Bidder's compliance with the minimum qualifying criteria of ITB 13.5(a) and (e); however, for a joint venture to qualify, the partner in charge must meet at least the percentage specified in the Bid Data Sheet of those minimum criteria. Failure to comply with this requirement will result in rejection of the joint venture's Bid. Subcontractors' experience and resources will not be taken into account in determining the Bidder's compliance with the qualifying criteria, unless otherwise stated in the Bid Data Sheet. |
|  |  | 13.7 | Domestic Bidders and joint ventures of domestic and foreign Bidders applying for eligibility for a margin of preference in Bid evaluation shall supply all information to satisfy the criteria for eligibility as described in ITB 33. |
|  |  | 13.8 | When Biding for more than one Contract under the slice and package arrangements, the Bidder must provide evidence that it meets or exceeds the sum of all the individual requirements for the slices or lots being applied for in regard to:- - average annual turnover; - particular experience including key production rates; - financial means, etc.; - personnel capabilities; and - Equipment capabilities. In case the Bidder fails to fully meet any of these criteria, it may be qualified only for those slices for which the Bidder meets the above requirement. |
| 14 | Documents Comprising the Technical Offer | 14.1 | The Bidder shall furnish a Technical Offer as stipulated in the Bid Data Sheet and in Section IV: Bid Submission Forms, in sufficient detail to demonstrate the adequacy of the Bidder’s proposal to meet the design and construction requirements of the Employer’s Requirements (Section X) and the completion time. |
| 15 | Forms of Bid | 15.1 | The Bidder shall complete the Bid Form furnished in the Biding Documents. The Bid Form must be completed without any alterations to its format and no substitute shall be accepted. |
|  |  | 15.2 | The documentary evidence of the Bidder’s eligibility to Bid shall establish to the Procuring Entity’s satisfaction that the Bidder, at the time of submission of its Bid, is from an eligible country as defined under ITB 3. |
| 16 | Bid Prices | 16.1 | The Contract shall be for the whole Works, as described in ITB 1.1, based on the Guaranteed Maximum Price in the Price Offer Form submitted by the Bidder and as defined in the Bid Data Sheet. |
|  |  | 16.2 | The Bidder shall fill in rates and prices for all items of the Works described in the Price Offer Form. Items for which no rate or price is entered by the Bidder will not be paid for by the Procuring Entity when executed and shall be deemed covered by the other rates and prices in the Price Offer Form. Upon award of the Contract, the successful Bidder shall be required to submit a detailed priced Bills of Quantities including detailed breakdown of the Contingency Sum. |
|  |  | 16.3 | Items that are not explicitly listed in the Price Offer Form shall be deemed to be included in the Contingency Sum in the Price Offer Form. On the other hand, if the Bidder introduces new items in the Price Offer Form that were not specified in the Biding documents, the new items, corresponding quantities and prices shall not be accepted and the Bid may be disqualified as being substantially non responsive. |
|  |  | 16.4 | All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of Bids, shall be included in the rates, prices, and total Bid price submitted by the Bidder. |
|  |  | 16.5 | The rates and price quoted by the Bidder shall be subject to adjustment during the performance of the Contract if provided for in the Bid Data Sheet and Special Conditions of Contract (SCC) of Contract and the provisions of 14 of the General Conditions of Contract. The Bidder shall submit with the Bid all the information required under the Special Conditions of Contract and 14 of the General Conditions of Contract. The Procuring Entity may require the Bidder to justify its proposed weighting. |
|  |  | 16.6 | As part of the financial offer, Bidder shall be required to specify Guaranteed Maximum Price which include the Bidder’s price for the design and construction under this contract. |
| 17. | Bid Currencies | 17.1 | The rates and prices shall be quoted by the Bidder entirely in Tanzania Shillings. Foreign currency requirements shall be indicated in the Bid Data Sheet as a percentage of the Bid price (excluding provisional sums). |
|  |  | 17.2 | The rates of exchange to be used by the Bidder in arriving at the local currency equivalent and the percentages mentioned in ITB 17.1 above shall be the selling rates for similar transactions established by the authority specified in the Bid Data Sheet prevailing on the date 28 days prior to the latest deadline for submission of Bids. These exchange rates shall apply for all payments so that no exchange risk will be borne by the Bidder. If the Bidder uses other rates of exchange, the provisions of ITB 31.1 shall apply. In any case, payments will be computed using the rates quoted in the Bid. |
| 18. | Bid Validity Period | 18.1 | Bids shall remain valid for the period specified in the Bid Data Sheet after the deadline for Bid submission Specified in ITB 23. A Bid valid for a shorter period shall be rejected by the Procuring Entity as non-responsive. |
|  |  | 18.2 | In exceptional circumstances, prior to expiry of the original Bid validity period, the Procuring Entity may request that the Bidders to extend the period of validity for a specified additional period. The request and the Bidders' responses shall be made in writing or by electronic mail. A Bidder may refuse the request without forfeiting its Bid security or causing to be executed its Bid securing declaration. A Bidder agreeing to the request will not be required or permitted to otherwise modify the Bid, but will be required to extend the validity of its Bid security or Bid Securing declaration for the period of the extension, and in compliance with ITB 19 in all respects. |
|  |  | 18.3 | In the case of fixed price contracts, if the award is delayed by a period exceeding sixty (60) days beyond the expiry of the initial Bid validity period, the contract price will be increased by a factor specified in the request for extension. The Bid evaluation shall be based on the Bid price without taking into consideration on the above correction. |
| 19. | Bid Security | 19.1 | Pursuant to ITB 12, unless otherwise specified in the Bid Data Sheet, the Bidder shall furnish as part of its Bid, a Bid Security in original form and in the amount and currency specified in the Bid Data Sheet or Bid Securing Declaration as specified in the Bid Data Sheet in the format provided in Section IV. |
|  |  | 19.2 | The Bid Security or Bid Securing Declaration is required to protect the Procuring Entity against the risk of Bidder’s conduct which would warrant the security’s forfeiture, pursuant to ITB 19.9. |
|  |  | 19.3 | The Bid security shall be denominated in the currency of the Bid or in another freely convertible currency, and shall be in one of the following forms: - a bank guarantee, an irrevocable letter of credit issued by a reputable bank located in the United Republic of Tanzania or abroad, in the form provided in the Biding documents or another form acceptable to the Procuring Entity and valid for thirty (30) days beyond the end of the validity of the Bid. This shall also apply if the period for Bid validity is extended. In either case, the form must include the complete name of the Bidder; or, - A cashier’s or certified cheque. - Another security if indicated in the Bid Data Sheet. |
|  |  | 19.4 | The Bid Security shall be in accordance with the Form of the Bid security included in Section IV or another form approved by the Procuring Entity prior to the Bid submission |
|  |  | 19.5 | The Bid Security shall be payable promptly upon written demand by the Procuring Entity in case any of the conditions listed in ITB 19.9 are invoked. |
|  |  | 19.6 | Any Bid not accompanied by a Bid Security in accordance with ITB 19.1 or 19.3 shall be rejected by the Procuring Entity as non-responsive, pursuant to ITB 29. |
|  |  | 19.7 | Unsuccessful Bidders’ Bid Security will be discharged or returned as promptly as possible as but not later than thirty (30) days after the expiration of the period of Bid validity prescribed by the Procuring Entity pursuant to ITB 41. |
|  |  | 19.8 | The successful Bidder’s Bid Security will be discharged upon the Bidder signing the contract, pursuant to ITB 41, and furnishing the performance security, pursuant to ITB 42. |
|  |  | 19.9 | The Bid Security may be forfeited: - if a Bidder - withdraws its Bid during the period of Bid validity specified by the Bidder on the Bid Form except as provided for in ITB 18.2; or - does not accept the correction of errors pursuant to 30; or - in the case of a successful Bidder, if the Bidder fails: - to sign the contract in accordance with ITB 41; or - to furnish performance security in accordance with ITB 42. |
|  |  | 19.10 | The Bid Security of a joint venture must be in the name of the joint venture submitting the Bid. |
|  |  | 19.11 | A Bidder shall be suspended from being eligible for Biding in any contract with the Procuring Entity for the period of time indicated in the Bid Security: (a) if the Bidder withdraws its Bid, except as provided in ITBs 18.2 and 30.2; or (b) in the case of a successful Bidder, if the Bidder fails within the specified time limit to: (i) sign the contract, or (ii) furnish the required performance security. |
| 20. | Alternative Bids by Bidders | 20.1 | Bidders shall submit offers that comply with the requirements of the Biding documents, including the basic Bidder’s technical design as indicated in the specifications, Drawings and Price Offer. Alternatives will not be considered, unless specifically allowed for in the Bid Data Sheet. If so allowed, ITB 20.2 and 32.3 shall govern. |
|  |  | 20.2 | When alternative times for completion are explicitly invited, a statement to that effect will be included in the Bid Data Sheet as will the method of evaluating different times for completion. |
|  |  | 20.3 | If so allowed in the Bid Data Sheet, Bidders wishing to offer technical alternatives to the requirements of the Biding documents must also submit a Bid that complies with the requirements of the Biding documents, including the basic technical design as indicated in the Employer’s Requirements and specifications. In addition to submitting the basic Bid, the Bidder shall provide all information necessary for a complete evaluation of the alternative by the Procuring Entity, including design calculations, technical specifications, breakdown of prices, proposed construction methods and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Procuring Entity. |
| 21. | Format and Signing of Bid | 21.1 | The Bidder shall prepare one original of the documents constituting the Bid as described in ITB 12 of these Instructions to Bidders, bound with the volume containing the Form of Bid, and clearly marked "ORIGINAL”. In addition, the Bidder shall submit copies of the Bid, in the number specified in the Bid Data Sheet, and clearly marked as "COPIES." In the event of discrepancy between them, the original shall prevail. |
|  |  | 21.2 | The original and the copy or copies of the Bid shall be typed or written in indelible ink and shall be signed by the Bidder or a person or persons duly authorized to sign on behalf of the Bidder. This authorization shall consist of a Power of Attorney as specified in the Bid Data Sheet and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid, except for un-amended printed literature, shall be initialed by the person or persons signing the Bid. |
|  |  | 21.3 | The Bid shall contain no alterations or additions, except those to comply with instructions, issued by the Procuring Entity, or as necessary to correct errors made by the Bidder, in which case such corrections shall be initialed by the person or persons signing the Bid. |
|  |  | 21.4 | The Bidder shall furnish information as described in the Form of Letter of Bid on commissions or gratuities, if any, paid or to be paid to agents relating to this Bid and to Contract execution if the Bidder is awarded the Contract. |

D. Submission of Bids

| 22. | Sealing and Marking of Bids | 22.1 | The Bidder shall enclose the original and each copy of the Technical Proposal in separate sealed envelopes, duly marking the envelopes as “TECHNICAL PROPOSAL and “ORIGINAL” and “COPY, as per ITB 21.1. These envelopes containing the original and the copies shall then be enclosed in one single envelope duly marking the envelope as “TECHNICAL PROPOSAL. Electronic copies of the Technical Proposal shall not contain any financial information. The Bid Security shall be enclosed together with the Technical Proposal. No reference should be made in the TECHNICAL SUBMISSION or its letter of Bid to any costs contained in the financial submission. Failure to respect any of these conditions may result in the rejection of the Bidders’ submission. Further details are provided in the Bid Data Sheet. |
| --- | --- | --- | --- |
|  |  | 22.2 | The Bidder shall enclose the original and the number of copies as per ITB 21.1, of the Price Offer in one single separate sealed envelope, duly marking the envelope as “PRICE OFFER ” and with a warning “Do Not Open With The Technical Proposal.” |
|  |  | 22.3 | The two envelopes shall then be enclosed in one single outer envelope The envelopes shall then be securely sealed in such a manner that opening and resealing cannot be achieved undetected. The inner and outer envelopes shall: a) be addressed to the Procuring Entity at the address given in the Bid Data Sheet; and - bear the Project name indicated in the Bid Data Sheet, the Invitation for Bids (IFB) title and number indicated in the Bid Data Sheet, and a statement: “DO NOT OPEN BEFORE,” to be completed with the time and the date specified in the Bid Data Sheet, pursuant to ITB 23.1. |
|  |  | 22.4 | In addition to the identification required in ITB 22.3, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to ITB 24, and for matching purposes under ITB 25. |
|  |  | 22.5 | If all envelopes are not sealed and marked required by ITB 22.4, the Procuring Entity shall assume no responsibility for the misplacement or premature opening of the Bid. |
|  |  | 22.6 | If the outer envelope discloses the Bidder's identity, the Procuring Entity will not guarantee the anonymity of the Bid submission, but this shall not constitute grounds for rejection of the Bid. |
| 23. | Deadline for Submission of Bids | 23.1 | The Bids shall be received by the Procuring Entity at the address specified under ITB 22.3 no later than the date and time specified in the Bid Data Sheet. |
|  |  | 23.2 | The Procuring Entity may, in exceptional circumstances and at its discretion, extend the deadline for the submission of Bids by amending the Biding documents in accordance with ITB 10, in which case all rights and obligations of the Procuring Entity and Bidders previously subject to the deadline will thereafter be subject to the new deadline. |
|  |  | 23.3 | The extension of the deadline for submission of Bids shall not be made later than the period specified in the Bid Data Sheet before the expiry of the original deadline. |
| 24 | Late Bids | 24.1 | The Procuring Entity shall not consider for evaluation any Bid that arrives after the deadline for submission of Bids, in accordance with ITB 23. |
|  |  | 24.2 | Any Bid received by the Procuring Entity after the deadline prescribed in ITB 23 will be declared late, rejected and returned unopened to the Bidder. |
| 25 | Modification and Withdrawal of Bids | 25.1 | A Bidder may modify or substitute or withdraw its Bid after it has been submitted, provided that written notice of the modification, including modification, substitution or withdrawal of the Bid, is received by the Procuring Entity prior to the deadline for submission of Bids. |
|  |  | 25.2 | The Bidder’s modification, substitution or withdrawal notice shall be prepared, sealed, marked, and dispatched in accordance with the provisions of ITB 22 and 23 with the outer and inner envelopes additionally marked “MODIFICATION” “SUBSTITUTION” or “WITHDRAWAL” as appropriate. The notice may also be sent by electronic mail, telex and facsimile but followed by a signed confirmation copy, postmarked no later than the deadline for submission of Bids. |
|  |  | 25.3 | Bids may only be modified by withdrawal of the original Bid and submission of a replacement Bid in accordance with ITB 25.1. Modifications submitted in any other way shall not be taken into account in the evaluation of Bids. |
|  |  | 25.4 | Bidders may only offer discounts to or otherwise modify the prices of their Bids by substituting Bid modifications in accordance with this ITB or included in the original Bid submission. |
|  |  | 25.5 | No Bid may be withdrawn, replaced or modified in the interval between the deadline for submission of Bids and the expiration of the period of Bid validity specified by the Bidder on the Form of Bid. Withdrawal of a Bid during this interval shall result in the Bidder’s forfeiture of its Bid security pursuant to the ITB 19.9. |

E. Opening and Evaluation of Bids

| 26. |  |  | Opening of Bids | 26.1 | Two Bid opening sessions shall be held. Technical Proposal Opening and Financial Offer Opening. The Procuring Entity will open all Bids including modifications, substitution or withdrawal notices made pursuant to ITB 25, in the presence of Bidders or their representatives who choose to attend, and other parties with a legitimate interest in the Bid proceedings, at the place, on the date and at the time specified in the Bid Data Sheet. The Bidders’ representatives present shall sign a register as proof of their attendance. |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 26.2 | Envelopes marked “WITHDRAWAL” shall be opened and read out first. Bids for which an acceptable notice of withdrawal has been submitted pursuant to ITB 25 shall not be opened but returned to the Bidder. If the withdrawal envelope does not contain a copy of the “Power of Attorney” confirming the signature as a person duly authorized to sign on behalf of the Bidder, the corresponding Bid will be opened. Subsequently, all envelopes marked "MODIFICATION" shall be opened and the submissions therein read out in appropriate detail. Thereafter all envelops marked ‘’SUBSTITUTION’’ shall be opened and the submission therein read out in appropriate detail. |
|  |  |  |  | 26.3 | At the initial Bid opening, only the Technical Proposal envelopes shall be opened one at a time. The Bidders' names, Bid modifications, the presence or absence of Bid security, Bid securing declaration and such other details as the appropriate Bid board may consider appropriate, will be announced by the Secretary of the Bid Board or his delegate at the opening. |
|  |  |  |  | 26.4 | Bids or modifications that are not opened and not read out at Bid opening shall not be considered further for technical evaluation, irrespective of the circumstances. |
|  |  |  |  | 26.5 | Bidders are advised to send in a representative with the knowledge of the content of the Bid who shall verify the information read out from the submitted documents. Failure to send a representative or to point out any un-read information by the sent Bidder’s representative shall indemnify the Procuring Entity against any claim or failure to read out the correct information contained in the Bidders Bid. |
|  |  |  |  | 26.6 | No Bid will be rejected at Bid opening except for late Bids which will be returned unopened to the Bidder, pursuant to ITB 24. |
|  |  |  |  | 26.7 | The Procuring Entity shall prepare minutes of the Bid opening, including the information disclosed to those present in accordance with ITB 26.3. The minutes of the Bid opening shall be furnished to the individual Bidders upon request. |
|  |  |  |  | 26.8 | The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and affect the record. A copy of the record shall be distributed to all the Bidders. |
|  |  |  |  | 26.9 | A copy of the minutes of the Bid opening shall be furnished to the individual Bidders upon request. |
|  |  |  |  | 26.10 | - On completion of the Technical Evaluation, a Public Financial Proposal Opening Session will be held to which all Bidders will be invited. The Financial Submissions of those Bidders achieving the score specified in the BDS in the Technical Evaluation will be opened and the lump sum price offered will be announced. The Financial Submissions of those Bidders who failed to meet the minimum Technical Evaluation scores will be returned un-opened to the Bidder. |
| 27. |  |  | Confidentiality | 27.1 | Information relating to the examination, clarification, evaluation, and comparison of Bids and recommendations for the award of a Contract shall not be disclosed to Bidders or any other persons not officially concerned with such process until the award to the successful Bidder has been announced. |
|  |  |  |  | 27.2 | Any effort by a Bidder to influence the Procuring Entity's processing of Bids or award decisions may result in the rejection of his Bid. |
|  |  |  |  | 27.3 | Notwithstanding ITB 27.2, from the time of Bid opening to the time of Contract award, if any Bidder wishes to contact the Procuring Entity on any matter related to the Biding process, he/she should do so in writing. |
| 28. |  | Clarification of Bids |  | 28.1 | To assist in the examination, evaluation, and comparison of Bids and post-qualifications of Bidders, the Procuring Entity may, at its discretion, ask any Bidder for clarification of its Bid including breakdown of prices. Any clarification submitted by a Bidder that is not in response to a request by the Procuring Entity shall not be considered. |
|  |  |  |  | 28.2 | The request for clarification and the response shall be in writing or by cable, or facsimile, but no change in the price or substance of the Bid shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the evaluation committee in the evaluation of the Bids in accordance with ITB 30. |
|  |  |  |  | 28.3 | From the time of Bid opening to the time of contract award if any Bidder wishes to contact the Procuring Entity on any matter related to the Bid it should do so in writing |
| 29. |  | Evaluation of Bids |  | 29.1 | Prior to the detailed evaluation of Bids, the Procuring Entity shall perform preliminary evaluation of Bids to determine whether each Bid; (a) meets the eligibility criteria defined in ITB 3; (b) has been properly signed in accordance with ITB 21; (c) is accompanied by the required securities in accordance with ITB 19; (d) meets the qualification criteria as specified in Section III Evaluation and Qualification Criteria; and (e) is substantially responsive to the requirements of the Biding documents. The Procuring Entity's determination of a Bid's responsiveness will be based on the contents of the Bid itself. |
|  |  |  |  | 29.2 | A substantially responsive Bid is one which conforms to all the terms, conditions, and specifications of the Biding documents, without material deviation or reservation. A material deviation or reservation is one that:- (a) affects in any substantial way the scope, quality, or performance of the design and construction of the works specified in the contract; (b) limits in any substantial way, inconsistent with the Biding documents, the Procuring Entity's rights or the Bidder's obligations under the Contract; or (c) if rectified, would affect unfairly the competitive position of other Bidders presenting substantially responsive Bids. |
|  |  |  |  | 29.3 | The Procuring Entity shall confirm that the documents and information specified under ITB 12, ITB 13 and ITB 14 have been provided in the Bid. If any of these documents or information is missing, or is not provided in accordance with the Instructions to Bidders, the Bid shall be rejected. |
|  |  |  |  | 29.4 | The Procuring Entity may waive any minor informality, nonconformity or irregularity in a Bid that does not constitute a material deviation, and that does not prejudice or affect the relative ranking of any Bidder as a result of the technical or commercial evaluation pursuant to ITB 28 and 30. |
|  |  |  |  | 29.5 | If a Bid is not substantially responsive, it will be rejected by the Procuring Entity and may not subsequently be made responsive by the Bidder by correction of the nonconformity. |
|  |  |  |  | 29.6 | The Procuring Entity shall confirm that the following documents and information have been provided in the Bid. If any of these documents or information is missing, or is not in accordance with the Instructions to Bidders, the Bid shall be rejected: - Form of Letter of Bid; - Information requested under ITB 13.3; - Information requested under ITB 13.4 if Bid is submitted by joint venture; - Information requested under ITB 13.5; - The Period of Bid Validity; - The Price Offer; - Written confirmation of authorization to commit the Bid; - Bid Security or Bid Securing Declaration; and - Any other information/data required by this Biding document as specified in the Bid Data Sheet. |
|  |  |  |  | 29.7 | The Procuring Entity shall examine the technical aspects of the Bid submitted in accordance with ITB 14, in particular, to confirm that all requirements of Section IV, Bid Submission Forms, Section VII, Price Offer Form, Section X, Employer’s Requirements, and Section XI, Location Plan, and have been met without any material deviation, reservation, or omission. |
|  |  |  |  | 29.8 | Bids determined to be substantial responsive to the qualification requirements in accordance with the ITB 29.2 shall be taken for detailed evaluation of the technical offer in accordance with the Section III – Evaluation and Qualification Criteria of the Biding Document. |
|  |  |  |  | 29.9 | Detailed evaluation of the technical offer shall be based on the technical offer submission Forms as described in ITB 14. These Forms shall be assessed and scored in accordance with scoring matrix provided in Section III. |
|  |  |  |  | 29.10 | Bids that found to meet the minimum technical evaluation scores shall be considered to be substantial responsive to the technical offer requirements in accordance with the Section III. These Bids shall be accepted by the Procuring Entity and invited for subsequent opening and evaluation of their respective Price Offer. Bids that do not meet the minimum technical evaluation score shall be rejected by the Procuring Entity. |
| 30. |  | Correction of Errors |  | 30.1 | As part of evaluation of Price Offer, Bids determined to be substantially responsive and that meet the minimum Technical evaluation score shall be checked for arithmetic errors. Arithmetic errors shall be corrected as follows:- - if there is a discrepancy between unit prices and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail, and the total price shall be corrected, unless in the opinion of the Procuring Entity there is an obvious misplacement of the decimal point in the unit price, in which the total price as quoted shall govern and the unit price shall be corrected; - if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and - Where there is a discrepancy between the amounts in figures and in words, the amount in words will govern. |
|  |  |  |  | 30.2 | The amount stated in the Bid will, be adjusted by the Procuring Entity in accordance with the above procedure for the correction of errors and, with, the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, its Bid will then be rejected, and the Bid security may be forfeited accordance with ITB 19.9. |
| 31. |  | Conversion to Single Currency |  | 31.1 | To facilitate evaluation and comparison, the Procuring Entity will convert all Bid prices expressed in the amounts in various currencies in which the Bid prices are payable to either: a) in Tanzania Shillings at the selling exchange rate established for similar transactions by the Bank of Tanzania or a commercial bank in the United Republic of Tanzania; or - A currency widely used in international trade, such as U.S. Dollars, at the selling rate of exchange published in the international press for the amount payable in foreign currency; and at the selling exchange rate established for similar transactions by the Bank of Tanzania in the United Republic of Tanzania for the amount payable in Tanzania Shillings. |
|  |  |  |  | 31.2 | The currency selected for converting Bid prices to a common base for the purpose of evaluation, along with the source and date of the exchange rate, are specified in the Bid Data Sheet. |
| 32. |  | Comparison of Bids |  | 32.1 | The Procuring Entity shall compares only the Bids determined to be substantially responsive in accordance with ITB 29. |
|  |  |  |  | 32.2 | In comparing the Bids, the Procuring Entity will determine for each Bid the evaluated Price Offer by adjusting the Bid Price as follows:- - making any correction for errors pursuant to ITB 30; - excluding provisional sums and the provision, if any, for contingencies in the Price Offer Form; - making appropriate adjustment for any other acceptable variations, deviations, or alternative offers submitted in accordance with ITB 20; - making an allowance for varying times of completion offered by Bidders, if permitted in the Bid Data Sheet and in the manner prescribed therein; - making appropriate adjustments to reflect discounts or other price modifications offered in accordance with ITB 32.5; and - Applying any discounts offered by the Bidder for the award of more than one Contract, if Biding for this Contract is being done concurrently with other contracts ( ITB 36.2). |
|  |  |  |  | 32.3 | The Procuring Entity reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Biding documents or otherwise result in unsolicited benefits for the Procuring Entity will not be taken into account in Bid evaluation. |
|  |  |  |  | 32.4 | The estimated effect of any price adjustment conditions under 14 of the General Conditions of Contract, during the period of implementation of the Contract, will not be taken into account in Bid evaluation. |
|  |  |  |  | 32.5 | In the case of several Lots, pursuant to ITB 32.2(f), the Procuring Entity will determine the application of discounts so as to minimize the combined cost of all the lots. |
|  |  |  |  | 32.6 | If the Bid, which results in the lowest Evaluated Bid Price, is seriously unbalanced or front loaded in relation to the Predetermined Bid Value of the items of work to be performed under the Contract, the Procuring Entity may require the Bidder to produce detailed price analysis for any or all items of the Price Offer Form, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, taking into consideration the schedule of estimated Contract payments, the Procuring Entity may require that the amount of the performance security set forth in ITB 42 be increased at the expense of the Bidder to a level sufficient to protect the Procuring Entity against financial loss in the event of default of the successful Bidder under the Contract |
| 33. |  | National Preferences |  | 33.1 | If so indicated in the Bid Data Sheet, domestic contractors may receive a margin of preference in Bid evaluation, for which this ITB shall apply. |
|  |  |  |  | 33.2 | Domestic Bidders shall provide all evidence necessary to prove that they meet the following criteria to be eligible for the margin of preference in the comparison of their Bids with those of Bidders who do not qualify for the preference. They should; - Be registered by relevant statutory bodies within the Zanzibar. - Be registered with the Zanzibar Public Procurment and Disposal of Public Asset for purposes of preference schemes; - Have at least fifty percent of the authorized capital of the company is owned either by the Government or by citizens of Tanzania; - Not subcontract more than ten (10) percent of the Contract price, excluding provisional sums to foreign contractors; - Have no arrangement whereby any major part of the net profits or other tangible benefits of the domestic company will accrue or be paid to persons not citizens of the United Republic of Tanzania or companies which would not be eligible under this ITB. |
|  |  |  |  | 33.3 | Joint ventures between domestic and foreign firms may be eligible for the margin of preference provided the domestic partner or partners:- - individually satisfy the above criteria of eligibility for the preference; - demonstrate a beneficiary interest of no less than 20 percent in the joint venture, as demonstrated by the profit and loss sharing provisions of the joint venture agreement; and - will, under the arrangements proposed, carry out at least ten percent of the Works, measured in terms of value, which shall exclude any materials or plant which are to be directly imported by the domestic partner(s) (always provided that the domestic partner or partners are qualified to carry out that amount of work, in accordance with the criteria of ITB 13.3). |
|  |  |  |  | 33.4 | The following procedure will be used to apply the margin of preference: - Responsive Bids will be classified into the following groups: - Group A: Bids offered by domestic Bidders and joint ventures meeting the respective criteria of ITB 33.2; - Group B: Bids offered by joint ventures of domestic and foreign firms meeting the criteria of ITB 33.3 above; or - Group C: Bids offered by foreign contractors. - For the purpose of further evaluation and comparison of Bids only, an amount equal to a percentage specified in the Bid Data Sheet of the evaluated Bid Prices determined in accordance with ITB 32.2(a), (b), and (d), will be added to all Bids classified in Group B. |
|  |  |  |  | 33.5 | Alternative offers, where solicited or permitted, will be evaluated separately, in accordance with the provisions of ITB 20, and shall be subject to the margin of preference in accordance with ITB 33.4 |
| 34. |  | Determination of Lowest Evaluated Bid Price |  | 34.1 | The Bid with the lowest evaluated price from among those which are eligible, compliant and substantially responsive shall be the lowest evaluated Price Offer as specified in the Bid Data Sheet. |
| 35. | Post-qualification of Bidder |  |  | 35.1 | If specified in the Bid Data Sheet, Post-qualification shall be undertaken. |
|  |  |  |  | 35.2 | - Where the Bid price of the lowest evaluate Bidder is considered to be abnormally low, the PE shall perform price analysis as part of the post-qualification. The following process shall apply: - The PE may reject a Bid if the PE has determined that the price in combination with other constituent elements of the Bid is abnormally low in relation to the subject matter of the procurement (scope of works or services) and raise concerns with the PE as to the ability of the Bidder that presented that Bid to perform the contract. - Before rejecting an abnormally low Bid the PE shall: request the Bidder an explanation of the Bid or of those parts which it considers contribute to the Bid being abnormally low; take account of the evidence provided in response to a request in writing or in electronic forms that provide record of the content of communication; and subsequently verify the Bid or parts of the Bid being abnormal - The decision of the PE to reject a Bid and reasons for the decision shall be recorded in the procurement proceedings and promptly communicated to the Bidder concerned; - The Accounting Officer (PE) shall seek the approval of the Authority prior to rejecting a Bid; - Neither the Authority nor the PE shall incur liability solely by rejecting abnormally Bid; and - An abnormally low Bid means, in the light of the PE’s estimate and of all the Bids submitted, the Bid appears to be abnormally low by not providing a margin for normal levels of profit. |
|  |  |  |  | 35.3 | The determination will take into account the Bidder’s financial, technical, and production capabilities. It will be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 3 [Eligibility of Bidders], as well as such other information as the Procuring Entity deems necessary and appropriate. Factors not included in these Biding Documents shall not be used in the evaluation of the Bidders’ qualifications as specified in the BDS |
|  |  |  |  | 35.4 | A Procuring Entity may seek independent references of a Bidder and the results of reference checks may be used in determining award of contract. |
|  |  |  |  | 35.5 | In case of a foreign company, a Procuring Entity shall seek independent reference of legal existence of a Bidder from Tanzania diplomatic missions abroad or from any other reliable source. |
|  |  |  |  | 35.6 | An affirmative determination Shall be a prerequisite for award of the Contract to the lowest evaluated Bidder. A negative determination will result in rejection of the Bidder's Bid, in which event the Procuring Entity will proceed to the next-lowest evaluated Bidder to make a similar determination of that Bidder's capabilities to perform satisfactorily. |

F. Award of Contract

| 36. | Criteria of Award | 36.1 | Subject to ITB 38, the Procuring Entity will award the Contract to the successful Bidder whose Bid has been determined to be substantially responsive to the Biding Documents and who has offered the lowest Evaluated Bid Price, provided that such Bidder has been determined to be (a) eligible in accordance with the provisions of ITB 3, and (b) qualified in accordance with the provisions of ITB 13. |
| --- | --- | --- | --- |
|  |  | 36.2 | If, pursuant to ITB 13.8, this Contract is being let on a “slice and package” basis, the lowest evaluated Price Proposal will be determined when evaluating this Contract in conjunction with other Contracts to be awarded concurrently, taking into account any discounts offered by the Bidders for award of more than one Contract. |
| 37. | Negotiations | 37.1 | Negotiations may be undertaken with the lowest evaluated Bid relating to the following areas: - a minor alteration to the technical details of the Employer’s Requirements; - reduction of quantities for budgetary reasons, where the reduction is in excess of any provided for in the solicitation documents; - a minor amendment to the special conditions of Contract; - finalizing payment arrangements; - mobilization arrangements; - agreeing final delivery or work schedule to accommodate any changes required by the Procuring Entity; - the methodology or staffing; or - clarifying details that were not apparent or could not be finalized at the time of Biding; - the Bid price may be negotiated for purposes of reduction. - Other issues as may be specified in the Bid Data Sheet. |
|  |  | 37.2 | Where negotiation fails to result into an agreement, the Procuring Entity may invite the next ranked Bidder for negotiations. Where negotiations are commenced with the next ranked Bidder, the Procuring Entity shall not reopen earlier negotiations. |
| 38. | Procuring Entity Right to Accept any Bid and to Reject any or all Bids | 38.1 | Notwithstanding ITB 36, the Procuring Entity reserves the right to accept or reject any Bid, and to cancel the Biding process and reject all Bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or Bidders or any obligation to inform the affected Bidder or Bidders. |
|  |  | 38.2 | Notice of the rejection of all Bids shall be given promptly to all Bidders that have submitted Bids. |
|  |  | 38.3 | The Procuring Entity shall upon request communicate to any Bidder the grounds for its rejection of its Bid but is not required to justify those grounds. |
| 39. | Procuring Entity Right to Vary Quantities at the Time of Award | 39.1 | The Procuring Entity reserves the right at the time of Contract award to increase or decrease the scope of services originally specified in these Biding Documents provided this does not exceed by the percentage indicated in the Bid Data Sheet, without any change in unit price or other terms and conditions of the Bid and Biding Documents. |
| 40. | Notification of Award | 40.1 | Prior to awarding of the contract, the Procuring Entity shall issue a notice of intention to award the contract to all Bidders who participated in the Bid in question giving them seven (14) days within which to submit complaints to the Procuring Entity thereof, if any. |
|  |  | 40.2 | Where no complaints have been lodged, the Bidder whose Bid has been accepted will be notified of the award by the Procuring Entity prior to expiration of the Bid validity period in writing or in electronic forms that provide record of the content of communication. The Letter of Acceptance will state the sum that the Procuring Entity will pay the successful Bidder in consideration for the execution of the scope of works as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price). |
|  |  | 40.3 | The notification of award will not constitute the formation of the Contract. Only after the Bidder has furnished evidence of registration with relevant statutory bodies within the country and furnishing the Performance Security in accordance with ITB 42 and signing the Contract in accordance with ITB 41.2 shall the Contract be in force |
|  |  | 40.4 | Upon the successful Bidder’s furnishing of the performance security pursuant to ITB 42, the Procuring Entity will promptly notify each unsuccessful Bidder, notify the name of the winning Bidder and the Contract amount and will discharge the Bid security or Bid securing declaration of the unsuccessful Bidders pursuant to ITB 19. |
|  |  | 40.5 | If, after notification of award, a Bidder wishes to ascertain the grounds on which its Bid was not selected, it should address its request to the Procuring Entity. Procuring Entity will promptly respond in writing to the unsuccessful Bidder citing grounds for rejection of its Bid without disclosing information about other Bidders. |
| 41. | Signing of Contract | 41.1 | Promptly after notification, Procuring Entity shall send the successful Bidder the Agreement and Special Conditions of Contract, incorporating all agreements between the parties obtained as a result of Contract negotiations. |
|  |  | 41.2 | Within fourteen (14) days of receipt of the Contract Agreement Form, the successful Bidder shall sign and date the Contract and return it to the Procuring Entity. |
|  |  | 41.3 | Upon the furnishing by the successful Bidder of the Performance Security, pursuant to Instructions to Bidders ITB 42, the Procuring Entity will promptly notify the other Bidders that their Bids have been unsuccessful and will notify the name of the winning Bidder to each unsuccessful Bidder and will discharge the Bid security of the unsuccessful Bidders pursuant to ITB 19. |
|  |  | 41.4 | - If, after notification of award, a Bidder wishes to ascertain the grounds on which its Bid was not selected, it should address its request to the Procuring Entity. Procuring Entity will promptly respond in writing to the unsuccessful Bidder citing grounds for rejection of its Bid without disclosing information about other Bidders. |
| 42. | Performance Security | 42.1 | Within fourteen (14) working days after receipt of the Letter of Acceptance, the successful Bidder shall deliver to the Procuring Entity a Performance Security in the amount and in the form stipulated in the Bid Data Sheet and the Special Conditions of Contract (SCC) of Contract, denominated in the type and proportions of currencies in the Letter of Acceptance and in accordance with the Conditions of Contract. |
|  |  | 42.2 | If the Performance Security is provided by the successful Bidder, it shall be in the form specified in the BDS which shall be in any of the following - cash, certified cheque, cashier’s or manager’s cheque, or bank draft; - irrevocable letter of credit issued by a reputable commercial bank or in the case of an irrevocable letter of credit issued by a foreign bank, the letter shall be confirmed or authenticated by a reputable local bank; - bank guarantee confirmed by a reputable local bank or, in the case of a successful foreign Bidder, bonded by a foreign bank; or - surety bond callable upon demand issued by any reputable surety or insurance company. - Any Performance Security submitted shall be enforceable in the United Republic of Tanzania. |
|  |  | 42.3 | Failure of the successful Bidder to comply with the requirement of ITB 42.1 shall constitute sufficient grounds for the annulment of the award and forfeiture of the Bid security, in which event the Procuring Entity may make the award to the next lowest evaluated Bidder or call for new Bids. |
| 43. | Advance Payment | 43.1 | The Procuring Entity will provide an Advance Payment upon the bidders request as stipulated in the Conditions of Contract, subject to a maximum amount, as stated in the Bid Data Sheet. The Advance Payment request shall be accompanied by an Advance Payment Security (Guarantee) in the form provided in Section IV. For the purpose of receiving the Advance Payment, the Bidder shall make an estimate of, and include in its Bid, the expenses that will be incurred in order to commence work. These expenses will relate to the purchase of equipment, machinery, materials, and on the engagement of labour during the first month beginning with the date of the Procuring Entity’s “Notice to Commence” as specified in the Special Conditions of Contract. |
| 44. | Adjudicator | 44.1 | The Procuring Entity proposes the person named in the Bid Data Sheet to be appointed as Adjudicator or under the Contract, at fees specified in the Bid Data Sheet, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Letter of Acceptance, the Procuring Entity has not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed by the Appointing Authority designated in the Special Conditions of Contract (SCC) of Contract at the request of either party. |
| 45. | Fraud Corruption, Coercion, Collusion, Fraudulent and Obstructive Practices | 45.1 | Revolutionary Government of Zanzibar requires that Procuring entities (including beneficiaries of Government funded projects and procurement) as well as Bidders/Suppliers/Contractors under Government financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. (a) defines, for the purpose of this provision, the terms set forth below as follows:- (i) “corrupt practice” means the offering, giving receiving or soliciting of anything of value to influence the action of a public officer in the procurement process or contract execution; (ii) “coercive practice” means impairing or harming, or threatening to impair or harm directly or indirectly, any party or the property of the party for the purpose of influencing improperly the action or that party in connection with public procurement or in furtherance of corrupt practice or fraudulent practice; (iii) collusive practices” means impairing or harming, or threatening to impair or harm directly or indirectly, any part or the property of the Party for the purpose of influencing improperly the action or a part or in connection with public procurement or government contracting or in furtherance of a corrupt practice or a Fraudulent Practice (iv) “fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Government or a public body and includes collusive practices among Bidders, prior to or after submission designed to establish Bid prices at artificial non-competitive levels and to deprive the Government of the benefits of free and open competition; (v) “obstructive practice” means acts intended to materially impede access to required information in exercising a duty under this Act; (b) Will reject a proposal for award if it determines that the Bidder recommended for award has engaged in corrupt, coercive, collusive, fraudulent or obstructive practices in competing for the contract; (c) In pursuit of the policy defined in ITB 45.1 [Corruption, Coercion, Collusion, Fraudulent or Obstruction Practices] the Government/Financing Institution will declare mis-procurement and cancel the portion of the funds allocated to a contract for goods, works, or services if it at any time determines that corrupt, coercive, collusive, fraudulent or obstructive practices were engaged in by representatives of the Procuring Entity or approving authority or of a beneficiary of the funds furring the procurement or the execution of that contract, without the Procuring Entity or approving authority having taken timely and appropriate action satisfactory to the Government of the united Republic of Tanzania/Financing Institution to remedy the situation (d) Declare a firm ineligible for a period of ten years, to be awarded a public-financed contract if it at any time it determines that the firm has engaged in corrupt, coercive, collusive, fraudulent or obstructive practices in competing for, or in executing, a public – financed contract |
|  |  | 45.2 | Revolutionary Government of Zanzibar reserves the right, where a firm has been found by a foreign country, international organization or other foreign organization to have engaged in corrupt or fraudulent practice, to declare that such a firm is ineligible, for a period of ten years to be awarded a public financed Contract in the Revolutionary Government of Zanzibar . |
|  |  | 45.3 | Any communication between the Bidder and the Procuring Entity related to matters of alleged fraud or corruption must be made in writing. |

- Review of Procurement Decisions

| 46. | Right to review | 46.1 | A Bidder who is aggrieved by a decision of a Procuring Entitymay make complaints in accordance with procedures prescribed in PART EIGHT (VIII) of the Public Procurement Act No 2 of 2025. |
| --- | --- | --- | --- |

# Section II

# Bid Data Sheet

# (BDS)

# Bid Data Sheet (BDS)

| BDS |  |  | ITB | Description |
| --- | --- | --- | --- | --- |
| A. Introduction |  |  |  |  |
| 1. |  |  | 1.1 | The Employer is (insert name of the PE) The Project is: (Briefy description of the Project) - Identification Number of the Contract: (insert number of Bid) |
| 2 |  |  | 2.1 | (insert name of the financial) has provided funds for the project. Financial year when the project will be carried out is: (financial year) The works under the Contract: (description of the project) |
|  |  |  | 2.2 | Payment will be done by: (currency of the payment) |
| 3 |  |  | 3.1 | - In case of Joint venture, consortium or association all parties shall be jointly and severely liable. - For purposes of clarity the (insert part which will lead company) shall be the Lead Member of the JV, Consortium or Association. |
| 4. |  |  | 7.3 | The site visit shall be held on (insert location) after Pre- bid meeting, The pre-Bid meeting shall be held on Day: Date: Time: |
|  |  |  | 7.5 | The minutes of the pre-Bid meeting will be transmitted within (insert number of days) days |
| B. Biding Documents |  |  |  |  |
| 5. | 8.2 |  |  | The number of copies of the Bid to be completed and returned shall be one original through www.zppra.go.tz in (eproz) or link eprocurement .zppra.go.tz. |
| 6. | 9.1 |  |  | Address for clarification of Biding Document is (insert address) |
|  | 9.2 |  |  | Period to Respond to request for clarification by the Procuring Entity(insert number of days) Deadline for submission of request for clarification: [insert number of days which is not less than seven (7) days] before the deadline for submission of Bids |
| C. Preparation of Bids |  |  |  |  |
| 7. |  | 11.1 |  | Language of Bid is (insert language) |
| 8. |  | 12.1 (i) |  | Other information or materials required to be completed and submitted by Bidder |
| 9. |  | 13.3 |  | Bidders must be registered by Public Procurement and Disposal of Public Assets Authority Zanzibar (ZPPRA) and other relevant boards/authorities listed below: - Contractors Registration Board - Zanzibar Revenue Board (ZRB) - Zanzibar Business and property registration Agency (BPRA) - Occupational safety and Health Authority (OSHA) - Power of Attoney - Litigation History - Anti biribery and Memorandoum of the company - Sign all pages - Bussiness Linceses - …………………. List all other required bidder |
|  |  | 13.3(b) |  | The total monetary value of building works performed for each of the last (insert years and amount) |
|  |  | 13.3(c) |  | Experience in Design and Construction at least one for the last (insert number of years) |
|  |  | 13.3(d) |  | Major Items of equipment proposed to carry out the contract; Please enter list of equipment.. |
|  |  | 13.3(j) |  | Litigation history (insert number of years) |
|  |  | 13.3(k) |  | Information regarding labour, occupational health and safety records of the company for the last (number of years) |
|  |  | 13.3(l) |  | Maximum percentage for subcontracting components of works is …………. |
|  |  | 13.4 |  | The qualification data required from Bidders in ITB 13.4 are modified as follows: |
|  |  | 13.5 |  | The qualification criteria in ITB 13.5 are modified as follows: |
|  |  | 13.5 (a) |  | The amount of Average Annual Volume of construction is ……………. Period for which annual volume of construction is to be submitted is ……………. |
|  |  | 13.5 (b) |  | Minimum Experience as a prime contractor must be …………… |
|  |  |  |  | Minimum Experience of the Bidder’s design firm(s) in Construction Works: ……….. |
|  |  | 13.5 (d) |  | The essential equipment to be made available for the Contract by the successful Bidder shall be as specified in 13.3(d) above and the Evaluation and Qualification Criteria (Section III) |
|  |  | 13.5 (e) |  | Period of experience for the key personnel ………….. |
|  |  | 13.5 (f) |  | The minimum amount of access to funds/credit facilities net of other contractual commitments of the successful Bidder shall be: …………………… |
|  |  | 13.6 |  | For the joint venture the partner in charge must meet the qualification criteria stated in Section III of the Biding document. Subcontractor’s experience and resources will be taken into account in determining the Bidder’s compliance with the qualifying criteria |
| 10. |  | 14 |  | As part of the Technical Offer submission the Bidder shall submit the documents listed in the Part C of Section IV –Bid Submission Forms. |
|  |  | 16.1 |  | Guaranteed Maximum Price is the Contract Price as defined in 14.1 of the GCC which shall not exceed the Guaranteed Maximum Price in the Price Offer Form. |
| 11. |  | 16.4 |  | Price adjustment shall …………. |
| 12. |  | 17.1 |  | Percentage of the amount of Bid price payable to the Bidder in foreign currency shall be:………………. |
|  |  | 17.2 |  | The rates of exchange to be used by the Bidder shall be those established by the Bank of Tanzania prevailing on 28 days before deadline of submission. |
| 13. |  | 18.1 |  | The period of Bid validity shall be …………….. after the deadline for Bid submission. |
| 14 |  | 19.1 |  | Bidder shall furnish a Bid Security in the form of Bank Guaranteeas provided in Section VII Forms of Security. The amount of Bid security shall be …………………………. Bid Securing Declaration shall not be acceptable in place of Bid Security |
|  |  | 19.3 |  | Another form of Bid Security if required: …….. |
| 15 |  | 20.1 |  | Alternative Bids to the requirements of the Biding documents will be permitted. ………. |
|  |  | 20.2 |  | Alternative time for completion ………….. |
|  |  | 20.3 |  | Technical alternative to the requirements of the Tendrering if required: …………. |
| 16. |  | 21.1 |  | In addition to One (1) original of the Technical Proposal including the completed Technical Schedules. Additionally, Bidders must include their Program and Schedule in MS Project or similar in the Technical Submission. In addition to the One (1) original of the Price offer, the number of required copies is: ………………. |
|  |  | 21.2 |  | The written authorization of Bidder: Project Specific Power of Attorney (SPOA) must contain names and signature of the Attorney. The Bidder must use the format of SPOA provided in this Biding Document in Section IV A of this document |

| D. Submission of Bids |  |  |  |
| --- | --- | --- | --- |
| 17 |  | 22.1 | The Bid must be submitted in two separate envelopes, comprising a Technical Submission and Price offer Submission. Both envelopes should be sealed in one outer envelope clearly marked with the Bid reference, ………………………………... and be clearly marked “DO NOT OPEN BEFORE insert date. Technical submission should contain (One (1) original through www.zppra.go.tz in (eproz portal) Note: The Technical Submission envelope must also contain the Bid Security in the form and format specified in Section IV “Biding Forms” No reference should be made in the Technical Submission or its Letter of Bid to any costs contained in the price offers submission. Failure to respect any of these conditions may result in the rejection of the Bidders’ submission. |
|  |  | 22.2 | Price offers Submission contain One (1) original through www.zppra.go.tz in (eproz portal) Price offers Submission must include Form of Letter of Price Offer, Price Offer Form and Cash Flow Projections linked to project milestones signed by the authorized representative. No technical information is required in the financial submission. |
|  |  | 22.3(a) | The Procuring Entity’s address for the purpose of Bid submission is: - (insert address) |
|  |  | 22.3(b) | Name of the project to be specified in the Bid submission envelope is: BID NO …………………………………………… The time and date for submission of Bids shall be: ………………………….. |
| 18. |  | 23.1 | The deadline for submission of Bids shall be: ……………………………….. |
|  |  | 23.3 | Extension of the deadline for submission of Bids shall be made Seven (7) days before the submission date. |
| E. Opening and Evaluation of Bids |  |  |  |
| 19. | 26.1 |  | - The time and place for opening of the Bids including modifications - (insert address) - Opening will be within 30 minutes immediately after the submission deadline time. This will be only for Technical Submissions only. - Price offer opening will be after evaluation and for those who will meet the minimum Technical Evaluation scores only. |
| 20. | 29.6 (i) |  | List any other information/data required: ……………… |
| 21. | 31.2 |  | The currency that shall be used for Bid evaluation and comparison purposes to convert all Bid prices expressed in various currencies is Tanzanian Shillings. The source of exchange rate shall be: Bank of Tanzania The date of exchange rate shall be: …………………….. |
| 22. | 32.2 (d) |  | Bid price will / will not be adjusted by making an allowance for varying times of completion |
| 23. | 33.1 |  | Domestic contractors will receive a margin of preference in Bid evaluation. |
|  | 33.4(b) |  | The margin of preference applicable shall be …………………………. |
| 24. | 34.1 |  | Determination of lowest evaluated Price Offer shall include all Contractors’ obligations plus contingencies if included in the Price Offer Form. |
| 25. | 34.1 |  | Post- qualification: state Applicable or Not applicable |
| F. Award of Contract |  |  |  |
| 26. |  | 39.1 | Percentage for quantity increase or decrease is (insert percent but not more than 20%) |
| 27. |  | 42.1 | The Performance Security shall be (insert percent but not exceed fifteen percent (15%) of Accepted Contract Amount) |
| 28. |  | 43.1 | The Advance Payment shall be limited …….% of Accepted Contract Amount upon signing of the Contract and submission of an acceptable Advance Payment Bank Guarantee for the …….% of the contract amount and Acceptable Performance Security. |
| 29. |  | 44.1 | The adjudicators shall be as per General Conditions of Contract The Adjudicators shall form a team of One (1) member of Dispute Adjudication Board (DAB) as specified in the General Conditions of Contract of this Biding document. |

# Section III

# Evaluation and Qualification Criteria

# Evaluation and Qualification Criteria

This Section contains evaluation and qualification criteria that shall be used in the preliminary and detailed evaluation of Bids. The section also provides the evaluation process and framework for preliminary and detailed evaluation of Bids. Further, the framework that shall be used to score the technical offer is provided with the explanation notes of the score.

Bidder is required to submit all the requirements of the Biding Documents in order to demonstrate its qualifications. All submitted documents must be in the standard format as provided in Section IV – Biding Forms.

A.	Eligibility and Qualifications

Bids shall be evaluated first to shall first establish that the Bidders meet the eligibility and qualification criteria in accordance with the eligibility and qualifications criteria set out in this section:

1.1.	Eligibility

1.2	Historical Contract Performance

1.3	Financial Situation

1.4	Experience - general, similar and specific - as it relates to both design and construction of similar projects.

Bids that shall be determined not to comply with the eligibility requirements and financial and technical qualifications criteria shall not be considered for detailed evaluation of technical offer.

| Factor | 1.1 Eligibility |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Bidder |  |  |  |  |
|  |  | Single Entity | Joint Venture or Other Consortium |  |  |  |
|  |  |  | All members combined | Each member | At least one member |  |
| ## 1.1.1 Conflict of Interest | No conflicts of interests per ITB ITB 4.1. | Must meet requirement | Existing or intended joint venture or other consortium must meet requirement | Must meet requirement | N / A | Form of Letter of Bid |
| ## 1.1.2 Ineligibility | Not having been deemed ineligible based on any criteria set forth in ITB ITB 4.2 | Must meet requirement | Existing or intended joint venture or other consortium must meet requirement | Must meet requirement | N / A | Form of Letter of Bid |
| ## 1.1.3. Government Owned Entity | Compliance with conditions of ITB ITB 4.3. | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Form EL 1.1 and EL 1.2 |

| Factor | 1.2. Historical Contract Non-Performance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Bidder |  |  |  |  |
|  |  | Single Entity | Joint Venture or Other Consortium |  |  |  |
|  |  |  | All members combined | Each member | At least one member |  |
| ## 1.2.1. History of Non-performing Contracts | Non-performance of a contract did not occur within the last (insert number of years) years prior to the deadline for Bid submission based on all information on fully settled disputes or litigation. A fully settled dispute or litigation is one that has been resolved in accordance with the dispute resolution mechanism under the respective contract, and where all appeal instances available to the Bidder have been exhausted. | Must meet requirement by itself or as member to past or existing joint venture or other consortium | N / A | Must meet requirement by itself or as member to past or existing joint venture or other consortium | N / A | Form: Contract Performance |
| ## 1.2.2. Failure to Sign a Contract | Failure to sign a contract after submitting a Bid security has not occurred in the past (insert number of years) years. Any deviation should be explained in the enclosed Contract Non-Performance form. | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Form: Contract Performance |
| ## 1.2.3. Pending Litigation | All pending litigation shall in total not represent more than ten percent (10%) of the Bidder’s net worth and shall be treated as resolved against the Bidder. | Must meet requirement by itself or as member to past or existing joint venture or other consortium | N / A | Must meet requirement by itself or as member to past or existing joint venture or other consortium | N / A | Form: Pending Litigation |

| Factor | 1.3. Financial Situation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Bidder |  |  |  |  |
|  |  | Single Entity | Joint Venture or Other Consortium |  |  |  |
|  |  |  | All members combined | Each member | At least one member |  |
| ## 1.3.1. Historical Financial Performance | Submission of audited financial statements prepared in accordance with International Financial Reporting Standards (IFRS) and International Accounting Standards (IAS) as promulgated by the International Federation of Accountants (IFAC) or National Accounting Standards based on IAS, for the last (insert number of years) consecutive years and the Bidder must have obtained an unqualified audit opinion for each of the year’s financial statements from an internationally recognized auditing body acceptable to the Procuring Entity to demonstrate: (a) Current soundness of the Bidder’s financial position and its prospective long-term profitability. (i) Average coefficient of Current ratio (Current Assets/Current Liabilities) ≥ 0.9 (ii)Average coefficient of Debt ratio (Total Debt / Total Assets) ≤ 0.75 (b) Average coefficient of Interest Coverage ratio (Current earnings before interest and taxes/total interest payable on bonds and contractual debt) ≥ 5.0 (c) Average coefficient of Debt-Equity ratio (Total liabilities/Total Net Worth) ≤ 3.0 | Must meet the Current Ratio requirement and at least 1 of the other ratio requirements | N / A | Must meet the Current ratio and at least 1 of the other ratio requirements | N / A | Form: Financial Situation, with attachments |
| ## 1.3.2 Average Annual Construction Turnover | Minimum average annual construction turnover of [insert amount] or equivalent, calculated as total certified payments received for contracts in progress or completed, within last (insert number of years) years. | Must meet requirement | N/A | N/A | Must meet 100% of the requirement | Form: Average Annual Construction Turnover |
| ## 1.3.3 Financial Resources | ### Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet: ### (i) Access to fund or credit facility amount of [insert amount] or equivalent; and ### (ii) The overall cash flow requirements for this Contract and its current commitments. | Must meet requirement | N/A | N/A | Must meet 100% of the requirement | Forms: Financial Resources; Current Contract Commitments/Works in Progress |

| Factor | 1.4. Experience |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria |  |  |  |  | Documentation Required |
|  | Requirement | Bidder |  |  |  |  |
|  |  | Single Entity | Joint Venture or Other Consortium |  |  |  |
|  |  |  | All members combined | Each member | At least one member |  |
| ## 1.4.1 General Design Experience | Experience under contracts in the role as a design Team (as a minimum this should include architectural – including interior design, structural, quantity surveying and services engineering) for at least the last (insert number of years) years prior to Bid submission deadline, and with activity in at least (insert number of months/years) each year. | Must meet requirement | N/A | N/A | Must meet requirement | Form: General Design Experience |
| ## 1.4.2 Similar Design Experience | ## Participation as designer/design Team (as a minimum this should include architectural including interior design, structural and services engineering, quantity surveying) in at least one (1) contracts each with a value of works of at least [insert amount] or equivalent, within the last (insert number of years) years, that have been successfully and substantially completed and that are similar to the proposed Works. Similarity shall be based on the physical size, complexity, or other characteristics as described in Section X Employer’s Requirements. ## The Employer may consider special cases where the Bidder has undertaken fewer numbers of larger similar projects. | Must meet requirement | N/A | N / A | Must meet requirement for all characteristics | Form: Similar Design Experience |
| ## 1.4.3 Specific Design Experience in Key Activities | ### For the above or other contracts executed during the period stipulated in 1.4.2 above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand | Must meet requirements | N/A | N / A | Must meet requirements | Form: Specific Design Experience in Key Activities |
| ## 1.4.4. General Construction Experience | Experience under contracts in the role of Contractor or Management Contractor for at least the last (insert number of years) years prior to Bid submission deadline, and with activity in at least (insert number of months/ years)each year. | Must meet requirement | N/A | N/A | Must meet requirement | Form: General Construction Experience |
| 1.4.5 Similar Construction Experience | ### Participation as Contractor or Management Contractor, in at least one (1) contracts each with a value of works of at least [insert amount]or equivalent within the last (insert number of years) years, that have been successfully and substantially completed and that are similar to the proposed Works. Similarity shall be based on the physical size, complexity, methods, technology or other characteristics as described in Section X, Employer’s Requirements. ### The Employer may consider special cases where the Bidder has undertaken fewer numbers of larger similar projects. | Must meet requirement | N/A | N / A | Must meet requirement | Form: Specific Construction Experience |
| 1.4.6 Specific Construction Experience in Key Activities | For the above or other contracts executed during the period stipulated in 1.4.5 above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand | Must meet requirements | N/A | N / A | Must meet requirements | Form: Specific Construction Experience in Key Activities |

B:	Preliminary Evaluation of Bids

Preliminary evaluation of Bids shall be conducted in two steps. Step 1 involves the determination of compliance of Bid to the submission requirements of the Biding Document. Bids shall be examined whether they contain all the required documents in accordance with; ITB    3 and 4,    12,   ITB 13.3,   ITB 13.4,   ITB 13.5 and    14 complete and submitted in the required format of Section IV – Bid Submission Forms.

Step 2 involves the evaluation of the submitted documents (in accordance with ITB   ITB 13.5) to determine the responsiveness of the Bids against the qualification criteria provided in Table 1.2, 1.3 and 1.4 of this section and ITB   ITB 13.5.

(a) 	Step 1: Compliance to Bid Submission Requirements

The purpose of this step shall be to examine the completeness of the Bids. All Bid submission forms must be completely filled, properly signed by the authorised personnel and submitted together with the Bid in the required format. Bids that shall successfully pass at this step shall be taken to Step 2: Determination of Responsiveness against qualification criteria.

| Table 1.5(a)– Preliminary Evaluation - Step 1: Compliance to the Bid Submission Requirements |  |  |
| --- | --- | --- |
| BID No. |  |  |
| Substantial Compliance (are the respective documents submitted/forms filled?) |  | Submitted Yes/No |
| 1.0 | Form of Letter of Bid submitted in accordance with ITB 15, in the required format as provided in Section IV and properly signed by the authorized personnel in accordance with ITB 21. |  |
|  | Submitted Bid in two separate sealed envelopes, first envelope containing Technical Proposal and second envelope containing Price Offer in accordance with ITB 22. |  |
| 2.0 | If Bid is submitted by a Joint Venture, Consortium or Association the following requirements must be submitted with the Bid in accordance with the ITB 13.4; |  |
|  | (i). A copy of the joint venture, consortium or association agreement(s) entered into by all partners. Alternatively, a Letter of Intent to execute a joint venture, consortium or association agreement(s) in the event of a successful Bid shall be signed by all partners, together with a copy of the proposed Agreement(s). |  |
|  | (ii). Specific Power of Attorney, signed by legally authorized signatories of all the partners nominating one of the partners as being in charge, |  |
|  | (iii). The Bid signed by the authorized signatories so as to be legally binding on all partners, |  |
| 3.0 | Original Bid security in the Format provided in Section IV (Bank Guarantee with amount of TZS /-) valid for thirty (30) days beyond the Bid validity period (90 days) as specified in the ITB 19.1 read together with the Bid Data Sheet |  |
| 4.0 | Documents defining the eligibility of the Bidder (ITB 3 and 12) |  |
|  | - Bidders Information Sheet 1.1 and1.2 completely filled and submitted by all parties. |  |
|  | - Copies of Original Documents establishing constitution or legal status of the Bidder, place of registration and principal place of business (company registration certificates, MEMAT) as per ITB 13.3(a). |  |
|  | - Registered Written Specific Power of Attorney, authorizing the signatory of the Bid to commit the Bidder as per ITB 13.3(a). |  |
|  | - Compliance Statement to the conflict of interest requirements in the Form of Letter of Bid as per ITB 4.1, |  |
|  | - Compliance to Eligibility Requirements as per Table 1.1 of Section III: Evaluation and Qualification Criteria of the Biding Document |  |
|  | - Historical Non-contract performance for the last (insert number of years) years prior to the date for submission of Bids based on all information on settled disputes. (Form CON-2) |  |
|  | - Information regarding any litigation as per ITB 13.3(i) |  |
|  | - Presence of a statement on anti-bribery or anti-money laundering as provided in Section IX. |  |
| 5.0 | Documents Establishing Financial Capacity of the Bidder (Must be submitted as in Section IV – Biding Forms) |  |
|  | (a). FIN 3.1 Historical Financial Performance of the Bidder |  |
|  | (b). FIN 3.2 Average Annual Turnover |  |
|  | (c). FIN 3.3 Financial Resources (Minimum Amount of access to funds/credit facilities net of other contractual commitments) |  |
|  | (d). Reports on the financial standing of the Bidder, such as profit and loss statements or auditor's reports as per ITB 13.3(g) |  |
|  | (e). Documentary Evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources) as per ITB 13.3(h) and 13.5 (g) |  |
| 6.0 | Documents Demonstrating the Experience of the Bidder (Must be submitted as in Section IV – Biding Forms) |  |
| 6.1 | Bidder’s Design Experience: (a). General Design Experience under contracts in the role as a Design Team (as a minimum this should include architectural – including interior design, structural and services engineering) for at least the last (insert number of years) years prior to Bid submission deadline. |  |
| 6.2 | (b). Similar Design Experience: Participation as Designer or Design Team in at least One (01) contracts each with a value of works of at least TZS [insert amount] or equivalent, within the last (insert number of years) years, that have been successfully and substantially completed and that are similar to the proposed Works. |  |
| 6.3 | (c). Specific design experience for the above or other contracts executed during the period stipulated in (b) above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand |  |
| 6.4 | Bidder’s Construction Experience; (a). General Construction Experience under contracts in the role of contractor or management contractor for at least the last (insert number of years) years prior to Bid submission deadline, and with activity in at least Nine (09) months each year. |  |
| 6.5 | (b). Similar Construction Experience: Participation as Contractor or Management Contractor, in at Least One (01) contracts, each with a value of works of at least TZS [insert amount] or equivalent, within the last (insert number of years) years, that have been successfully and substantially completed and that are similar to the proposed Works. |  |
| 6.6 | (c). Specific construction for the above or other contracts executed during the period stipulated in (b) above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand |  |
| 7.0 | Technical Proposal Submission Forms as required in Section IV – (Bid Submission Forms) |  |
|  | (i). Design Proposal |  |
|  | (ii). Project Execution Plan (Method Statement, Program and Time Schedule, Cost Management Plan, Schedule of Materials and Procurement Plan) |  |
|  | (iii). Major items of equipment proposed to carry out the Contract as per ITB 13.3 (d) |  |
|  | (iv). Project Management Organization and Staffing |  |
|  | (v). Curriculum Vitae (CV) for Proposed Key Staff |  |
|  | (vi). Environmental, Social, Health and Management Plan |  |
|  | (vii). Risk Management Plan |  |
|  | (viii). Quality Management Plan |  |
|  | (ix). Project Performance Management Plan |  |
| Has the Bidder Substantially Complied to the Submission Requirements |  |  |

(b). Step 2: Determination of Responsiveness against Qualification Criteria

The purpose of this stage to determine the responsiveness of the submitted Bids against the qualification criteria in Table 1.2, 1.3 and 1.4 of this section III of the Biding  Document, ITB 13.3(d) and   ITB 13.3(e). Bids that shall be determined to be responsive to qualification criteria shall be taken detailed evaluation of the Technical Offer.

| Table 1.5(b) – Preliminary Evaluation - Step 2: Determination of Responsiveness Against Qualification Criteria |  |  |
| --- | --- | --- |
| BID NO. |  | Comments on the Bidders submission |
| 1. | Historical Contract Non- performance of the Bidder (ITB 13.5) |  |
|  | (i). Non-performance of a contract did not occur within the last (insert number of years) years prior to the deadline for Bid submission based on all information on fully settled disputes or litigation. A fully settled dispute or litigation is one that has been resolved in accordance with the dispute resolution mechanism under the respective contract, and where all appeal instances available to the Bidder have been exhausted. |  |
|  | (ii).Failure to sign a contract after submitting a Bid security has not occurred in the past (insert number of years) years. Any deviation should be explained in the enclosed Contract Non-Performance form. |  |
|  | (iii). All pending litigation shall in total not represent more than ten percent (10%) of the Bidder’s net worth and shall be treated as resolved against the Bidder. |  |
| 2 | Bidder’s Qualifications in Design and Construction Experience (ITB 12.5) |  |
| 2.1 | (i). Bidder’s Design Experience: (a). General Design Experience under Contracts in the role of a Designer or Design Team (as a minimum this should include architectural including interior design, structural and services engineering and quantity surveying) for at least the last (insert number of years) years prior to Bid submission deadline. |  |
| 2.2 | (b). Participation as Designer or Design Team (as a minimum this should include architectural including interior design, structural and services engineering and quantity surveying) in at least three (3) contracts each with a value of works of at least [insert amount]or equivalent, within the last (insert number of years) years, that have been successfully and substantially completed and that are similar to the proposed Works. |  |
| 2.3 | (c). For the above or other contracts executed during the period stipulated in (b) above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand |  |
| 2.4 | (ii). Bidder’s Construction Experience; (a). General Construction Experience under contracts in the role of Contractor or Management Contractor for at least the last (insert number of years) years prior to Bid submission deadline, and with activity in at least nine (9) months each year. |  |
| 2.5 | (b). Participation as Contractor or Management Contractor, in at least three (3) contracts each with a value of works of at least TZS [insert amount] or equivalent, within the last (insert number of years) years that have been successfully and substantially completed and that are similar to the proposed Works. |  |
| 2.6 | (c). For the above or other contracts executed during the period stipulated in (b) above, experience in the following key activities: - Construction of commercial buildings - Construction of parking lots and/or bus stand |  |
| 3.0 | Bidder’s Qualifications Against the Financial Standing |  |
|  | (a). FIN 3.1 Historical Financial Performance of the Bidder |  |
|  | Average Coefficient of Current Ratio ≥ 0.9 |  |
|  | Average Coefficient of Debt Ratio ≤ 0.75 |  |
|  | Average Coefficient of Interest Coverage Ratio ≥ 5.0 |  |
|  | Debt Equity Ratio ≤ 3.0 |  |
|  | (b). FIN 3.2 Average Annual Turnover Minimum Tanzanian Shillings [insert amount] (ITB 13.5(a)) |  |
|  | (c). FIN 3.3 Financial Resources Minimum Amount of access to funds/credit facilities net of other contractual commitments is Tanzania Shillings [insert amount] (ITB 13.5(g)) |  |
|  | (d). Documentary Evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources as per ITB 13.3(h) and 13.5 (g) |  |
| 4.0 | Bidder’s Qualification of the Proposed Key Personnel (ITB 13.3e) |  |
|  | Architect /Construction Project Manager (15/10) |  |
|  | - Interior Designer (10/5) |  |
|  | - Structural /Civil Engineer (10/5) |  |
|  | Services/Mechanical Engineer (10/5) |  |
|  | - Electrical Engineer (10/5) |  |
|  | - Quantity Surveyor (10/5) |  |
|  | - Site Engineer/ Construction Manager (10/5) |  |
|  | - ICT Expert(10/5) |  |
|  | NOTE: The submission of CV of each of the above key personnel should be accompanied with the relevant certified copies of academic and professional credentials issued by the responsible regulatory bodies. Failure to meet these requirements the Employer may reject the submitted proposal |  |
| 5.0 | Bidder’s Qualification of the Proposed Construction Equipment (ITB 13.3d) |  |
|  | Mechanical hoist (at least one) |  |
|  | Excavator/ Pneumatic digger (Nr 1) |  |
|  | Concrete batching plant (Nr 1) |  |
|  | Concrete Pump (Nr 2) |  |
|  | Scaffolding set 6000 sqm (preferably metal material) |  |
|  | 5 Ton lorry tipper (Nr 10) etc |  |
| NOTE: These are just minimum essential equipment required, evidence of ownership must be submitted together with this list otherwise the Bidder has to demonstrate other acceptable plan to make them available for the works (Hiring or buying) Failure to meet these requirements the Employer may reject the submitted proposal |  |  |
| Has the Bidder Determined to be Substantially Responsive to Perform the Contract |  |  |

Note:

Items #3 may not apply for Contractors who are registered as government agencies

C. 	Detailed Evaluation of Technical Offer

Evaluation Process of the Technical Offer

The Technical Offer comprised of the Design Proposal for the Works and other forms as called for in Section IV, Biding Forms. The Procuring Entity shall then evaluate the Technical Offers of the Bidders who were determined substantially responsive to the requirements stated in Biding documents. In so doing, they will examine and analyse the technical aspects of each Bid on the basis of the information supplied in the Bids. The Technical Offer shall be scored in accordance with the criteria summarized in Table 1.6 as detailed in table 1.7 below.

A score of 70 percent must be achieved for the Technical Offers of Bidders to qualify and accepted for opening and evaluation of financial offers.

Table 1.6: EVALUATION CRITERIA OF TECHNICAL OFFER

| A | The TECHNICAL OFFER FORMS (provided in the Biding Documents) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.0 | DESIGN PROPOSAL |  |  |  |  |  |  |  |  |  |
|  | 1.1 | Understanding of Employer’s Requirements and Preliminary Investigation |  |  |  |  |  |  |  |  |  |
|  | 1.2 | Design Philosophy and Compliance with the Employer’s Requirements |  |  |  |  |  |  |  |  |  |
|  | 1.3 | Design Standards |  |  |  |  |  |  |  |  |  |
|  | 1.4 | Preliminary Design |  |  |  |  |  |  |  |  |  |
|  | 1.5 | Sequencing and Consistence of Design Disciplines |  |  |  |  |  |  |  |  |  |
|  | 1.6 | Software Application and Design Process |  |  |  |  |  |  |  |  |  |
|  | 2.0 | PROJECT EXECUTION PLAN |  |  |  |  |  |  |  |  |  |
|  | 2.1 | Method Statement |  |  |  |  |  |  |  |  |  |
|  | 2.2 | Programme of Works and Time Schedule |  |  |  |  |  |  |  |  |  |
|  | 2.3 | Cost Management Plan |  |  |  |  |  |  |  |  |  |
|  | 2.4 | Schedule of Materials and Procurement Plan |  |  |  |  |  |  |  |  |  |
|  | 2.5 | Construction Equipment |  |  |  |  |  |  |  |  |  |
|  | 3.0 | PROJECT MANAGEMENT ORGANIZATION AND STAFFING |  |  |  |  |  |  |  |  |  |
|  | 3.1 | Organization Structure |  |  |  |  |  |  |  |  |  |
|  | 3.2 | Sub-contractors Arrangement for Specialist Work |  |  |  |  |  |  |  |  |  |
|  | 3.3 | Documentation Management Plan |  |  |  |  |  |  |  |  |  |
|  | 3.4 | CVs of Key Personnel |  |  |  |  |  |  |  |  |  |
|  | 4.0 | ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY MANAGEMENT PLAN (Forms 4a and 4b) |  |  |  |  |  |  |  |  |  |
|  | 5.0 | RISK MANAGEMENT PLAN |  |  |  |  |  |  |  |  |  |
|  | 6.0 | QUALITY MANAGEMENT PLAN |  |  |  |  |  |  |  |  |  |
|  | 7.0 | PROJECT PERFORMANCEMANAGEMENT PLAN |  |  |  |  |  |  |  |  |  |
| B | Each of the seven FORMS is assigned a Level 1 WEIGHTING |  |  |  |  |  |  |  |  |  |  |
|  | The sum of all Level 1 Weightings = 100% |  |  |  |  |  |  |  |  |  |  |
| C | Each FORM is split into various ITEMS to be evaluated |  |  |  |  |  |  |  |  |  |  |
| D | Each ITEM in a FORM is assigned a Level 2 WEIGHTING |  |  |  |  |  |  |  |  |  |  |
|  | The sum of all Level 2 Weightings for each FORM = 100% |  |  |  |  |  |  |  |  |  |  |
| E | Each ITEM is evaluated in terms of COMPLETENESS, APPROPRIATENESS, ADEQUACY, and QUALITY |  |  |  |  |  |  |  |  |  |  |
|  | See Explanatory Note below |  |  |  |  |  |  |  |  |  |  |
| F | Each CRITERIA (Completeness, Appropriateness, Adequacy, Quality) is assigned a Level 3 WEIGHTING |  |  |  |  |  |  |  |  |  |  |
|  | The Sum of all Level 3 Weightings = 100% |  |  |  |  |  |  |  |  |  |  |
| G | Evaluation of an ITEM is determined by assigning a SCORE to each of the four CRITERIA |  |  |  |  |  |  |  |  |  |  |
| H | Possible SCORES are 1 to 5, where … |  |  |  |  |  |  |  |  |  |  |
|  |  | 5 | Very Good |  |  |  |  |  |  |  |  |
|  |  | 4 | Good |  |  |  |  |  |  |  |  |
|  |  | 3 | Average |  |  |  |  |  |  |  |  |
|  |  | 2 | Poor |  |  |  |  |  |  |  |  |
|  |  | 1 | Very Poor |  |  |  |  |  |  |  |  |
| I | WEIGHTED SCORES are calculated … |  |  |  |  |  |  |  |  |  |  |
|  | - | For each ITEM, using Level 3 Weightings |  |  |  |  |  |  |  |  |  |
|  | - | For each FORM, using Level 2 Weightings |  |  |  |  |  |  |  |  |  |
|  | - | OVERALL, using Level 1 Weightings |  |  |  |  |  |  |  |  |  |
| J | Bids shall be considered TECHNICALLY NON-RESPONSIVE if the OVERALL SCORE is LESS THAN 75% |  |  |  |  |  |  |  |  |  |  |
|  | EXPLANATORY NOTE |  |  |  |  |  |  |  |  |  |  |
|  | COMPLETENESS |  |  | Sufficient AND relevant information has been provided. Evaluation of completeness is independent of appropriateness, adequacy, and/or quality of the information provided |  |  |  |  |  |  |  |
|  | APPROPRIATENESS |  |  | The item is appropriate. E.g. the Bidder is not offering a system or a technology that is inappropriate or does not comply with the requirements of the Specifications |  |  |  |  |  |  |  |
|  | ADEQUACY |  |  | The item is adequate in terms of performance, in that it will meet the requirements of the Specifications and will fulfil the purpose for which it is intended |  |  |  |  |  |  |  |
|  | QUALITY |  |  | Includes accuracy and clarity of calculations and drawings; methodology; consistency between documents |  |  |  |  |  |  |  |

Table 1.7: Sample Scoring Matrix of Technical Offer

| - FORM TITLE |  |  | - WEIGHTING |  | - CRITERIA & LEVEL 3 WT. (Score 1-5) |  |  |  | - SCORE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - Item for Evaluation |  |  |  | - Complete | - Appropriate | - Adequate | - Quality |  |
|  |  | - Typical features / requirements | - Level 1 | - Level 2 | - 25% | - 25% | - 25% | - 25% |  |
| - FORM:1 DESIGN PROPOSAL |  |  | 50% |  |  |  |  |  |  |
| - 1.1 | - Understanding of Employer’s Requirements and Preliminary Investigations |  |  |  |  |  |  |  |  |
|  |  | Interpretation and comments to the Employer’s Requirements |  | - 20% |  |  |  |  |  |
|  |  | - Understanding and interpretation of the technical data provided and their verification. |  | - 15% |  |  |  |  |  |
| - 1.2 | Design Philosophy and Compliance with the Employer’s Requirements |  |  |  |  |  |  |  |  |
|  |  | - Design philosophy and general compliance with requirements in Architectural, Interior Design, Quantity Surveying, Structural and Service Design (electrical, Mechanical, ICT, etc.) |  | - 10% |  |  |  |  |  |
| - 1.3 | Design Standards |  |  |  |  |  |  |  |  |
| - Compliance to National and International Design Standards |  |  |  | - 10% |  |  |  |  |  |
| - 1.4 | - Preliminary Designs |  |  |  |  |  |  |  |  |
|  |  | - Architectural Layouts |  | - 10% |  |  |  |  |  |
|  |  | - Structural Layouts |  | - 10% |  |  |  |  |  |
|  |  | - Service Layouts (electrical, Mechanical, ICT etc.) |  | - 10% |  |  |  |  |  |
| - 1.5 | - Sequencing and Consistence of Design Disciplines |  |  |  |  |  |  |  |  |
|  |  | - Integrating the design works (i.e. architectural, interior design, structural and services) |  | - 10% |  |  |  |  |  |
| - 1.6 | - Software Application in Design Process |  |  |  |  |  |  |  |  |
|  |  | Type of Design software used and convertibility of the output |  | - 5% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  | - 100% |  |  |  |  |  |
| - FORM:2 PROJECT EXECUTION PLAN |  |  | 14% |  |  |  |  |  |  |
| - 2.1 | - Method Statement |  |  |  |  |  |  |  |  |
|  |  | - Overall approach to construction, construction method, and resource adequacy and mix |  | - 10% |  |  |  |  |  |
|  |  | - Evidence of application of the methods |  | - 5% |  |  |  |  |  |
|  |  | Contractor’s Site Layout Plan |  | - 5% |  |  |  |  |  |
|  |  | - Provision of site offices, stores, workshops, sanitation, services, security provision, fire evacuation plan and access roads. |  | - 10% |  |  |  |  |  |
| - 2.2 | - Programme of Works and Time Schedule |  |  |  |  |  |  |  |  |
|  |  | - Should include design, preliminary investigations, approvals, procurement, and construction, testing and hand-over. - Addresses multiple work activities, teams and provision of contingencies. |  | - 15% |  |  |  |  |  |
| - 2.3 | - Cost Management Plan |  |  |  |  |  |  |  |  |
|  |  | - Should clearly indicate how the contractor intends to manage the project costs. Must be linked with the programme of work and the project milestone |  | 10% |  |  |  |  |  |
| - 2.4 | - Schedule of Material and Procurement Plan |  |  |  |  |  |  |  |  |
|  |  | - List of required materials and quantities; Materials procurement plan and sources of materials |  | - 10% |  |  |  |  |  |
| - 2.5 | - Construction Equipment or Alternatives consistent with method statement |  |  |  |  |  |  |  |  |
|  |  | Mechanical hoist (at least one) |  | - 5% |  |  |  |  |  |
|  |  | Excavator/ Pneumatic digger (Nr 1) |  | 5% |  |  |  |  |  |
|  |  | Concrete batching plant (Nr 1) |  | 7% |  |  |  |  |  |
|  |  | Concrete Pump (Nr 1) |  | - 6% |  |  |  |  |  |
|  |  | Scaffolding set 6000 sqm (preferably metal material) |  | - 7% |  |  |  |  |  |
|  |  | 10 Ton lorry tipper (Nr 10) |  | - 5% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  | - 100% |  |  |  |  |  |
| - FORM 3.0: PROJECT MANAGEMENT ORGANIZATION AND STAFFING |  |  | 20% |  |  |  |  |  |  |
| - 3.1 | - Organization Structure |  |  |  |  |  |  |  |  |
|  |  | - Management, design, supervision, tech support, suppliers, JV partnership, teams by discipline, consistent with method statement |  | - 25% |  |  |  |  |  |
| - 3.2 | - Sub-Contracting Arrangements for Specialist Works |  |  |  |  |  |  |  |  |
|  |  | - Areas of sub-contracting for specialist works and identification of scope |  | - 15% |  |  |  |  |  |
| - 3.3 | - Documentation Management Plan |  |  |  |  |  |  |  |  |
|  |  | Document / drawing control, updates / revisions, records, correspondence, site forms |  | - 15% |  |  |  |  |  |
| - 3.4 | - CVs of Key Personnel (requirement in terms of number of years of general / specific experience) |  |  |  |  |  |  |  |  |
|  |  | Architect /Construction Project Manager (15/10) |  | - 8.0% |  |  |  |  |  |
|  |  | - Structural /Civil Engineer (10/5) |  | - 6.0% |  |  |  |  |  |
|  |  | Services/Mechanical Engineer (10/5) |  | - 6.0% |  |  |  |  |  |
|  |  | - Electrical Engineer (10/5) |  | - 6% |  |  |  |  |  |
|  |  | - Quantity Surveyor (10/5) |  | - 6.0% |  |  |  |  |  |
|  |  | - Site Engineer/ Construction Manager (10/5) |  | 7% |  |  |  |  |  |
|  |  | - ICT Expert(10/5) |  | - 6% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  | - 100% |  |  |  |  |  |
| - FORM 4.0: ENVIRONMENTAL SOCIAL, HEALTH AND SAFETY MANAGEMENT PLAN |  |  | - 4% |  |  |  |  |  |  |
|  |  | - Environmental and Social Impact management-Staffing, Roles and Responsibilities |  | 20% |  |  |  |  |  |
|  |  | - Managing Environmental and Social Impact Impacts and Mitigation plan. |  | 20% |  |  |  |  |  |
|  |  | - Incorporation of Environmental Factors in design / during construction and operation; |  | - 20% |  |  |  |  |  |
|  |  | - H&S Staffing, Roles and Responsibilities |  | 20% |  |  |  |  |  |
|  |  | - Managing H&S Impacts and Mitigation plan |  | 20% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  | - 100% |  |  |  |  |  |
| FORM 5.0: RISK MANAGEMENT PLAN |  |  | - 4% |  |  |  |  |  |  |
|  |  | Overview of the Process |  | - 25% |  |  |  |  |  |
|  |  | - Risk Identification and Impact Assessment |  | - 25% |  |  |  |  |  |
|  |  | - Risk Response and Control Strategy |  | - 25% |  |  |  |  |  |
|  |  | - Roles and Responsibilities |  | - 25% |  |  |  |  |  |
|  |  | Sub-Total Level 2 |  | 100% |  |  |  |  |  |
| FORM 6.0: QUALITY MANAGEMENT PLAN |  |  | - 4% |  |  |  |  |  |  |
|  |  | - Quality Assurance Plan tools and procedures. |  | - 100% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  |  |  |  |  |  |  |
| FORM 7.0: PROJECT PERFORMANCE MANAGEMENT PLAN |  |  | - 4% |  |  |  |  |  |  |
|  |  | - Establishment of Baselines |  | - 40% |  |  |  |  |  |
|  |  | - Monitoring and Control |  | - 30% |  |  |  |  |  |
|  |  | - Reporting |  | - 30% |  |  |  |  |  |
|  |  | - Sub-Total Level 2 |  |  |  |  |  |  |  |
|  |  | - TOTAL | - 100% |  |  |  |  |  |  |

D. 	Evaluation of Price Offer

The Procuring Entity shall then consider the Bids of qualified Bidders whose Technical Offers have been determined to be substantially responsive and have score at least the minimum technical score. The Procuring Entity shall first determine whether the financial submissions are complete and compliant with the Instructions to Bidders. Then, they shall examine the following:

(i).	The Bid Price, including cost per square meter for construction of a modern, provisional and prime cost sums, if any, for contingencies in the Summary Schedule of Prices and Unit Rates, including Day work items and percentage additions on Provisional Sum Items for overhead and profit, where priced competitively.

(ii)	Price adjustment for correction of arithmetic errors in accordance with ITB   32.1.

(iii)	Price adjustment due to discounts offered in accordance with ITB 15.4, if any.

(iv)	Adjustment for non-conformities in accordance with ITB 31.3.

As provided in the Price Offer Form, the Bidder shall submit:

A Bid Price for the Works, including design and construction, based on fixed lump sum prices, and prices derived by multiplying unit rates by quantities estimated by the Bidder.

This amount is the total Bid Price for each Bidder and, subject to any adjustments pursuant to the Instructions to Bidders and Conditions of Contract, shall be the Accepted Contract Amount of the successful Bidder.

The Bid Evaluation Committee shall recommend award of the Contract to the Bidder with the lowest evaluated Bid that has been determined to be eligible, qualified, and substantially responsive.

# Section IV

Bid Submission Forms

Table of Contents

A.  Bid Submission Forms	74

Form of Letter of Bid	77

Appendix to Bid	Error! Bookmark not defined.

Standard Power of Attorney……………………………………………………………….………….80

B.  Bidder Qualification Forms	82

Bidder Information Sheet	83

Contract Performance	85

Form CON – 2	85

Financial Situation	86

Form FIN – 3.1	86

Historical Financial Performance	86

Form FIN – 3.2	87

Average Annual Turnover	87

Form FIN3.3	87

Financial Resources	87

Current Contract Commitments / Works in Progress	88

General Design Experience	89

Similar Design Experience	89

Specific Design Experience in Key Activities	91

General Construction Experience	92

Similar Construction Experience	92

Specific Construction Experience in Key Activities	93

C.  Technical Offer Forms	94

Form 1: Design Proposal	95

Construction Equipment	99

Form 3: Project Management Organization and Staffing	100

Project Management Organization	100

CVs of Key Personnel	101

Form 4: Environmental & Social Staffing and Methodology	102

Form 5: Health and Safety Documents	102

Form 6: Risk Management Plan	102

Form 7: Quality Management Plan	103

Form 8: Project Performance Management Plan	104

Form of Bid Security (Bank Guarantee)	205

##### A. Bid Submission Forms

# Form of Agreement

This Agreement, made the [day] day of [month], [year] between [name and address of Employer] (hereinafter called “the Employer”) and [name and address of Contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute [name and identification number of contract] (hereinafter called “the Works”) and the Employer has accepted the Bid by the Contractor for the execution and completion of such works and the remedying of any defects therein in the sum of [contract price in words and figures] (hereinafter called “Contract Price”).

Now this Agreement witnessed as follows:

    - In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

    - In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

    - The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4.	The following documents forming the integral part of this Contract shall be interpreted in the order of priority shown:

- The Contract Agreement (if any);

- The Letter of Acceptance;

- The Minutes of Negotiation;

- The Form of Bid (with its Appendix);

- The Special Conditions of Contract (SCC); (PC)

- The General Conditions (GCC),

- The Employer’s Requirements;

- The Particular Specifications

- The General Specifications;

- Amendments to IFB (if any);

- Clarifications to IFB (if any);

- Employer’s Modifications (if any);

- The Price Offer Form;

- Any other form of document requested and submitted during the Biding process.

The Schedules and any other documents forming part of the Contract in Witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of

Was hereunto affixed in the presence of:

Signed, Sealed, and Delivered by the said

In the presence of:

Binding Signature of Employer

Binding Signature of Contractor

###### Form of Letter of Bid

Name of Contract: …………………………………………………

To:

Gentlemen:

We, the undersigned, declare that:

1.	We have examined and we have no reservations to the Biding Documents, including addenda thereto issued in accordance with the Instructions to Bidders.

2.	In accordance with the Conditions of Contract, Employer’s Requirements, Basic Site Information, Price Offer and Addenda Nos. [Insert Addenda Nos.]for the execution of the above-named Works, we offer to design, construct and install such Works and remedy any defects therein in conformity with the Conditions of Contract, Employer’s Requirements, Basic Site Information, Price Offer, and Addenda for the sum stated in our Financial Offer (submitted in a separate envelop) as specified in the Appendix to Bid or such other sums as may be ascertained in accordance with the conditions.

3.	We acknowledge that the Appendix to Bid forms part of our Bid.

4.	We accept the appointment of the Adjudicator as per General Conditions of Contract.

[or]

We do not accept the appointment of the Adjudicator as proposed. Instead, we propose to appoint the Adjudicator as per [insert alternative procedure].

5. 	We undertake, if our Bid is accepted, to obtain a Performance Security in accordance with the Biding Documents and commence the Works as soon as is reasonably possible after the receipt of the Employer’s notice to commence, and to complete the whole of the Works comprised in the Contract within the time stated in the Appendix to Bid.

6.	We agree to a Bidder by this Bid until the date specified in ITB   19, and it shall remain binding upon us and may be accepted at any time before that date.

7. 	Unless and until a formal Contract is prepared and executed, this Bid, together with your written acceptance thereof, shall constitute a binding contract between us.

8.	We understand that you are not bound to accept the lowest or any Bid you may receive.

9. 	We certify that we, including any subcontractors and suppliers for any part of the Contract have or will have nationalities from eligible countries in accordance with ITB   ITB 3.3.

10. 	We certify that we and any subcontractors and suppliers for any part of the Contract comply with the requirements of ITB  4 of the Biding Documents. By that, we mean that we, including any subcontractors or suppliers for any part of the Contract, do not have any conflict of interest in accordance with ITB  4.1; have not been declared ineligible as described in ITB  4.2; and have not been excluded as a result of the laws of Tanzania or official Regulations, or by an act of compliance with a decision of the United Nations Security Council.

11. 	Commissions or gratuities, if any, paid or to be paid by us to agents relating to this Bid, and to Contract execution if we are awarded the Contract, are listed below:

| Name and address of agent |  | Amount and currency |  | Purpose of commission or gratuity |
| --- | --- | --- | --- | --- |
| (if none, state “none”) |  |  |  |  |

12.	We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in bribery.

Dated this 	 day of 	 20

Names of the Authorised Signatory. _____________________________________________

Signature 	 In the capacity of

Duly authorized to sign Bids for and on behalf of

[in block capitals or typed]

Address:

Witness:

Address:

Occupation:

- Standard Power of Attorney

## TO ALL IT MAY CONCERN

THAT BY THIS POWER OF ATTORNEY given on the [insert date, month and year],

WE the undersigned [insert name of the company/donor] of [insert address of the company/donor], by virtue of authority conferred to us by the Board Resolution No		of 		day of 				[insert year], do hereby ordain nominate and appoint [insert name of donee] of [insert address of the donee] to be our true lawful Attorney and Agent, with full power and authority, for us and in our names, and for our accounts and benefits, to do any, or all of the following acts, in the execution of Bid No. [insert Bid number] that is to say;

To act for the company and do any other thing or things incidental for [insert Bid Number] of [insert description of procurement] for the [insert name of the Procuring Entity];

AND provided always that this Power of Attorney shall not revoke or in any manner affect any future power of attorney given to any other person or persons for such other power or powers shall remain and be of the same force and affect as if this deed has not been executed.

AND we hereby undertake to ratify everything, which our Attorney or any substitute or substitutes or agent or agents appointed by him under this power on his behalf herein before contained shall do or purport to do in virtue of this Power of Attorney.

SEALED with the common seal of the said [[insert name of the company] and delivered in the presence of us this [insert date] day of [insert month] [insert year].

IN WITNESS whereof we have signed this deed on this [insert date] day of [insert month] [insert year] at [insert region] for and on behalf of [insert name of the company] ………………………………………

SEALED and DELIVERED by the

Common Seal of [insert name of the donor/coy]

This [insert date, month and year]

DONOR

BEFORE ME:

COMMISSIONER FOR OATHS

Acknowledgement

I [insert name of donee] doth hereby acknowledge and accept to be Attorney of the said [insert name of the company/donor] under the terms and conditions contained in this POWER OF ATTORNEY and I promise to perform and discharge my duties as the lawfully appointed Attorney faithfully and honestly.

SIGNED AND DELIVERED by the said

[insert name of donee] Identified to me

by [insert name]

The latter known to me personally

This [insert date, month and year],

DONEE

BEFORE ME

COMMISSIONER FOR OATHS

# Letter of Acceptance

[Letterhead paper of the Employer]

[Date]

To:  [name and address of the Contractor]

This is to notify you that your Bid dated [date] for execution of [insert name of the project],  for the Accepted Contract Amount of [amount in words and numbers] [name of currency], as corrected and modified in accordance with the Instructions to Bidders, is hereby accepted by us in our capacity as Employer under the Contract.

Within 14 working days of your receipt of this Letter of Acceptance you are hereby instructed to (a) sign and return the attached Contract Agreement in accordance with   ITB 1.6 of the General Conditions of Contract and (b) forward the Performance Security in accordance with   ITB 5.2 of the General Conditions of Contract, using for that purpose the Form of Performance Bank Guarantee, Forms of Agreement and Security, of the Biding Documents, or another form acceptable to us.

Authorized Signature:

Name and Title of Signatory:

Attachment:  Contract Agreement

##### B.  Bidder Qualification Forms

###### Bidder Information Sheet

Form ELI 1.1

Date:  ______________________

1. Bidder’s Legal Name

2. In case of JV, legal name of each party:

3. Bidder’s actual or intended Country of Registration:

4. Bidder’s Year of Registration:

5. Bidder’s Legal Address in Country of Registration:

6. Bidder’s Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of: (i). In case of single entity, articles of incorporation or similar documents of constitution of the legal entity named above, in accordance with ITB 3.1 and 3.2. (ii). Authorization to represent the Bidder named in above, in accordance with ITB 21.2. (iii). In the case of joint venture or other consortium, (a) the joint venture or similar documents of constitution and documents of registration of the joint venture or other consortium, or (b) the letter of intent to form the joint venture or other consortium and demonstrating the joint and several liability of all members, in accordance with ITB 3.1.

Form ELI 1.2

Party to JV, Consortium or Association Information Sheet

Date: ______________________

1. Bidder’s Legal Name:

2. Party legal name:

3. Party Country of Registration:

4. Party Year of Registration:

5. Party Legal Address in Country of Registration:

6. Party Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of: (i). Authorization to represent the Bidder named in above, in accordance with ITB 21.2. (ii). In the case of joint venture or other consortium, (a) the joint venture or similar documents of constitution and documents of registration of the joint venture or other consortium, or (b) the letter of intent to form the joint venture or other consortium and demonstrating the joint and several liability of all members, in accordance with ITB 3.1.

###### Contract Performance

###### Form CON – 2

Bidder’s Legal Name:  ______________________

JV, consortium or association Partner Legal Name:  ____________________

(Each Bidder or member of a joint venture, consortium or association making up a Bidder must fill in this form).

| Non-Performing Contracts in accordance with (Evaluation and Qualification Criteria) |  |  |  |
| --- | --- | --- | --- |
| Contract non-performance did not occur during the stipulated period, in accordance with Section III (Evaluation and Qualification Criteria) Contract non-performance during the stipulated period, in accordance with Section III (Evaluation and Qualification Criteria). |  |  |  |
| Year | Outcome as Percent of Total Assets | Contract Identification | Total Contract Amount (current value, TZS equivalent) |
|  |  | Contract Identification: Name of Employer: Address of Employer: - Matter in dispute: |  |
| Pending Litigation, in accordance with Section III (Evaluation and Qualification Criteria) |  |  |  |
| No pending litigation in accordance with Section III (Evaluation and Qualification Criteria) Pending litigation in accordance with Section III (Evaluation and Qualification Criteria), as indicated below |  |  |  |
| Year | Outcome as Percent of Total Assets | Contract Identification | Total Contract Amount (current value, TZS equivalent) |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  |
|  |  | Contract Identification: Name of Employer: Address of Employer: Matter in dispute: |  |

###### Financial Situation

###### Form FIN – 3.1 - Historical Financial Performance

Bidder’s Legal Name: _________________________

JV, Consortium or association Partner Legal Name: _______________________

[To be completed by the Bidder and, if JV, consortium or association by each partner]

| Financial Information in TZS | Historic information for previous Three (3) years (Tanzania Shillings) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Avg. Ratio |
| Information from Balance Sheet |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |

Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:

- Must reflect the financial situation of the Bidder or partner to a JV, and not sister or parent companies

- Historic financial statements must be audited by a certified accountant

- Historic financial statements must be complete, including all notes to the financial statements

- Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

###### Form FIN – 3.2

###### Average Annual Turnover

Bidder’s Legal Name:  ___________________________

JV,consortium or association Partner Legal Name: ___________________________

| Annual Construction Turnover data |  |  |
| --- | --- | --- |
| Year | Amount and Currency | TZS equivalent |
| *Average Annual Construction Turnover |  |  |

*Average annual turnover calculated as total certified payments received for service rendered over the number of years specified in Evaluation and Qualification Criteria.

###### Form FIN 3.3

###### Financial Resources

[Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total operational cash flow demands of the subject contract]

| Source of financing | Amount (TZS equivalent) |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

###### Current Contract Commitments / Works in Progress

[Each Bidder and each member of a joint venture or other consortium making up a Bidder should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued].

| Name of Contract | Employer, contact address/fax | Value of outstanding work (current TZS equivalent) | Estimated completion date | Average monthly invoicing over last six months (TZS/month) |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| etc. |  |  |  |  |

###### General Design Experience

[Each Bidder or the designated designer of a Bidder which is a joint venture, consortium or association must fill in this form.]

| - General Design Experience |  |  |  |  |
| --- | --- | --- | --- | --- |
| Starting Month Year | Ending Month Year | Years | Contract Identification and Name Name and Address of Employer Brief Description of the Designs Developed by the Bidder | Role of Bidder |

###### Similar Design Experience

[Fill in one (1) form per contract.]

| - Contract of Similar Size and Nature |  |  |  |
| --- | --- | --- | --- |
| Contract No._____of __ | - Contract Identification: |  |  |
| Award Date |  | Completion Date |  |
|  |  | Percentage completion of the works |  |
| Role in Contract | - Architect | - Structural | - Services |
| Total Value of the Works | TZS Equivalent |  |  |
| If a member of a JV, consortium or association making up the Bidder or a subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone/Fax Number E-mail |  |  |  |
| - Description of the similarity in accordance with Section III |  |  |  |

###### Specific Design Experience in Key Activities

[Fill in one (1) form for each of the following design experience in key activities: Architectural, interior designing, structural, Electrical, quantity surveying, Service design etc].

| - Contract with Specific Key Activities |  |  |  |
| --- | --- | --- | --- |
| Contract No._____of __ | - Contract Identification: |  |  |
| Award Date |  | Completion Date |  |
|  |  | Percentage completion of the works |  |
| Role in Contract | - Architect | - Structural | - Services |
| Total Value of Works | TZS Equivalent |  |  |
| If a member of a JV, consortium or association making up the Bidder or a subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone Number Fax Number E-mail |  |  |  |
| Description of the key activities in accordance with Table 1.4 of Section III of Biding Document |  |  |  |

###### General Construction Experience

[Each Bidder or member of a joint venture or other consortium making up a Bidder must fill in this form]

| - General Construction Experience |  |  |  |  |
| --- | --- | --- | --- | --- |
| Starting Month Year | Ending Month Year | Years | Contract Identification and Name, Name and Address of Employer, Brief Description of the Works Executed by the Bidder | Role of Bidder |

###### Similar Construction Experience

[Fill in one (1) form per contract].

| - Contract of Similar Size and Nature |  |  |  |
| --- | --- | --- | --- |
| Contract No._____of __ | - Contract Identification |  |  |
| Award Date |  | Completion Date |  |
|  |  | Percentage completion of the works |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Value of Works | TZS Equivalent |  |  |
| If a member of a JV, consortium or association making up the Bidder or a subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone/Fax Number E-mail |  |  |  |
| - Description of the key activities in accordance with Table 1.4 of Section III of Biding Document |  |  |  |

###### Specific Construction Experience in Key Activities

[Fill in one (1) form per contract]

| - Contract with Specific Key Activities |  |  |  |
| --- | --- | --- | --- |
| Contract No._____of __ | - Contract Identification |  |  |
| Award Date |  | - Completion Date |  |
|  |  | - Percentage completion of the works |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Value of Works | TZS Equivalent |  |  |
| If a member of a JV, consortium or association making up the Bidder or a subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s Name Address Telephone Number Fax Number E-mail |  |  |  |
| Description of the key activities in accordance with Table 1.4 of Section III of Biding Document |  |  |  |

##### C.  Technical Offer Forms

###### Form 1: Design Proposal

## The Bidder shall prepare the following documents that will form the Design Proposal:

(a).	Preliminary Design of all elements of the Works (architectural, interior design, quantity surveying, structural, services engineering, etc.). The Preliminary Design shall comprise of drawings and specific technical specifications to demonstrate that the Employer’s Requirement have been met. Drawings scales shall be selected to show designs in sufficient detail to allow proper evaluation. Drawings which show insufficient detail, and do not allow a proper assessment, may result in the design being considered technically non-compliant.

(b).	Bidder shall indicate relevant international standards, design criteria, loading conditions, assumptions, etc., that will be adopted during detailed design.

(c).	Bidder must demonstrate how the Employer’s Requirements have been achieved in his design proposal on item by item. Commentary on the Employer's Requirements, including comments to the technical and project brief will demonstrate Bidders understanding, interpretation and compliance to the Employer’s Requirements.

(d).	Discussion of how the Bidder proposes to develop the design at key stages, including a commentary on any necessary mapping and/or survey work, and verification of site investigations as described in the Biding  documents, and the proposed design methodology for key elements of the Works. The Bidder shall identify key areas where design disciplines will overlap and the sequencing / iterations that will be required.

(e).	Name and version of all software to be used for design purposes. Software packages shall be internationally recognized, and established software programs. Software packages must be capable of providing printed output except for animation software.

Form 2: Project Execution Plan

Method Statement

(a).	Each Bidder shall set out details of the Method Statement for the Works (specifically prepared for this project) to demonstrate how it will meet the Employer’s objective and requirements. At a minimum, the specific Method Statement shall address the following:

(i).	Details of the arrangements and methods which the Bidder proposes to adopt for the design and construction of the Works, with sufficient detail to demonstrate their adequacy to achieve the requirements of the Contract including completion within the Time for Completion stated in the Appendix to Bid.

(ii).	the statement shall include discussion on the potential risks and impacts associated with construction below the ground level (e.g. possibility of high groundwater levels on site), and construction at heights. Method statement should provide the mitigation measure for such impacts.

(iii).	Outline of the arrangements which the Bidder proposes to adopt to manage coordination of Site access including location and operation of major construction equipment (such as crane, hoists, concrete pump, trucks etc.)

(iv).	Commentary on the geotechnical and subsurface aspects of the Works.

(v).	Commentary on design and construction logistics and how the Bidder will comply with the project time frame.

(vi).	Outline of the arrangements which the Bidder proposes to adopt to ensure compliance with the Employer’s Requirements. In particular, the Bidder shall describe his proposal for working in and around a limited space.

(vii).	Outline of the arrangements which the Bidder proposes for acceptance criteria and its application upon completion as called for in the Employer’s Requirements.

(viii).	Bidders shall describe the proposed sequencing of the Works, which shall also include the Defects Notification Period to the complete works following successful Testing on Completion, and subsequent taking over by the Employer.

(ix).	Outline of arrangements for handover, including completion of as-built drawings, preparation of operation and maintenance manuals, and any additional matters.

Programme of Works

(b).	Each Bidder shall set out a detailed Program of Works for design and construction of the Works to be undertaken and completed within the Time for Completion, including estimated start and finish dates for individual components and identification of major milestones and critical path. The proposed Program of Works shall be developed according to the Employer’s Requirements and shall address the following:

(i).	Details of the proposed schedule for design of the Works, including preliminary investigations and reporting, and the submission of design documents, review and approval by the Engineer.

(ii).	Details of the Program of Works for permitting processes that may be necessary in order to commence the Works, including preparation of required studies, supporting information, and applications.

(iii).	Details of the proposed timeline for carrying out the Works in the form of a bar chart showing notably the critical path, including allowances for potential risks such as rainy season.

(iv).	Details of the proposed timeline for the commissioning and handing over of the completed Works.

(v).	Where the program indicates multiple concurrent activities of the same discipline, the Bid shall clearly demonstrate that sufficient equipment, personnel and other resources will be available to allow such multiple activities to be undertaken.

Cost Management Plan (Not indicating cash flow projection)

Each Bidder shall be required to indicate a generic cost management plan that will indicate how he has arrived at the cost estimate; the cost plan and establishment of cost limits, Cash Flow projections, the procedures and steps to be taken to limit and control variations, financial appraisal procedures and final account and project closure process and report format.

Schedule of Materials and Procurement Plans

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the materials, estimated quantities, sources and estimated delivery dates.

| Description/type of material | Estimated Quantities | Sources (country of origin) | Estimated Delivery Dates |
| --- | --- | --- | --- |

Construction Equipment

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III, Evaluation and Qualification Criteria. A separate form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location. |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

[Omit the following information for equipment owned by the Bidder].

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax |  |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

###### Form 3: Project Management Organization and Staffing

###### Project Management Organization

The Bidder shall set out details of the Project Management Organization, together with identification and Curriculum Vitae (“CV”) for each key member for each component of the Project.

CVs are provided for the key personnel for the following positions, using the forms provided for that purpose:

| No. | Position | Total Related Work Similar Experience (years) | Experience in Similar Designs and/or Works (years) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |

In particular, the Bidder must provide the names and particulars of the individuals from the proposed design company to prepare the design of the Works.

In addition, the Bidder shall provide the following information:

(a).	organizational chart showing lines of communications as well as communication plan for managing communications with key stakeholders. The chart shall indicate the number and type of work-teams (e.g., concrete, mechanical installation, electrical, pipe-fitters, etc.). The number of teams shall be compatible with the requirements of the Work Program described above;

(b).	plans for sub-contracting any parts of the Works and the services to be carried out or the Plant and Equipment to be provided by sub-contractors;

(c).	quality management system, describing the basis and operation of the proposed quality management system, including management reviews, procedural audits, checking, procedures for monitoring, reporting and dealing with nonconformities, corrective actions, and feedback. Quality management procedures shall be described for both design and construction activities, and

(d).	Data management plan in accordance with the Employer’s Requirements, describing the proposed system for storing, indexing, and accessing data such as correspondence, meeting minutes, reports, drawings, etc.

###### CVs of Key Personnel

| Name of Bidder: |  |  |
| --- | --- | --- |
| Proposed Position for this Project: |  |  |
| Personnel information | Name: | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize below professional experience over the last 10 years, in reverse chronological order.  Indicate particular technical and managerial experience relevant to the project.

| From | To | Company / Project / Position / Relevant technical and management experience |
| --- | --- | --- |

CERTIFICATION

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes myself, my qualifications, and my experience. I understand that any wilful misstatement described herein may lead to my disqualification or dismissal, if engaged.

_______________________________________________________Date:_______________

[Signature of staff member or authorized representative of the staff]Day/Month/Year

Full name of authorized representative: ____________________________________________

Form 4a: Environmental & Social Staffing and Methodology

The Bidder shall demonstrate in a narrative section of their Technical Offer that it can successfully manage the Environmental and Social (E&S) risks associated with the implementation of the proposed Works, as follows:

Describe the proposed E&S staffing, roles and responsibilities, and management structure; and describe the proposed approach to managing E&S impacts during implementation of this project, including a description of the mitigation measures that will be used and E&S standards that may be applicable. The Bidder shall provide enough detail to demonstrate an understanding of the critical E&S issues related to the project.

[Note] The successful Bidder will be required to carry out the Works in accordance with the site-specific Environmental and Social Management Plan (“ESMP”), to be prepared by the Contractor following Contract award, and approved by the Engineer. The site-specific ESMP shall be prepared based on the contents of these Biding documents.

###### Form 4b: Health and Safety Documents

The Bidder shall demonstrate in a narrative section of their Technical Offer that he can successfully manage the Health and Safety (H&S) risks related to the implementation of the Works as follows:

Describe the proposed H&S staffing, roles and responsibilities, and management structure; and describe the proposed approach to managing H&S impacts during implementation of the Works, including a summary of mitigation measures that will be used and H&S standards that may be applicable. Provide enough detail to demonstrate an understanding of the critical H&S issues related to the project.

[Note: The successful Bidder will be required to carry out the Works in accordance with the site-specific Health and Safety Plan to be developed by the Bidder following Contract award, and approved by the Engineer.]

###### Form 5: Risk Management Plan

The Risk Management Plan (RMP) for the project will establish the activities, processes, and procedures for ensuring project risks are managed. As part of RMP the following elements should be addressed by the Bidder.

| No. | Steps | Description of the Activity |
| --- | --- | --- |
| 1 | Overview of the Process | Provide an overview of the process to be employed to manage risks, what roles will be involved, procedures and how risks impact will be identified, measured and mitigated. |
| 2 | Risk Identification and Impact Assessment | Details of the process of risks identification, prioritization and quantification of the impacts. |
| 3 | Risk Response and Control Strategy | Details of the proposed strategy for managing priority risks such as assessing risks, monitoring and control, implementing mitigation measures, escalation procedures and thresholds. Propose a format for risk register. |
| 4 | Roles and Responsibilities | Describe who and what teams will be involved in the risk management process including roles of those involved. Describe what methods will be used to communicate on issues and the escalation procedures. Describe what rules or procedures the team must follow when logging, managing and accessing risks and mechanism to be used to log risks. Describe the process that will be used to assess the impact of each risk. |

###### Form 6: Quality Management Plan

The Quality Management Plan for the project will establish the activities, processes, and procedures for ensuring a quality product upon the conclusion of the project. The purpose of this plan is to: Ensure quality is planned, define how quality will be managed, quality assurance activities, quality control activities, acceptable quality standards.

| No. | Steps | Description of the Activity |
| --- | --- | --- |
| 1 | Quality Management Approach | This section describes the approach the organization will use for managing quality throughout the contract period. |
| 2 | Quality Requirements / Standards | This section should describe how the project team and/or quality group will identify and document the quality requirements and standards. Additionally, there should also be an explanation of how the project will demonstrate compliance with those identified quality standards. The quality standards and requirements should include both the products and processes. |
| 3 | Quality Assurance | This section should explain how you will define and document the process for auditing the quality requirements and results from quality control measurements in order to ensure that quality standards and operational definitions are used. This section should also document the actual quality assurance metrics used for this project. |
| 4 | Quality Control | This section describes how you will define and document the process for monitoring and recording the results of executing the quality activities to assess performance and recommend necessary changes. It should include what the acceptable standards and/or performance are for the product and how these measurements will be conducted. |
| 5 | Quality Control Measurements | This section should contain a sample or useable table/log to be used in taking quality measurements and comparing them against standards/requirements and proposed actions if actual measurements do not meet the standards or requirements. |

###### Form 7: Project Performance Management Plan

The Project Performance Management Plan (PPMP) describes the methods used by the Bidder or its subcontractors, to quantitatively manage the time and cost performance of the project. The PPMP shall establish baselines against which this shall be measured and controlled.

| No. | Steps | Description of the Activity |
| --- | --- | --- |
| 1 | Establish the Baselines | This section shall indicate how the Bidder plans to establish project targets, baselines and associated measurements (i.e metrics) for time and cost performance. |
| 2 | Monitoring and Control | The section shall describe methods for project tracking by indicating the frequency of measurement and control actions to be taken while identifying opportunities for performance improvements. Monitoring and control tools for time and cost performance should clearly be stated. |
| 3 | Reporting | This section shall indicate the generic formats of reporting results of project tracking, associated metrics/measurements, control actions to be taken where necessary including recommendations. |

Part II

CONDITIONS OF CONTRACT

# Section V

# General Conditions of Contract

SECTION VI. GENERAL CONDITIONS OF CONTRACT (GCC)

A.	General Provisions	113

1.1 	Definition	113

1.1.1	The Contract	113

1.1.2	Parties and Persons	113

1.1.3	Dates, Tests, Periods and Completion	114

1.1.4	Money and Payments	115

1.1.5	Works and Goods	116

1.1.6	Other Definitions	116

1.2 	Interpretation	117

1.3	Communications	117

1.4	Governing Language and Law	118

1.5	Priority of Documents	118

1.6	Assignment	118

1.7	Care and Supply of Documents	118

1.8	Error in the Employer’s  Requirements	119

1.9	Employer’s Use of Contractor’s Documents	119

1.10	Contractor’s Use of Employer’s Documents	120

1.11	Confidential Details	120

1.12	Compliance with Laws	120

1.13	Taxes and Duties	120

1.14	Joint and Several Liability	120

1.15	Instructions, Inspections and Audits	121

B.	The Employer	121

2.1	Right of Access to the Site	121

2.2	Permits, Licences or Approvals	122

2.3	Employer’s Personnel	122

2.4	Suspension of Financing	122

2.5	Employer’s Claims	122

C.	The Project Manager	123

3.1	Project Manager’s Appointment, Duties and Authority	123

3.2	Delegation by the Project Manager	125

3.3	Instructions of the Project Manager	125

3.4	Replacement of the Project Manager	126

3.5	Determinations	126

D.	The Contractor	126

4.1	Contractor’s General Obligations	127

4.2	Performance Security	127

4.3	Contractor’s Representative	128

4.4	Subcontractors	129

4.5	Nominated Subcontractors	129

4.6	Co-operation	129

4.7	Setting Out	130

4.8	Safety Procedures	130

4.9	Quality Assurance	131

4.10	Site Data	131

4.11	Sufficiency of the Accepted Contract Amount	132

4.12	Unforeseeable Physical Conditions	132

4.13	Rights of Way and Facilities	133

4.14	Avoidance of Interference	133

4.15	Access Route	133

4.16	Transport of Goods	134

4.17	Contractor’s Equipment	134

4.18	Protection of the Environment	134

4.19	Electricity, Water and Gas	135

4.20	Employer’s Equipment and Free-Issue Materials	136

4.21	Progress Reports	136

4.22	Security of the Site	137

4.23	Contractor’s Operations on Site	137

4.24	Fossils	138

E.	Design	138

5.1 	General Design Obligations	138

5.2 	Contractor's Documents	139

5.3 	Contractor’s Undertaking	141

5.4	Technical Standards and Regulations	141

5.5 	Training	142

5.6	As-Built Documents	142

5.7 	Operation and Maintenance Manuals	142

5.8 	Design Error	142

F.	Staff and Labour	143

6.1	Engagement of Staff and Labour	143

6.2	Rates of Wages and Conditions of Labour	143

6.3	Persons in the Service of Employer	143

6.4	Labour Laws	143

6.5	Facilities for Staff and Labour	143

6.6	Health and Safety	143

6.7	Contractor’s Superintendence	144

6.8	Contractor’s Personnel	144

6.9	Records of Contractor’s Personnel and Equipment	145

6.10	Disorderly Conduct	145

6.11	Foreign Personnel	145

6.12	Funeral Arrangements	145

6.13	Prohibition of Forced or Compulsory Labour	145

6.14	Prohibition of Harmful Child Labour	145

6.15	Employment Records of Workers	146

G.	Plant, Materials and Workmanship	146

7.1	Manner of Execution	146

7.2	Samples	146

7.3	Inspection	146

7.4	Testing	147

7.5	Rejection	148

7.6	Remedial Work	148

7.7	Ownership of Plant and Materials	149

7.8	Royalties	149

H.	Commencement, Delays and Suspension	149

8.1 	Commencement of Works	149

8.2 	Time for Completion	150

8.3 	Programme	150

8.4	Extension of Time for Completion	151

8.5 	Rate of Progress	152

8.6 	Liquidated Damages	152

8.7 	Suspension of Work	153

8.8 	Consequences of Suspension	153

8.9 	Payment for Plant and Materials in Event of Suspension	153

8.10 	Prolonged Suspension	153

8.11 	Resumption of Work	154

I.	Tests on Completion	154

9.1	Contractor’s Obligations	154

9.2	Delayed Tests	155

9.3	Retesting	155

9.4	Failure to Pass Tests on Completion	155

J.	Employer’s Taking Over	156

10.1	Taking Over of the Works and Sections	156

10.2	Taking Over of Parts of the Works	158

10.3	Delay of Tests on Completion	159

10.4	Surfaces Requiring Reinstatement	159

K.	Defects Liability	159

11.1	Completion of Outstanding Work and Remedying Defects	159

11.2	Cost of Remedying Defects	160

11.3	Extension of Defects Liability Period	160

11.4	Failure to Remedy Defects	160

11.5	Removal of Defective Work	161

11.6	Further Tests	161

11.7	Right of Access	161

11.8	Contractor to Search	161

11.9	Performance Certificate	161

11.10	Unfulfilled Obligations	162

11.11	Clearance of Site	162

L.	Tests after Completion	162

12.1 	Procedure for Tests after Completion	162

12.2 	Delayed Test	163

12.3 	Retesting	163

12.4 	Failure to Pass Tests after Completion	164

M.	Variations and Adjustments	164

13.1	Right to Vary	164

13.2	Value Engineering	165

13.3	Variation Procedure	166

13.4	Payment in Applicable Currencies	166

13.5	Provisional Sums	167

13.6	Daywork	167

13.7	Adjustments for Changes in Legislation	168

13.8	Adjustments for Changes in Cost	168

N.	Contract Price and Payment	170

14.1	The Contract Price	170

14.2	Advance Payment	170

14.3	Application for Interim Payment Certificates	172

14.4	Schedule of Payments	173

14.5	Plant and Materials intended for the Works	173

14.6	Issue of Interim Payment Certificates	175

14.7	Payment and Currency	175

14.8	Delayed Payment	176

14.9	Payment of Retention Money	176

14.10	Statement at Completion	177

14.11	Application for Final Payment Certificate	177

14.12	Discharge	178

14.13	Issue of Final Payment Certificate	178

14.14	Cessation of Employer’s Liability	178

O.	Termination by Employer	179

15.1	Notice to Correct	179

15.2	Termination by Employer	179

15.3	Valuation at Date of Termination	180

15.4	Payment after Termination	180

15.5	Employer’s Entitlement to Termination for Convenience	181

15.6	Corrupt or Fraudulent Practices	181

P.	Suspension and Termination by the Contractor	182

16.1	Contractor’s Entitlement to Suspend Work	182

16.2	Termination by Contractor	182

16.3	Cessation of Work and Removal of Contractor’s Equipment	183

16.4	Payment on Termination	184

Q.	Risk and Responsibility	184

17.1	Indemnities	184

17.2	Contractor’s Care of the Works	184

17.3	Employer’s Risks	185

17.4	Consequences of Employer’s Risks	185

17.5	Intellectual and Industrial Property Rights	186

17.6	Limitation of Liability	186

17.7	Use of Employer’s Accomodation/Facilities	187

R.	Insurance	187

18.1	General Requirements for Insurances	187

18.2	Insurance for Works and Contractor’s Equipment	189

18.3	Insurance against Injury to Persons and Damage to Property	190

18.4	Insurance for Contractor’s Personnel	191

S.	Force Majeure	191

19.1	Definition of Force Majeure	191

19.2	Notice of Force Majeure	192

19.3	Duty to Minimize Delay	192

19.4	Consequences of Force Majeure	192

19.5	Force Majeure Affecting Subcontractor	193

19.6	Optional Termination, Payment and Release	193

19.7	Release from Performance	193

T.	Claims, Disputes and Arbitration	194

20.1	Contractor’s Claims	194

20.2	Amicable Settlement	195

20.3	Appointment of the Dispute Adjudication Panel	195

20.4	Obtaining Dispute Board’s Decision	196

20.5	Arbitration	197

20.6	Failure to Comply with Dispute Board’s Decision	198

| - General Provisions |  |
| --- | --- |
| 1.1 Definition | In these Conditions of Contract, (General Conditions and Special Conditions), the following words and expressions shall have the meanings stated. Words indicating persons or parties include corporations and other legal entities, except where the context requires otherwise. |
| 1.1.1 The Contract | “Contract” means the Contract entered between the Employer and the Contractor for design and construction of works. “Letter of Acceptance” means the letter of formal acceptance of the bid, signed by the Employer and communicated to the Contractor. “Form of Bid” means the document entitled Form of Bid, which was completed by the Contractor and includes the signed offer to the Employer for the works. “Employer’s Requirement” means the document entitled Employer’s Requirement, as included in the Contract, and any additions and modifications to the Employer’s Requirement in accordance with the Contract. Such document specifies the Works. “Drawings” means the drawings of the Works, as included in the Contract, and any additional and modified drawings issued by (or on behalf of) the Employer in accordance with the Contract. “Schedules” means the document(s) entitled schedules, completed by the Contractor and submitted with the Form of Bid, as included in the Contract. Such document may include the Bill of Quantities, data, lists, and schedules of rates and/or prices. “Bid” means the Form of Bid and all other documents which the Contractor submitted with the Form of Bid, as included in the Contract. “Bill of Quantities” and “Day Work Schedule” and “Schedule of Payment Currencies” mean the documents so named (if any) which are comprised in the Schedules. |
| 1.1.2 Parties and Persons | “Party” means the Employer or the Contractor, as the context requires. “Employer” means the person named as Employer in the Special Conditions of Contracts (SCC) and the legal successors in title to this person. “Contractor” means the person(s) named as contractor in the Form of Bid accepted by the Employer and the legal successors in title to this person(s). “Project Manager” means the person appointed by the Employer to act as the Project Manager for the purposes of the Contract and named in the SCC, or other person appointed from time to time by the Employer and notified to the Contractor under GCC 3.4 [Replacement of the Project Manager]. “Contractor’s Representative” means the person named by the Contractor in the Contract or appointed from time to time by the Contractor under GCC 4.3 [Contractor’s Representative], who acts on behalf of the Contractor. “Employer’s Personnel” means the Project Manager, the assistants referred to in GCC 3.2 [Delegation by the Project Manager] and all other staff, labour and other employees of the Project Manager and of the Employer; and any other personnel notified to the Contractor, by the Employer or the Project Manager, as Employer’s Personnel. “Contractor’s Personnel” means the Contractor’s Representative and all personnel whom the Contractor utilises on Site, who may include the staff, labour and other employees of the Contractor and of each Subcontractor; and any other personnel assisting the Contractor in the execution of the Works. “Subcontractor” means any person named in the Contract as a subcontractor, or any person appointed as a subcontractor, for a part of the Works; and the legal successors in title to each of these persons. “Dispute Adjudication Panel (DAP)” means the person or three persons appointed under GCC 20.3 [Appointment of the Dispute Board] or GCC 20.3 [Failure to Agree on the Composition of the Dispute Board] |
| 1.1.3 Dates, Tests, Periods and Completion | “Base Date” means the date 28 days prior to the latest date for submission of the Bid. “Commencement Date” means the date notified under GCC 8.1 [Commencement of Works]. “Time for Completion” means the time for completing the Works or a Section (as the case may be) under GCC 8.2 [Time for Completion], as stated in the SCC (with any extension under GCC 8.4 [Extension of Time for Completion]), calculated from the Commencement Date. “Tests on Completion” means the tests which are specified in the Contract or agreed by both Parties or instructed as a Variation, and which are carried out under GCC 9 [Tests on Completion] before the Works or a Section (as the case may be) are taken over by the Employer. “Taking-Over Certificate” means a certificate issued under GCC 10 [Employer’s Taking Over]. “Tests after Completion” means the tests (if any) which are specified in the Contract and which are carried out in accordance with the Employer’s Requirement after the Works or a Section (as the case may be) are taken over by the Employer. “Defects Liability Period” means the period for notifying defects in the Works or a Section (as the case may be) under GCC 11.1 [Completion of Outstanding Work and Remedying Defects], which extends over twelve months except if otherwise stated in the SCC (with any extension under GCC 11.3 [Extension of Defects Liability Period]), calculated from the date on which the Works or Section is completed as certified under GCC 10.1 [Taking Over of the Works and Sections]. “Performance Certificate” means the certificate issued under GCC 11.9 [Performance Certificate]. “day” means a calendar day and “year” means 365 days. |
| 1.1.4 Money and Payments | “Accepted Contract Amount” means the amount accepted in the Letter of Acceptance for the execution and completion of the Works and the remedying of any defects. “Contract Price” means the price defined in GCC 14.1 [The Contract Price], and includes adjustments in accordance with the Contract. “Cost” means all expenditure reasonably incurred (or to be incurred) by the Contractor, whether on or off the Site, including overhead and similar charges, but does not include profit. “Final Payment Certificate” means the payment certificate issued under GCC 14.13 [Issue of Final Payment Certificate]. “Final Statement” means the statement defined in GCC 14.11 [Application for Final Payment Certificate]. “Foreign Currency” means a currency in which part (or all) of the Contract Price is payable, but not the Local Currency. “Interim Payment Certificate” means a payment certificate issued under GCC 14 [Contract Price and Payment], other than the Final Payment Certificate. “Local ‘’Currency” means the currency of the Country. “Payment Certificate” means a payment certificate issued under GCC 14 [Contract Price and Payment]. “Provisional Sum” means a sum (if any) which is specified in the Contract as a provisional sum, for the execution of any part of the Works or for the supply of Plant, Materials or services under GCC 13.5 [Provisional Sums]. “Retention Money” means the accumulated retention moneys which the Employer retains under GCC 14.3 [Application for Interim Payment Certificates] and pays under GCC 14.9 [Payment of Retention Money]. “Statement” means a statement submitted by the Contractor as part of an application, under GCC 14 [Contract Price and Payment], for a payment certificate. |
| 1.1.5 Works and Goods | “Contractor’s Equipment” means all apparatus, machinery, vehicles and other things required for the execution and completion of the Works and the remedying of any defects. However, Contractor’s Equipment excludes Temporary Works, Employer’s Equipment (if any), Plant, Materials and any other things intended to form or forming part of the Permanent Works. “Goods” means Contractor’s Equipment, Materials, Plant and Temporary Works, or any of them as appropriate. “Materials” means things of all kinds (other than Plant) intended to form or forming part of the Permanent Works, including the supply-only materials (if any) to be supplied by the Contractor under the Contract. “Permanent Works” means the permanent works to be executed by the Contractor under the Contract. “Plant” means the apparatus, machinery and other equipment intended to form or forming part of the Permanent Works, including vehicles purchased for the Employer and relating to the construction or operation of the Works. “Section” means a part of the Works specified in the SCC as a Section (if any). “Temporary Works” means all temporary works of every kind (other than Contractor’s Equipment) required on Site for the execution and completion of the Permanent Works and the remedying of any defects. “Works” mean the Permanent Works and the Temporary Works, or either of them as appropriate. |
| 1.1.6 Other Definitions | “Contractor’s Documents” means the calculations, computer programs and other software, drawings, manuals, models and other documents of a technical nature (if any) supplied by the Contractor under the Contract. “Country” means the country in which the Site (or most of it) is located, where the Permanent Works are to be executed. “Employer’s Equipment” means the apparatus, machinery and vehicles (if any) made available by the Employer for the use of the Contractor in the execution of the Works, as stated in the Employer’s Requirement; but does not include Plant which has not been taken over by the Employer. “Force Majeure” is defined in GCC 19 [Force Majeure]. “Laws” means all national (or state) legislation, statutes, ordinances and other laws, and regulations and by-laws of any legally constituted public authority. “Performance Security” means the security (or securities, if any) under GCC 4.2 [Performance Security]. “Site” means the place stated in the SCC where the Permanent Works are to be executed including storage and working areas and to which Plant and Materials are to be delivered and any other places as may be specified in the SCC as forming part of the Site. “Unforeseeable” means not reasonably foreseeable by an experienced contractor by the Base Date. “Variation” means any change to the Works, which is instructed or approved as a variation under GCC 13 [Variations and Adjustments]. |
| 1.2 Interpretation | In the Contract, except where the context requires otherwise: - words indicating one gender include all genders; - words indicating the singular also include the plural and words indicating the plural also include the singular; - provisions including the word “agree,” “agreed” or “agreement” require the agreement to be record in writing; - “written” or “in writing” means hand-written, type-written, printed or electronically made, and resulting in a permanent record; and - the word “Bid” is synonymous with “bid”, and “Bidder” with “bidder” and the words “Bid documents” with “bidding documents” The marginal words and other headings shall not be taken into consideration in the interpretation of these Conditions. |
| 1.3 Communications | Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is received by the concerned party. The language for communications shall be English |
| 1.4 Governing Language and Law | The governing language of the Contract shall be English. The Contract shall be governed by the laws of Tanzania |
| 1.5 Priority of Documents | The documents forming the Contract are to be taken as mutually explanatory of one another. For the purposes of interpretation, the priority of the documents shall be in accordance with the following sequence: - Form of Agreement; - the Letter of Acceptance; - Minutes of negotiations and addenda (if any); - the Form of Bid; - the Special Conditions of Contract; - these General Conditions of Contract; - the Employer’s Requirements and Drawings (if any); - the Schedules; - Contractor’s Proposal; and - any other documents listed in the SCC forming part of the Contract. If an ambiguity or discrepancy is found in the documents, the Project Manager shall issue any necessary clarification or instruction. |
| 1.6 Assignment | The Contractor shall not assign the whole or any part of the Contract or any benefit or interest in or under the Contract. However, the contractor: - may assign the whole or any part with the prior consent in writing of the Employer; and - may, as security in favour of a bank or financial institution, assign its right to any moneys due, or to become due, under the Contract. |
| 1.7 Care and Supply of Documents | Each of the Contractor’s Documents shall be in the custody and care of the Contractor, unless and until taken over by the Employer. Unless otherwise stated in the Contract, the Contractor shall supply to the Project Manager number of copies of Contractor’s Documents stated in the SCC. The Contractor shall keep, on the Site, a copy of the Contract, publications named in the Employer’s Requirements, the Contractor’s Documents including Drawings and approved Variations and other communications given under the Contract. Authorized personnel of the Employer shall have the right to access to the aforementioned documents at all reasonable times. If a Party becomes aware of an error or defect of technical nature in a document which was prepared for use in executing the Works, the Party shall promptly give notice to the other Party of such error or defect. |
| 1.8 Error in the Employer’s Requirements | If the Contractor suffers delay and/or incurs Cost as a result of an error in the Employer requirements, and experienced Contractor exercising due care would not have discovered the error when scrutinizing the employer’s requirements under GCC 5.1 (General Design Obligations), the contractor shall give notice to the Project Manager and may be entitled subject to GCC 20.1 (contractor’s claims) to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion]. After receiving this further notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| 1.9 Employer’s Use of Contractor’s Documents | The Contractor shall retain the copyright and other intellectual property rights in the Contractor’s Documents and other design documents made by (or on behalf of) the Contractor. The Contractor shall be deemed (by signing the Contract) to give to the Employer a non-terminable transferable non-exclusive royalty-free licence to copy, use and communicate the Contractor’s Documents, including making and using modifications of them. This licence shall: - apply throughout the actual or intended working life (whichever is longer) of the relevant parts of the Works, - entitle any person in proper possession of the relevant part of the Works to copy, use and communicate the Contractor’s Documents for the purposes of completing, operating, maintaining, altering, adjusting, repairing and demolishing the Works, and - in the case of Contractor’s Documents which are in the form of computer programs and other software, permit their use on any computer on the Site and other places as envisaged by the Contract, including replacements of any computers supplied by the Contractor. The Contractor’s Documents and other design documents made by the Contractor shall not, without the Contractor’s consent, be used, copied or communicated to a third party by (or on behalf of) the Employer for purposes other than those permitted under this GCC. |
| 1.10 Contractor’s Use of Employer’s Documents | The Employer shall retain the copyright and other intellectual property rights in the Employer’s requirements including Drawings and other documents made by (or on behalf of) the Employer. The Contractor may, at his cost, copy, use, and obtain communication of these documents for the purposes of the Contract. They shall not, without the Employer’s consent, be copied, used or communicated to a third party by the Contractor, except as necessary for the purposes of the Contract. |
| 1.11 Confidential Details | The Contractor shall disclose all such confidential and other information as may be reasonably required by the Employer in order to verify the Contractor’s compliance with the Contract and allow its proper implementation. |
| 1.12 Compliance with Laws | The Contractor shall, in performing the Contract, comply with applicable Laws. Unless otherwise stated in the SCC: - the Employer shall have obtained (or shall obtain) the planning, zoning, or similar permission for the Permanent Works, and any other permissions described in the Employer’s Requirement as having been (or to be) obtained by the Employer; and the Employer shall indemnify and hold the Contractor harmless against and from the consequences of any failure to do so; and - the Contractor shall give all notices, pay all taxes, duties and fees, and obtain all permits, licenses and approvals, as required by the Laws in relation to the design, execution and completion of the Works and the remedying of any defects; and the Contractor shall indemnify and hold the Employer harmless against and from the consequences of any failure to do so. |
| 1.13 Taxes and Duties | The Contractor, Sub-contractors and Personnel shall pay such taxes, duties, fees and other impositions as may be levied under the Applicable Law unless otherwise stated in the SCC. |
| 1.14 Joint and Several Liability | If the Contractor constitutes a joint venture, consortium, association of firms or other unincorporated grouping of two or more persons: - these persons shall be deemed to be jointly and severally liable to the Employer for the performance of the Contract; - these persons shall notify the Employer of their leader who shall have authority to bind the Contractor and each of these persons; and - the Contractor shall not alter its composition or legal status without the prior consent of the Employer. |
| 1.15 Instructions, Inspections and Audits | The Employer’s personnel shall at all reasonable times during construction of the Work be entitled to examine, inspect, measure and test the materials and workmanship, and to check the progress of the construction. If the Project Manager instructs the contractor to carry out a test not specified in the Employer’s Requirement to check whether any work has a defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no defect, the test shall be a Compensation Event. The Contractor shall permit the Funding Source named in the SCC to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by auditors appointed by the Funding Source, if so required by the Funding Source. |
| - The Employer |  |
| 2.1 Right of Access to the Site | The Employer shall give the Contractor right of access to, and possession of, all parts of the Site within the time (or times) stated in the SCC. The right and possession may not be exclusive to the Contractor. If, under the Contract, the Employer is required to give (to the Contractor) possession of any foundation, structure, plant or means of access, the Employer shall do so in the time and manner stated in the Employer’s requirements. However, the Employer may withhold any such right or possession until the Performance Security has been received. If no such time is stated in the SCC, the Employer shall give the Contractor right of access to, and possession of, the Site within such times as required to enable the Contractor to proceed without disruption in accordance with the programme submitted under GCC 8.3 [Programme]. If the Contractor suffers delay and/or incurs Cost as a result of a failure by the Employer to give any such right or possession within such time, the Contractor shall give notice to the Project Manager and may be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion], and After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. However, if and to the extent that the Employer’s failure was caused by any error or delay by the Contractor, including an error in, or delay in the submission of, any of the Contractor’s Documents, the Contractor shall not be entitled to such extension of time and any associated costs. |
| 2.2 Permits, Licences or Approvals | The Employer shall provide, at the request of the Contractor, such reasonable assistance as to allow the Contractor to obtain properly: - copies of the Laws of the Country which are relevant to the Contract but are not readily available, and - any permits, licences or approvals required by the Laws of the Country: - which the Contractor is required to obtain under GCC 1.12 [Compliance with Laws], - for the delivery of Goods, including clearance through customs, and - for the export of Contractor’s Equipment when it is removed from the Site. |
| 2.3 Employer’s Personnel | The Employer shall be responsible for ensuring that the Employer’s Personnel and the Employer’s other contractors on the Site: - co-operate with the Contractor’s efforts under GCC 4.6 [Co-operation], and - take actions similar to those which the Contractor is required to take under sub-paragraphs (a), (b) and (c) of GCC 4.8 [Safety Procedures] and under GCC 4.18 [Protection of the Environment]. |
| 2.4 Suspension of Financing | If the Government has notified the Employer that the Government has suspended funds, which finances in whole or in part the execution of the Works, the Employer shall give notice of such suspension to the Contractor with detailed particulars, including the date of such notification, with a copy to the Project Manager, within 7 days of the Employer having received the suspension notification from the Government. In the event that the source of financing is suspended to the Employer, from which part of the payments to the Contractor are being made: (a) The Employer shall notify the Contractor of such suspension within Seven (7) days of having received the financing agency’s suspension notice. (b) After the Notice has been issued and within fourteen (14) working days, the Parties shall mutually agree on the future events of the Contract |
| 2.5 Employer’s Claims | If the Employer considers himself to be entitled to any payment under any Clause of these Conditions or otherwise in connection with the Contract, and/or to any extension of the Defects Liability Period, the Employer or the Project Manager shall give notice and particulars to the Contractor. However, notice is not required for payments due under GCC 4.19 [Electricity, Water and Gas], under GCC 4.20 [Employer’s Equipment and Free-Issue Material], or for other services requested by the Contractor. The notice shall be given as soon as practicable and no longer than 28 days after the Employer became aware, or should have become aware, of the event or circumstances giving rise to the claim. A notice relating to any extension of the Defects Liability Period shall be given before the expiry of such period. The particulars shall specify the Clause or other basis of the claim, and shall include substantiation of the amount and/or extension to which the Employer considers himself to be entitled in connection with the Contract. The Project Manager shall then proceed in accordance with GCC 3.5 [Determinations] to agree or determine (i) the amount (if any) which the Employer is entitled to be paid by the Contractor, and/or (ii) the extension (if any) of the Defects Liability Period in accordance with GCC 11.3 [Extension of Defects Liability Period]. This amount may be included as a deduction in the Contract Price and Payment Certificates. The Employer shall only be entitled to set off against or make any deduction from an amount certified in a Payment Certificate, or to otherwise claim against the Contractor, in accordance with this GCC. |
| - The Project Manager |  |
| 3.1 Project Manager’s Appointment, Duties and Authority | The Employer shall appoint the Project Manager who shall carry out the duties assigned to him in the Contract. The Project Manager shall be an independent legal entity or firm duly registered by relevant professional bodies in Tanzania and contracted by the Employer. The Project Manager’s staff shall include suitably qualified Architects/Engineers and other professionals who are competent to carry out these duties. The Project Manager shall have no authority to amend the Contract without approval of the Employer. The Project Manager may exercise the authority attributable to the Project Manager as specified in or necessarily to be implied from the Contract. Notwithstanding the provisions of this Contract, if the Project Manager is required to obtain the approval of the Employer before exercising a specified authority, the requirements shall be as stated in the SCC. The Employer shall promptly inform the Contractor of any change to the authority attributed to the Project Manager. However, whenever the Project Manager exercises a specified authority for which the Employer’s approval is required, then (for the purposes of the Contract) the Project Manager shall seek and obtain a written approval of the Employer. Except as otherwise stated in these Conditions: (a) whenever carrying out duties or exercising authority, specified in or implied by the Contract, the Project Manager shall be deemed to act for the Employer; (b) the Project Manager has no authority to relieve either Party of any duties, obligations or responsibilities under the Contract; and - any approval, check, certificate, consent, examination, inspection, instruction, notice, proposal, request, test, or similar act by the Project Manager (including absence of disapproval) shall not relieve the Contractor from any responsibility he has under the Contract, including responsibility for errors, omissions, discrepancies and non-compliances. - Any act by the Project Manager in response to a Contractor’s request, except otherwise expressly specified, shall be notified in writing to the Contractor within the period stated in the SCC. Provided that such time shall not exceed 28 days from receipt of the request. The following provisions shall apply: The Project Manager shall obtain the specific approval of the Employer before taking action under the following GCCs of these Conditions: (a) GCC 4.12 [Unforeseeable Physical Conditions]: Agreeing or determining an extension of time and/or additional cost. (b) GCC 13.1 [Right to Vary]: Instructing a Variation, except; (i) in an emergency situation as determined by the Project Manager, or (ii) if such a Variation would not increase the total Contract Amount (c) GCC 13.3 [Variation Procedure]: Approving a proposal for Variation submitted by the Contractor in accordance with GCC 13.1 or 13.2. (d) GCC 13.4 [Payment in Applicable Currencies]: Specifying the amount payable in each of the applicable currencies. (e) Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Project Manager, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibility under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Project Manager, be necessary to abate or reduce the risk. The Contractor shall forthwith comply, despite the absence of approval of the Employer, with any such instruction of the Project Manager. The Project Manager shall determine an addition to the Contract Price, in respect of such instruction, in accordance with GCC 13 [Variations and Adjustments] and shall notify the Contractor accordingly, with a copy to the Employer. |
| 3.2 Delegation by the Project Manager | The Project Manager may from time to time assign duties and delegate authority to assistants, and may also revoke such assignment or delegation. These assistants may include a resident Architect/Engineer and/or independent inspectors appointed to inspect and/or test items of Plant and/or Materials. The assignment, delegation or revocation shall be in writing and shall not take effect until copies have been received by both Parties. However, unless otherwise agreed by both Parties, the Project Manager shall not delegate the authority to determine any matter in accordance with GCC 3.5 [Determinations]. Assistants shall be suitably qualified persons, who are competent to carry out these duties and exercise this authority, and who are fluent in the language for communications defined in GCC 1.4 [Law and Language]. Each assistant, to whom duties have been assigned or authority has been delegated, shall only be authorised to issue instructions to the Contractor to the extent defined by the delegation. Any approval, check, certificate, consent, examination, inspection, instruction, notice, proposal, request, test, or similar act by an assistant, in accordance with the delegation, shall have the same effect as though the act had been an act of the Project Manager. However: - any failure to disapprove any work, Plant or Materials shall not constitute approval, and shall therefore not prejudice the right of the Project Manager to reject the work, Plant or Materials; - if the Contractor questions any determination or instruction of an assistant, the Contractor may refer the matter to the Project Manager, who shall promptly confirm, reverse or vary the determination or instruction. |
| 3.3 Instructions of the Project Manager | The Project Manager may issue to the Contractor (at any time) instructions and additional or modified Drawings which may be necessary for the execution of the Works and the remedying of any defects, all in accordance with the Contract. The Contractor shall only take instructions from the Project Manager, or from an assistant to whom the appropriate authority has been delegated under this Clause . If an instruction constitutes a Variation, GCC 13 [Variations and Adjustments] shall apply. The Contractor shall comply with the instructions given by the Project Manager or delegated assistant, on any matter related to the Contract. Whenever practicable, their instructions shall be given in writing. If the Project Manager or a delegated assistant: - gives an oral instruction, - receives a written confirmation of the instruction, from (or on behalf of) the Contractor, within two working days after giving the instruction, and - does not reply by issuing a written rejection and/or instruction within two working days after receiving the confirmation, then the confirmation shall constitute the written instruction of the Project Manager or delegated assistant (as the case may be). |
| ### 3.4 Replacement of the Project Manager | Notwithstanding GCC 3.1, if the Employer intends to replace the Project Manager, the Employer shall, not less than 21 days before the intended date of replacement, give notice to the Contractor of the name, address and relevant experience of the intended replacement Project Manager. If the Contractor considers the intended replacement Project Manager to be unsuitable, he has the right to raise reasonable objection against him by notice to the Employer, with supporting particulars, and the Employer shall give consideration to this objection. |
| 3.5 Determinations | Whenever these Conditions provide that the Project Manager shall proceed in accordance with this GCC 3.5 to agree or determine any matter, the Project Manager shall consult with each Party in an endeavour to reach agreement. If agreement is not achieved, the Project Manager shall make a fair determination in accordance with the Contract, taking due regard of all relevant circumstances. The Project Manager shall give notice to both Parties of each agreement or determination, with supporting particulars within 14 working days from the receipt of the corresponding claim or request except when otherwise specified. Each Party shall give effect to each agreement or determination unless and until revised under GCC 20 [Claims, Disputes and Arbitration]. |
| - The Contractor |  |
| 4.1 Contractor’s General Obligations | The Contractor shall design, execute and complete the Works in accordance with the Contract and with the Project Manager’s instructions, and shall remedy any defects in the Works. The Contractor shall provide the Plant and Contractor’s Documents specified in the Contract, and all Contractor’s Personnel, Goods, consumables and other things and services, whether of a temporary or permanent nature, required in and for this design, execution, completion and remedying of defects. The works shall include any work which is necessary to satisfy the Employer’s Requirements, contractor’s proposal and Schedules, or is implied by the contract, and all works which (although not mentioned in the contract) are necessary for stability or for the completion, or safe and proper operation, of the works. The Contractor shall be responsible for the adequacy, stability and safety of all Site operations and of all methods of construction. The Contractor shall, whenever required by the Project Manager, submit details of the arrangements and methods which the Contractor proposes to adopt for the execution of the Works. No significant alteration to these arrangements and methods shall be made without this having previously been notified to the Project Manager. |
| 4.2 Performance Security | The Contractor shall obtain (at his cost) a Performance Security for proper performance, in the form, amount and currencies stated in the SCC. The Contractor shall deliver the Performance Security to the Employer within 14 working days after receiving the Letter of Acceptance, and shall send a copy to the Project Manager. The Performance Security shall be issued by an entity and from within a country (or other jurisdiction) approved by the Employer, and shall be in the form annexed to the SCC or in another form approved by the Employer. The Contractor shall ensure that the Performance Security is valid and enforceable until the Contractor has executed and completed the Works and remedied any defects. If the terms of the Performance Security specify its expiry date, and the Contractor has not become entitled to receive the Performance Certificate by the date 28 days prior to the expiry date, the Contractor shall extend the validity of the Performance Security until the Works have been completed and any defects have been remedied. The Employer shall not make a claim under the Performance Security, except for amounts to which the Employer is entitled under the Contract in the event of: - failure by the Contractor to extend the validity of the performance security as described in the preceding paragraph, in which event the Employer may claim the full amount of the performance security; - failure by the Contractor to pay the Employer an amount due, as either agreed by the Contractor or determined under GCC 2.5 [Employer’s Claims] or GCC 20 [Claims, Disputes and Arbitration], within 42 days after this agreement or determination, - failure by the Contractor to remedy a default within 42 days after receiving the Employer’s notice requiring the default to be remedied, or - Circumstances which entitle the Employer to termination under GCC 15.2 [Termination by Employer], irrespective of whether notice of termination has been given. The Employer shall indemnify and hold the Contractor harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from a claim under the Performance Security to the extent to which the Employer was not entitled to make the claim. The Employer shall return the Performance Security to the Contractor within 21 days after receiving a copy of the Performance Certificate. |
| 4.3 Contractor’s Representative | The Contractor shall appoint the Contractor’s Representative and shall give him all authority necessary to act on the Contractor’s behalf under the Contract. Unless the Contractor’s Representative is named in the Contract, the Contractor shall, prior to the Commencement Date, submit to the Project Manager for consent the name and particulars of the person the Contractor proposes to appoint as Contractor’s Representative. If consent is withheld or subsequently revoked or if the appointed person fails to act as Contractor’s Representative, the Contractor shall similarly submit the name and particulars of another suitable person for such appointment. The Contractor shall not, without the prior consent of the Project Manager, revoke the appointment of the Contractor’s Representative or appoint a replacement. The whole time of the Contractor’s Representative shall be given to directing the Contractor’s performance of the Contract. If the Contractor’s Representative is to be temporarily absent from the Site during the execution of the Works, a suitable replacement person shall be appointed, subject to the Project Manager’s prior consent, and the Project Manager shall be notified accordingly. The Contractor’s Representative shall, on behalf of the Contractor, receive instructions under GCC 3.3 [Instructions of the Project Manager]. The Contractor’s Representative may delegate any powers, functions and authority to any competent person, and may at any time revoke the delegation. Any delegation or revocation shall not take effect until the Project Manager has received prior notice signed by the Contractor’s Representative, naming the person and specifying the powers, functions and authority being delegated or revoked. The Contractor’s Representative shall be fluent in the language for communications defined in GCC 1.4 [Law and Language]. |
| 4.4 Subcontractors | The Contractor shall not subcontract the whole of the Works. The Contractor shall be responsible for the acts or defaults of any Subcontractor, his agents or employees, as if they were the acts or defaults of the Contractor. Unless otherwise stated in the SCC: - the Contractor shall not be required to obtain consent to suppliers of Materials, or to a subcontract for which the Subcontractor is named in the Contract; - the prior consent of the Project Manager shall be obtained to other proposed Subcontractors; - the Contractor shall give the Project Manager not less than 28 days’ notice of the intended date of the commencement of each Subcontractor’s work, and of the commencement of such work on the Site; and |
| 4.5 Nominated Subcontractors | In this GCC, "nominated Subcontractor" means a Subcontractor whom the Project Manager, under GCC 13 [Variations and Adjustments], instructs the Contractor to employ as a Subcontractor. The Contractor shall not be under any obligation to employ a nominated Subcontractor against whom the Contractor raises reasonable objection by notice to the Project Manager as soon as practicable, with supporting particulars. |
| 4.6 Co-operation | The Contractor shall, as specified in the Contract or as instructed by the Project Manager, allow appropriate opportunities for carrying out work to: - the Employer’s Personnel, - any other contractors employed by the Employer, and - the personnel of any legally constituted public authorities, who may be employed in the execution on or near the Site of any work not included in the Contract. Any such instruction may constitute a Variation if and to the extent that it causes the Contractor to suffer delays and/or to incur Unforeseeable Cost. Services for these personnel and other contractors may include the use of Contractor’s Equipment, Temporary Works or access arrangements which are the responsibility of the Contractor. The Contractor shall be responsible for his construction activities on the Site, and shall co-ordinate his own activities with those of other contractors to the extent (if any) specified in the Employer's Requirements. If, under the Contract, the Employer is required to give to the Contractor possession of any foundation, structure, plant or means of access in accordance with Contractor’s Documents, the Contractor shall submit such documents to the Project Manager in the time and manner stated in the Employer's Requirements. |
| 4.7 Setting Out | The Contractor shall set out the Works in relation to original points, lines and levels of reference specified in the Contract or notified by the Project Manager. The Contractor shall be responsible for the correct positioning of all parts of the Works, and shall rectify any error in the positions, levels, dimensions or alignment of the Works. The Employer shall be responsible for any errors in these specified or notified items of reference, but the Contractor shall use reasonable efforts to verify their accuracy before they are used. If the Contractor suffers delay and/or incurs cost from executing work which was necessitated by an error in these items of reference, and an experienced contractor could not reasonably have discovered such error and avoided this delay and/or cost, the Contractor shall give notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion]. After receiving this further notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| 4.8 Safety Procedures | The Contractor shall: - comply with all applicable safety regulations, - take care for the safety of all persons entitled to be on the Site, - use reasonable efforts to keep the Site and Works clear of unnecessary obstruction so as to avoid danger to these persons, - provide fencing, lighting, guarding and watching of the Works until completion and taking over under GCC 10 [Employer’s Taking Over], and - provide any Temporary Works (including roadways, footways, guards and fences) which may be necessary, because of the execution of the Works, for the use and protection of the public and of owners and occupiers of adjacent land. |
| 4.9 Quality Assurance | The Contractor shall institute a quality assurance system to demonstrate compliance with the requirements of the Contract. The system shall be in accordance with the details stated in the Contract. The Project Manager shall be entitled to audit any aspect of the system. Details of all procedures and compliance documents shall be submitted to the Project Manager for information before each design and execution stage is commenced. When any document of a technical nature is issued to the Project Manager, evidence of the prior approval by the Contractor himself shall be apparent on the document itself. Compliance with the quality assurance system shall not relieve the Contractor of any of his duties, obligations or responsibilities under the Contract. |
| 4.10 Site Data | The Employer shall have made available to the Contractor for his information, prior to the Base Date, all relevant data in the Employer’s possession on sub-surface and hydrological conditions at the Site, including environmental aspects. The Employer shall similarly make available to the Contractor all such data which come into the Employer’s possession after the Base Date. The Contractor shall be responsible for interpreting all such data. To the extent which was practicable (taking account of cost and time), the Contractor shall be deemed to have obtained all necessary information as to risks, contingencies and other circumstances which may influence or affect the Bid or Works. To the same extent, the Contractor shall be deemed to have inspected and examined the Site, its surroundings, the above data and other available information, and to have been satisfied before submitting the Bid as to all relevant matters, including (without limitation): - the form and nature of the Site, including sub-surface conditions, - the hydrological and climatic conditions, - the extent and nature of the work and Goods necessary for the execution and completion of the Works and the remedying of any defects, - the Laws, procedures and labour practices of the Country, and - the Contractor’s requirements for access, accommodation, facilities, personnel, power, transport, water and other services. |
| 4.11 Sufficiency of the Accepted Contract Amount | The Contractor shall be deemed to: - have satisfied himself as to the correctness and sufficiency of the Accepted Contract Amount, and - have based the Accepted Contract Amount on the data, interpretations, necessary information, inspections, examinations and satisfaction as to all relevant matters referred to in GCC 4.10 [Site Data] and any further data relevant to the Contractor’s design. Unless otherwise stated in the Contract, the Accepted Contract Amount covers all the Contractor’s obligations under the Contract (including those under Provisional Sums, if any) and all things necessary for the proper design, execution and completion of the Works and the remedying of any defects. |
| 4.12 Unforeseeable Physical Conditions | In this GCC, “physical conditions” means natural physical conditions and man-made and other physical obstructions and pollutants, which the Contractor encounters at the Site when executing the Works, including sub-surface and hydrological conditions but excluding climatic conditions. If the Contractor encounters adverse physical conditions which he considers to have been Unforeseeable, the Contractor shall give notice to the Project Manager as soon as practicable. This notice shall describe the physical conditions, so that they can be inspected by the Project Manager, and shall set out the reasons why the Contractor considers them to be Unforeseeable. The Contractor shall continue executing the Works, using such proper and reasonable measures as are appropriate for the physical conditions, and shall comply with any instructions which the Project Manager may give. If an instruction constitutes a Variation, GCC 13 [Variations and Adjustments] shall apply. If and to the extent that the Contractor encounters physical conditions which are Unforeseeable, gives such a notice, and suffers delay and/or incurs Cost due to these conditions, the Contractor may be entitled subject to notice under GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for any such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion]. After receiving this further notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. However, before additional Cost is finally agreed or determined under sub-paragraph (ii), the Project Manager may also review whether other physical conditions in similar parts of the Works (if any) were more favourable than could reasonably have been foreseen when the Contractor submitted the Bid. If and to the extent that these more favourable conditions were encountered, the Project Manager may proceed in accordance with GCC 3.5 [Determinations] to agree or determine the reductions in Cost which were due to these conditions, which may be included (as deductions) in the Contract Price and Payment Certificates. However, the net effect of all adjustments under sub-paragraph (b) and all these reductions, for all the physical conditions encountered in similar parts of the Works, shall not result in a net reduction in the Contract Price. The Project Manager may take account of any evidence of the physical conditions foreseen by the Contractor when submitting the Bid, which may be made available by the Contractor, but shall not be bound by any such evidence. |
| 4.13 Rights of Way and Facilities | The Contractor shall bear all costs and charges for special and/or temporary rights-of-way which he may require, including those for access to the Site. The Contractor shall also obtain, at his risk and cost, any additional facilities outside the Site which he may require for the purposes of the Works. |
| 4.14 Avoidance of Interference | The Contractor shall not interfere unnecessarily or improperly with: - the convenience of the public, or - the access to and use and occupation of all roads and footpaths, irrespective of whether they are public or in the possession of the Employer or of others. The Contractor shall indemnify and hold the Employer harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from any such unnecessary or improper interference. |
| 4.15 Access Route | The Contractor shall be deemed to have been satisfied as to the suitability and availability of access routes to the Site at Base Date. The Contractor shall use reasonable efforts to prevent any road or bridge from being damaged by the Contractor’s traffic or by the Contractor’s Personnel. These efforts shall include the proper use of appropriate vehicles and routes. Except as otherwise stated in these Conditions: - the Contractor shall (as between the Parties) be responsible for any maintenance which may be required for his use of access routes; - the Contractor shall provide all necessary signs or directions along access routes, and shall obtain any permission which may be required from the relevant authorities for his use of routes, signs and directions; - the Employer shall not be responsible for any claims which may arise from the use or otherwise of any access route; - the Employer does not guarantee the suitability or availability of particular access routes; and - Costs due to non-suitability or non-availability, for the use required by the Contractor, of access routes shall be borne by the Contractor. |
| 4.16 Transport of Goods | Unless otherwise stated in the SCC: the Contractor shall give the Project Manager not less than 21 days notice of the date on which any Plant or a major item of other Goods will be delivered to the Site; the Contractor shall be responsible for packing, loading, transporting, receiving, unloading, storing and protecting all Goods and other things required for the Works; and the Contractor shall indemnify and hold the Employer harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from the transport of Goods, and shall negotiate and pay all claims arising from their transport. |
| ### 4.17 Contractor’s Equipment | The Contractor shall be responsible for all Contractor’s Equipment. When brought on to the Site, Contractor’s Equipment shall be deemed to be exclusively intended for the execution of the Works. The Contractor shall not remove from the Site any major items of Contractor’s Equipment without the consent of the Project Manager. However, consent shall not be required for vehicles transporting Goods or Contractor’s Personnel off Site. |
| 4.18 Protection of the Environment | The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Employer’s Requirement or prescribed by applicable Laws. |
| 4.19 Electricity, Water and Gas | The Contractor shall, except as stated below, be responsible for the provision of all power, water and other services he may require for his construction activities and to the extent defined in the Employer’s Requirements, for the tests. The Contractor shall be entitled to use for the purposes of the Works such supplies of electricity, water, gas and other services as may be available on the Site and of which details and prices are given in the Employer’s Requirement. The Contractor shall, at his risk and cost, provide any apparatus necessary for his use of these services and for measuring the quantities consumed. The quantities consumed and the amounts due (at these prices) for such services shall be agreed or determined by the Project Manager in accordance with GCC 2.5 [Employer’s Claims] and GCC 3.5 [Determinations]. The Contractor shall pay these amounts to the Employer. |
| ### 4.20 Employer’s Equipment and Free-Issue Materials | The Employer shall make the Employer’s Equipment (if any) available for the use of the Contractor in the execution of the Works in accordance with the details, arrangements and prices stated in the Schedule of Prices. Unless otherwise stated in the Employer’s Requirement: - the Employer shall be responsible for the Employer’s Equipment, except that - the Contractor shall be responsible for each item of Employer’s Equipment whilst any of the Contractor’s Personnel is operating it, driving it, directing it or in possession or control of it. The appropriate quantities and the amounts due (at such stated prices) for the use of Employer’s Equipment shall be agreed or determined by the Project Manager in accordance with GCC 2.5 [Employer’s Claims] and GCC 3.5 [Determinations]. The Contractor shall pay these amounts to the Employer. The Employer shall supply, free of charge, the “free-issue materials” (if any) in accordance with the details stated in the Employer’s Requirement. The Employer shall, at his risk and cost, provide these materials at the time and place specified in the Contract. The Contractor shall then visually inspect them, and shall promptly give notice to the Project Manager of any shortage, defect or default in these materials. Unless otherwise agreed by both Parties, the Employer shall immediately rectify the notified shortage, defect or default. After this visual inspection, the free-issue materials shall come under the care, custody and control of the Contractor. The Contractor’s obligations of inspection, care, custody and control shall not relieve the Employer of liability for any shortage, defect or default not apparent from a visual inspection. |
| ### 4.21 Progress Reports | Unless otherwise stated in the SCC, monthly progress reports shall be prepared by the Contractor and submitted to the Project Manager in six copies. The first report shall cover the period up to the end of the first calendar month following the Commencement Date. Reports shall be submitted monthly thereafter, each within 7 working days after the last day of the period to which it relates. Reporting shall continue until the Contractor has completed all work which is known to be outstanding at the completion date stated in the Taking-Over Certificate for the Works. Each report shall include: - charts and detailed descriptions of progress, including each stage of design (if any), Contractor’s Documents, procurement, manufacture, delivery to Site, construction, erection and testing; and including these stages for work by each nominated Subcontractor (as defined in GCC 4.5 [Nominated Subcontractors]), - photographs showing the status of manufacture and of progress on the Site; - for the manufacture of each main item of Plant and Materials, the name of the manufacturer, manufacture location, percentage progress, and the actual or expected dates of: - commencement of manufacture, - Contractor’s inspections, - tests, and - shipment and arrival at the Site; - the details described in GCC 6.10 [Records of Contractor’s Personnel and Equipment]; - copies of quality assurance documents, test results and certificates of Materials; - list of notices given under GCC 2.5 [Employer’s Claims] and notices given under GCC 20.1 [Contractor’s Claims]; - safety statistics, including details of any hazardous incidents and activities relating to environmental aspects and public relations; and - comparisons of actual and planned progress, with details of any events or circumstances which may jeopardise the completion in accordance with the Contract, and the measures being (or to be) adopted to overcome delays. |
| 4.22 Security of the Site | Unless otherwise stated in the SCC: - The Contractor shall be responsible for security of the site; - the Contractor shall be responsible for keeping unauthorised persons off the Site; and - authorised persons shall be limited to the Contractor’s Personnel and the Employer’s Personnel; and to any other personnel notified to the Contractor, by the Employer or the Project Manager, as authorised personnel of the Employer’s other contractors on the Site. |
| 4.23 Contractor’s Operations on Site | The Contractor shall confine his operations to the Site, and to any additional areas which may be obtained by the Contractor and agreed by the Project Manager as additional working areas. The Contractor shall take all necessary precautions to keep Contractor’s Equipment and Contractor’s Personnel within the Site and these additional areas, and to keep them off adjacent land. During the execution of the Works, the Contractor shall keep the Site free from all unnecessary obstruction, and shall store or dispose of any Contractor’s Equipment or surplus materials. The Contractor shall clear away and remove from the Site any wreckage, rubbish and Temporary Works which are no longer required. Upon the issue of a Taking-Over Certificate, the Contractor shall clear away and remove, from that part of the Site and Works to which the Taking-Over Certificate refers, all Contractor’s Equipment, surplus material, wreckage, rubbish and Temporary Works. The Contractor shall leave that part of the Site and the Works in a clean and safe condition. However, the Contractor may retain on Site, during the Defects Liability Period, such Goods as are required for the Contractor to fulfill obligations under the Contract. |
| 4.24 Fossils | All fossils, coins, articles of value or antiquity and structures and other remains or things of geological or archaeological interest discovered on the Site shall, as between the Employer and the Contractor, be the absolute property of the Employer and the Contractor shall take reasonable precautions to prevent his workers or any other persons from removing or damaging any such article or thing and shall immediately upon discovery thereof and before removal acquaint the Project Manager of such discovery and carry out at the expense of the Employer the instructions of the Project Manager as to the disposal of the same. The Contractor shall, upon discovery of any such finding, promptly give notice to the Project Manager, who shall issue instructions for dealing with it. If the Contractor suffers delay and/or incurs Cost from complying with the instructions, the Contractor shall give a further notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and any associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion]. After receiving this further notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| - Design |  |
| ### 5.1 General Design Obligations | The Contractor shall carry out, and be responsible for, the design of the Works. Design shall be prepared by qualified designers who are Architects/engineers or other professionals who comply with the criteria (if any) stated in the Employer's Requirements. Unless otherwise stated in the Contract, the Contractor shall submit to the Project Manager for consent the name and particulars of each proposed designer and design Subcontractor. The Contractor warrants that he, his designers and design Subcontractors have the experience and capability necessary for the design. The Contractor undertakes that the designers shall be available to attend discussions with the Project Manager at all reasonable times, until the expiry date of the relevant Defects Liability Period. Upon receiving notice under GCC 8.1 [Commencement of Works], the Contractor shall scrutinise the Employer's Requirements (including design criteria and calculations, if any) and the items of reference mentioned in GCC 4.7 [Setting Out]. Within the period stated in the Appendix to Bid, calculated from the Commencement Date, the Contractor shall give notice to the Project Manager of any error, fault or other defect found in the Employer's Requirements or these items of reference. After receiving this notice, the Project Manager shall determine whether GCC 13 [Variation s and Adjustments] shall be applied, and shall give notice to the Contractor accordingly. If and to the extent that (taking account of cost and time) an experienced contractor exercising due care would have discovered the error, fault or other defect when examining the Site and the Employer's Requirements before submitting the Bid, the Time for Completion shall not be extended and the Contract Price shall not be adjusted. |
| ### 5.2 Contractor's Documents | The Contractor’s Documents shall comprise the technical documents specified in the Employer’s Requirements, documents required to satisfy all regulatory approvals, and the documents described in GCC 5.6 [As-Built Documents] and GCC 5.7 [Operation and Maintenance Manuals]. Unless otherwise stated in the Employer’s Requirements, the Contractor's Documents shall be written in the language for communications defined in GCC 1.4 [Law and Language]. The Contractor shall prepare all Contractors’ Documents, and shall also prepare any other documents necessary to instruct the Contractor's Personnel. The Employer's Personnel shall have the right to inspect the preparation of all these documents, wherever they are being prepared. If the Employer's Requirements describe the Contractor's Documents which are to be submitted to the Project Manager for review and/or for approval, they shall be submitted accordingly, together with a notice as described below. In the following provisions of this GCC, (i) "review period" means the period required by the Project Manager for review and (if so specified) for approval, and (ii) "Contractor's Documents" exclude any documents which are not specified as being required to be submitted for review and/or for approval. Unless otherwise stated in the Employer's Requirements, each review period shall not exceed 21 days, calculated from the date on which the Project Manager receives a Contractor's Document and the Contractor’s notice. This notice shall state that the Contractor's Document is considered ready, both for review (and approval, if so specified) in accordance with this GCC and for use. The notice shall also state that the Contractor's Document complies with the Contract, or the extent to which it does not comply. The Project Manager may, within the review period, give notice to the Contractor that a Contractor's Document fails (to the extent stated) to comply with the Contract. If a Contractor's Document so fails to comply, it shall be rectified, resubmitted and reviewed (and, if specified, approved) in accordance with this GCC, at the Contractor’s cost. For each part of the Works, and except to the extent that the prior approval or consent of the Project Manager shall have been obtained: (a) in the case of a Contractor's Document which has (as specified) been submitted for the Project Manager’s approval: (i) the Project Manager shall give notice to the Contractor that the Contractor's Document is approved, with or without comments, or that it fails (to the extent stated) to comply with the Contract; (ii) execution of such part of the Works shall not commence until the Project Manager has approved the Contractor's Document; and (iii) the Project Manager shall be deemed to have approved the Contractor's Document upon the expiry of the review periods for all the Contractor's Documents which are relevant to the design and execution of such part, unless the Project Manager has previously notified otherwise in accordance with sub-paragraph (i); (b) execution of such part of the Works shall not commence prior to the expiry of the review periods for all the Contractor's Documents which are relevant to its design and execution; (c) execution of such part of the Works shall be in accordance with these reviewed (and, if specified, approved) Contractor's Documents; and (d) if the Contractor wishes to modify any design or document which has previously been submitted for review (and, if specified, approval), the Contractor shall immediately give notice to the Project Manager. Thereafter, the Contractor shall submit revised documents to the Project Manager in accordance with the above procedure. If the Project Manager instructs that further Contractor's Documents are required, the Contractor shall prepare them promptly. Any such approval or consent, or any review (under this GCC or otherwise), shall not relieve the Contractor from any obligation or responsibility. |
| ### 5.3 Contractor’s Undertakings | The Contractor undertakes that the design, the Contractor's Documents, the execution and the completed Works will be in accordance with: (a) the Laws of Tanzania, and (b) the documents forming the Contract, as altered or modified by Variations. |
| ### 5.4 Technical Standards and Regulations | The design, the Contractor's Documents, the execution and the completed Works shall comply with the Country’s technical standards, building, construction and environmental Laws, Laws applicable to the product being produced from the Works, and other standards specified in the Employer's Requirements, applicable to the Works, or defined by the applicable Laws. All these Laws shall, in respect of the Works and each Section, be those prevailing when the Works or Section are taken over by the Employer under GCC 10 [Employer’s Taking Over]. References in the Contract to published standards shall be understood to be references to the edition applicable on the Base Date, unless stated otherwise. If changed or new applicable standards come into force in the Country after the Base Date, the Contractor shall give notice to the Project Manager and (if appropriate) submit proposals for compliance. In the event that: - the Project Manager determines that compliance is required, and - the proposals for compliance constitute a variation, then the Project Manager may initiate a Variation in accordance with GCC 13 [ Variation s and Adjustments]. |
| ### 5.5 Training | The Contractor shall carry out the training of Employer's Personnel in the operation and maintenance of the Works to the extent specified in the Employer's Requirements. If the Contract specifies training which is to be carried out before taking-over, the Works shall not be considered to be completed for the purposes of taking-over under GCC 10.1 [Taking Over of the Works and Section s] until this training has been completed. |
| ### 5.6 As-Built Documents | The Contractor shall prepare, and keep up-to-date, a complete set of "as-built" records of the execution of the Works, showing the exact as-built locations, sizes and details of the work as executed. These records shall be kept on the Site and shall be used exclusively for the purposes of this GCC. Two copies shall be supplied to the Project Manager prior to the commencement of the Tests on Completion. In addition, the Contractor shall supply to the Project Manager as-built drawings of the Works, showing all Works as executed, and submit them to the Project Manager for review under GCC 5.2 [Contractor's Documents]. The Contractor shall obtain the consent of the Project Manager as to their size, the referencing system, and other relevant details. Prior to the issue of any Taking-Over Certificate, the Contractor shall supply to the Project Manager the specified numbers and types of copies of the relevant as-built drawings, in accordance with the Employer's Requirements. The Works shall not be considered to be completed for the purposes of taking-over under GCC 10.1 [Taking Over of the Works and Section s] until the Project Manager has received these documents. |
| ### 5.7 Operation and Maintenance Manuals | Prior to commencement of the Tests on Completion, the Contractor shall supply to the Project Manager provisional operation and maintenance manuals in sufficient detail for the Employer to operate, maintain, dismantle, reassemble, adjust and repair the Plant. The Works shall not be considered to be completed for the purposes of taking-over under GCC 10.1 [Taking Over of the Works and Section s] until the Project Manager has received final operation and maintenance manuals in such detail, and any other manuals specified in the Employer's Requirements for these purposes. |
| ### 5.8 Design Error | If errors, omissions, ambiguities, inconsistencies, inadequacies or other defects are found in the Contractor's Documents, they and the Works shall be corrected at the Contractor’s cost, notwithstanding any consent or approval under this Clause |
| - Staff and Labour |  |
| 6.1 Engagement of Staff and Labour | Except as otherwise stated in the Employer’s Requirement, the Contractor shall make arrangements for the engagement of all staff and labour, local or otherwise, and for their payment, feeding, transport, and, when appropriate, housing. The Contractor shall be obliged, to the extent practicable and reasonable, to employ staff and labour in compliance with Laws of Tanzania. |
| 6.2 Rates of Wages and Conditions of Labour | The Contractor shall pay rates of wages, and observe conditions of labour, which are not lower than those established for the trade or industry where the work is carried out. If no established rates or conditions are applicable, the Contractor shall pay rates of wages and observe conditions which are not lower than the general level of wages and conditions observed locally by Employers whose trade or industry is similar to that of the Contractor. |
| 6.3 Persons in the Service of Employer | The Contractor shall not recruit, or attempt to recruit, staff and labour from amongst the Employer’s Personnel. |
| 6.4 Labour Laws | The Contractor shall comply with all the relevant labour Laws applicable to the Contractor’s Personnel, including Laws relating to their employment, health, safety, welfare, immigration and emigration, and shall allow them all their legal rights. The Contractor shall require his employees to obey all applicable Laws, including those concerning safety at work. |
| 6.5 Facilities for Staff and Labour | Except as otherwise stated in the Employer’s Requirement, the Contractor shall provide and maintain all necessary accommodation and welfare facilities for the Contractor’s Personnel. The Contractor shall also provide facilities for the Employer’s Personnel as stated in the Employer’s Requirement. The Contractor shall not permit any of the Contractor’s Personnel to maintain any temporary or permanent living quarters within the structures forming part of the Permanent Works. |
| 6.6 Health and Safety | The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel and the Public in accordance with the governing occupational health and safety Laws. In collaboration with local health authorities, the Contractor shall ensure that medical staff, first aid facilities, sick bay and ambulance service are available at all times at the Site and at any accommodation for Contractor’s and Employer’s Personnel, and that suitable arrangements are made for all necessary welfare and hygiene requirements and for the prevention of epidemics. The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. This person shall be qualified for this responsibility, and shall have the authority to issue instructions and take protective measures to prevent accidents. Throughout the execution of the Works, the Contractor shall provide whatever is required by this person to exercise this responsibility and authority. The Contractor shall send, to the Project Manager, details of any accident as soon as practicable after its occurrence. The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require. The Contractor shall conduct an HIV-AIDS awareness programme via an approved service provider, and shall undertake such other measures as are specified in this Contract to reduce the risk of the transfer of the HIV between and among the Contractor’s Personnel and the local community, to promote early diagnosis and to assist affected individuals. |
| 6.7 Contractor’s Superintendence | Throughout the execution of the Works, and as long thereafter as is necessary to fulfil the Contractor’s obligations, the Contractor shall provide all necessary superintendence to plan, arrange, direct, manage, inspect and test the work. Superintendence shall be given by a sufficient number of persons having adequate knowledge of the language for communications (defined in GCC 1.4 [Law and Language]) and of the operations to be carried out (including the methods and techniques required, the hazards likely to be encountered and methods of preventing accidents), for the satisfactory and safe execution of the Works. |
| 6.8 Contractor’s Personnel | The Contractor’s Personnel shall be appropriately qualified, skilled and experienced in their respective trades or occupations. The Project Manager may require the Contractor to remove (or cause to be removed) any person employed on the Site or Works, including the Contractor’s Representative if applicable, who: - persists in any misconduct or lack of care, - carries out duties incompetently or negligently, - fails to conform with any provisions of the Contract, or - persists in any conduct which is prejudicial to safety, health, or the protection of the environment. If appropriate, the Contractor shall then appoint (or cause to be appointed) a suitable replacement person. |
| 6.9 Records of Contractor’s Personnel and Equipment | The Contractor shall submit, to the Project Manager, details showing the number of each class of Contractor’s Personnel and of each type of Contractor’s Equipment on the Site. Details shall be submitted each calendar month, in a form approved by the Project Manager, until the Contractor has completed all work which is known to be outstanding at the completion date stated in the Taking-Over Certificate for the Works. |
| 6.10 Disorderly Conduct | The Contractor shall at all times take all reasonable precautions to prevent any unlawful, riotous or disorderly conduct by or amongst the Contractor’s Personnel, and to preserve peace and protection of persons and property on and near the Site. |
| 6.11 Foreign Personnel | The Contractor may bring in to the country any foreign personnel who are necessary for the execution of the Works to the extent allowed by the applicable Laws. The Contractor shall ensure that these personnel are provided with the required residence visas and work permits. The Employer will, if requested by the Contractor, use his best endeavours in a timely and expeditious manner to assist the Contractor in obtaining any local, state, national, or government permission required for bringing in the Contractor’s personnel. The Contractor shall be responsible for the return of these personnel to the place where they were recruited or to their domicile. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. |
| 6.12 Funeral Arrangements | The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of his local employees who may die while engaged upon the Works. |
| 6.13 Prohibition of Forced or Compulsory Labour | The contractor shall not employ "forced or compulsory labour" in any form. "Forced or compulsory labour" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. |
| 6.14 Prohibition of Harmful Child Labour | The Contractor shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. |
| 6.15 Employment Records of Workers | The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked and wages paid to all workers. These records shall be summarized on a monthly basis and submitted to the Project Manager, and these records shall be available for inspection by Auditors during normal working hours. These records shall be included in the details to be submitted by the Contractor under GCC 6.10 [Records of Contractor’s Personnel and Equipment]. |
| - Plant, Materials and Workmanship |  |
| 7.1 Manner of Execution | The Contractor shall carry out the manufacture of Plant, the production and manufacture of Materials, and all other execution of the Works: - in the manner (if any) specified in the Contract, - in a proper workmanlike and careful manner, in accordance with recognised good practice, and - with properly equipped facilities and non-hazardous Materials, except as otherwise specified in the Contract. |
| 7.2 Samples | The Contractor shall submit the following samples of Materials, and relevant information, to the Project Manager for consent prior to using the Materials in or for the Works: - manufacturer’s standard samples of Materials and samples specified in the Contract, all at the Contractor’s cost, and - additional samples instructed by the Project Manager as a Variation. Each sample shall be labelled as to origin and intended use in the Works. |
| 7.3 Inspection | The Authorized Employer’s Personnel shall at all reasonable times: - have full access to all parts of the Site and to all places from which natural Materials are being obtained, and - during production, manufacture and construction (at the Site and elsewhere), be entitled to examine, inspect, measure and test the materials and workmanship, and to check the progress of manufacture of Plant and production and manufacture of Materials. The Contractor shall give the Employer’s Personnel full opportunity to carry out these activities, including providing access, facilities, permissions and safety equipment. No such activity shall relieve the Contractor from any obligation or responsibility. The Contractor shall give notice to the Project Manager whenever any work is ready and before it is covered up, put out of sight, or packaged for storage or transport. The Project Manager shall then either carry out the examination, inspection, measurement or testing without unreasonable delay, or promptly give notice to the Contractor that the Project Manager does not require to do so. If the Contractor fails to give the notice, he shall, if and when required by the Project Manager, uncover the work and thereafter reinstate and make good, all at the Contractor’s cost. |
| 7.4 Testing | This GCC shall apply to all tests specified in the Contract, other than the Tests after Completion (if any). Except as otherwise specified in the Contract, the Contractor shall provide all apparatus, assistance, documents and other information, electricity, equipment, fuel, consumables, instruments, labour, materials, and suitably qualified and experienced staff, as are necessary to carry out the specified tests efficiently. The Contractor shall agree, with the Project Manager, the time and place for the specified testing of any Plant, Materials and other parts of the Works. The Project Manager may, under GCC 13 [Variations and Adjustments], vary the location or details of specified tests, or instruct the Contractor to carry out additional tests. If these varied or additional tests show that the tested Plant, Materials or workmanship is not in accordance with the Contract, the cost of carrying out this Variation shall be borne by the Contractor, notwithstanding other provisions of the Contract. The Project Manager shall give the Contractor not less than 24 hours’ notice of the Project Manager’s intention to attend the tests. If the Project Manager does not attend at the time and place agreed, the Contractor may proceed with the tests, unless otherwise instructed by the Project Manager, and the tests shall then be deemed to have been made in the Project Manager’s presence. If the Contractor suffers delay and/or incurs Cost from complying with these instructions or as a result of a delay for which the Employer is responsible, the Contractor shall give notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion]. After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. The Contractor shall promptly forward to the Project Manager duly certified reports of the tests. When the specified tests have been passed, the Project Manager shall endorse the Contractor’s test certificate, or issue a certificate to him, to that effect. If the Project Manager has not attended the tests, he shall be deemed to have accepted the readings as accurate. |
| 7.5 Rejection | If, as a result of an examination, inspection, measurement or testing, any Plant, Materials or workmanship is found to be defective or otherwise not in accordance with the Contract, the Project Manager may reject the Plant, Materials or workmanship by giving notice to the Contractor, with reasons. The Contractor shall then promptly make good the defect and ensure that the rejected item complies with the Contract. If the Project Manager requires this Plant, Materials or workmanship to be retested, the tests shall be repeated under the same terms and conditions. If the rejection and retesting cause the Employer to incur additional costs, the Contractor shall subject to GCC 2.5 [Employer’s Claims] pay these costs to the Employer. |
| 7.6 Remedial Work | Notwithstanding any previous test or certification, the Project Manager may instruct the Contractor to: - remove from the Site and replace any Plant or Materials which is not in accordance with the Contract, - remove and re-execute any other work which is not in accordance with the Contract, and - execute any work which is urgently required for the safety of the Works, whether because of an accident, unforeseeable event or otherwise. The Contractor shall comply with the instruction within a reasonable time, which shall be the time (if any) specified in the instruction, or immediately if urgency is specified under sub-paragraph (c). If the Contractor fails to comply with the instruction, the Employer shall be entitled to employ and pay other persons to carry out the work. Except to the extent that the Contractor would have been entitled to payment for the work, the Contractor shall subject to GCC 2.5 [Employer’s Claims] pay to the Employer all costs arising from this failure. |
| 7.7 Ownership of Plant and Materials | Except otherwise specified in the Contract, each item of Plant and Materials shall, to the extent consistent with the Laws of the Country, become the property of the Employer at whichever is the earlier of the following times, free from liens and other encumbrances: - when it is incorporated in the Works; - when the Contractor is paid the corresponding value of the Plant and Materials under GCC 8.10 [Payment for Plant and Materials in Event of Suspension]. |
| 7.8 Royalties | Unless otherwise stated in the Employer’s Requirements, the Contractor shall pay all royalties, rents and other payments for: - natural Materials obtained from outside the Site, and - the disposal of material from demolitions and excavations and of other surplus material (whether natural or man-made), except to the extent that disposal areas within the Site are specified in the Contract. |
| - Commencement, Delays and Suspension |  |
| ### 8.1 Commencement of Works | Except otherwise specified in the SCC, the Commencement Date shall be the date at which the following precedent conditions have all been fulfilled and the Project Manager’s instruction recording the agreement of both Parties on such fulfilment and instructing to commence the Works is received by the Contractor: - Signing of the Contract by both Parties, and if required, approval of the Contract by relevant authorities in the Country; and - except if otherwise specified in the SCC, possession of the Site given to the Contractor together with such permission(s) under (a) of GCC 1.13 [Compliance with Laws] as required for the commencement of the Works Where the above conditions have been met and the Project Manager’s instruction is received by the Contractor, the Contractor shall commence the execution of the Works as soon as is reasonably practicable after the Commencement Date, and shall then proceed with the Works with due expedition and without delay. Where the conditions (a) and (b) above have been met and the Project Manager’s instruction is not received by the Contractor within 180 days from the date of signing the Contract without any justifiable reasons, the Contractor may terminate the Contract under GCC 16.2 [Termination by Contractor]. |
| ### 8.2 Time for Completion | The Contractor shall complete the whole of the Works, and each Section (if any), within the Time for Completion for the Works or Section (as the case may be), including: (a) achieving the passing of the Tests on Completion, and (b) completing all work which is stated in the Contract as being required for the Works or Section to be considered to be completed for the purposes of taking-over under GCC 10.1 [Taking Over of the works and sections] |
| ### 8.3 Programme | The Contractor shall submit a detailed time programme to the Project Manager within 14 working days after receiving the notice under GCC 8.1 [Commencement of Works]. The Contractor shall also submit a revised programme whenever the previous programme is inconsistent with actual progress or with the Contractor’s obligations. Each programme shall include: (a) the order in which the Contractor intends to carry out the Works, including the anticipated timing of each stage of design, Contractor's Documents, procurement, manufacture, inspection, delivery to Site, construction, erection, testing, commissioning and trial operation, (b) the periods for reviews under GCC 5.2 [Contractor's Documents] and for any other submissions, approvals and consents specified in the Employer's Requirements, (c) the sequence and timing of inspections and tests specified in the Contract, and (d) a supporting report which includes: (i) a general description of the methods which the Contractor intends to adopt, and of the major stages, in the execution of the Works, and (ii) details showing the Contractor’s reasonable estimate of the number of each class of Contractor's Personnel and of each type of Contractor's Equipment, required on the Site for each major stage. Unless the Project Manager, within 14 working days after receiving a programme, gives notice to the Contractor stating the extent to which it does not comply with the Contract, the Contractor shall proceed in accordance with the programme, subject to his other obligations under the Contract. The Employer's Personnel shall be entitled to rely upon the programme when planning their activities. The Contractor shall promptly give notice to the Project Manager of specific probable future events or circumstances which may adversely affect the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to submit an estimate of the anticipated effect of the future event or circumstances, and/or a proposal under GCC 13.3 [Variation Procedure]. If, at any time, the Project Manager gives notice to the Contractor that a programme fails (to the extent stated) to comply with the Contract or to be consistent with actual progress and the Contractor’s stated intentions, the Contractor shall submit a revised programme to the Project Manager in accordance with this GCC. |
| 8.4 Extension of Time for Completion | The Employer may extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work. The Contractor shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of the Time for Completion if and to the extent that completion for the purposes of GCC 10.1 [Taking Over of the Works and Section s] is or will be delayed by any of the following causes: (a) a Variation (unless an adjustment to the Time for Completion has been agreed under GCC 13.3 [ Variation Procedure]), (b) a cause of delay giving an entitlement to extension of time under a GCC of these Conditions, (c) exceptionally adverse climatic conditions, (d) Unforeseeable shortages in the availability of personnel or Goods caused by epidemic or governmental actions, or (e) any delay, impediment or prevention caused by or attributable to the Employer, the Employer’s Personnel, or the Employer’s other contractors on the Site. If the Contractor considers himself to be entitled to an extension of the Time for Completion, the Contractor shall give notice to the Project Manager in accordance with GCC 20.1 [Contractor’s Claims]. When determining each extension of time under GCC 20.1, the Employer shall review previous determinations and may increase, but shall not decrease, the total extension of time. The Employer shall, within twenty one (21) days of receipt of application for extension of the Intended Completion Date by the Contractor, decide whether or not to grant the extension. The application by the Contractor shall be granted only when supported by full information of a compensation event(s) or variation. In the event the Contractor has not issued an early warning notice of a delay or has failed to cooperate in dealing with a delay, such a delay or failure may be a ground for not granting the extension of the Intended Completion Date. |
| ### 8.5 Rate of Progress | If, at any time: (a) actual progress is too slow to complete within the Time for Completion, and/or (b) progress has fallen (or will fall) behind the current programme under GCC 8.3 [Programme], other than as a result of a cause listed in GCC 8.4 [Extension of Time for Completion], then the Project Manager may, upon written approval of the Employer, instruct the Contractor to submit, under GCC 8.3 [Programme], a revised programme and supporting report describing the revised methods which the Contractor proposes to adopt in order to expedite progress and complete within the Time for Completion. Unless the Project Manager notifies otherwise, the Contractor shall adopt these revised methods, which may require increases in the working hours and/or in the numbers of Contractor’s Personnel and/or Goods, at the risk and cost of the Contractor. If these revised methods cause the Employer to incur additional costs, the Contractor shall subject to GCC 2.5 [Employer’s Claims] pay these costs to the Employer, in addition to delay damages (if any) under GCC 8.7 below |
| ### 8.6 Liquidated Damages | The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the maximum amount of performance security stated in the SCC. The Employer may deduct liquidated damages from payments due to the Contractor. Where the Project Manager, after assessment of work progress, upon satisfaction that the Contractor will not complete the works within the contract period, may issue a notice to the Contractor requiring the payment of liquidated damages pursuant to GCC 51.1 If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC 45.1 |
| ### 8.7 Suspension of Work | The Project Manager may at any time instruct the Contractor to suspend progress of part or all of the Works. During such suspension, the Contractor shall protect, store and secure such part or the Works against any deterioration, loss or damage. The Project Manager may also notify the cause for the suspension. If and to the extent that the cause is notified and is the responsibility of the Contractor, the following GCCs 8.8, 8.9 and 8.10 shall not apply. |
| ### 8.8 Consequences of Suspension | If the Contractor suffers delay and/or incurs Cost from complying with the Project Manager’s instructions under GCC 8.7 [Suspension of Work] and/or from resuming the work, the Contractor shall give notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion ], and After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. The Contractor shall not be entitled to an extension of time for, or to payment of the Cost incurred in, making good the consequences of the Contractor’s faulty design, workmanship or materials, or of the Contractor’s failure to protect, store or secure in accordance with GCC 8.7 [Suspension of Work]. |
| ### 8.9 Payment for Plant and Materials in Event of Suspension | The Contractor shall be entitled to payment of the value (as at the date of suspension) of Plant and/or Materials which have not been delivered to Site if: (a) the work on Plant or delivery of Plant and/or Materials has been suspended for more than 28 days, and (b) the Contractor has marked the Plant and/or Materials as the Employer’s property in accordance with the Project Manager’s instructions. |
| ### 8.10 Prolonged Suspension | If the suspension under GCC 8.7 [Suspension of Work] has continued for more than 84 days, the Contractor may request the Project Manager’s permission to proceed. If the Project Manager does not give permission within 28 days after being requested to do so, the Contractor may, by giving notice to the Project Manager, treat the suspension as an omission under GCC 13 [Variations and Adjustments] of the affected part of the Works. If the suspension affects the whole of the Works, the Contractor may give notice of termination under GCC 16.2 [Termination by Contractor]. |
| ### 8.11 Resumption of Work | After the permission or instruction to proceed is given, the Contractor and the Project Manager shall jointly examine the Works and the Plant and Materials affected by the suspension. The Contractor shall make good any deterioration or defect in or loss of the Works or Plant or Materials, which has occurred during the suspension. |
| - Tests on Completion |  |
| 9.1 Contractor’s Obligations | The Contractor shall carry out the Tests on Completion in accordance with this Clause and GCC 7.4 [Testing], after providing the documents in accordance with sub-paragraph (d) of GCC 4.1 [Contractor’s General Obligations]. The Contractor shall give to the Project Manager not less than 21 days notice of the date after which the Contractor will be ready to carry out each of the Tests on Completion. Unless otherwise agreed, Tests on Completion shall be carried out within 14 working days after this date, on such day or days as the Project Manager may instruct. Unless otherwise stated in the SCC, the Tests on Completion shall be carried out in the following sequence: (a) pre-commissioning tests, which shall include the appropriate inspections and ("dry" or "cold") functional tests to demonstrate that each item of Plant can safely undertake the next stage; (b) commissioning tests, which shall include the specified operational tests to demonstrate that the Works or Section can be operated safely and as specified, under all available operating conditions; and (c) trial operation, which shall demonstrate that the Works or Section perform reliably and in accordance with the Contract. During trial operation, when the Works are operating under stable conditions, the Contractor shall give notice to the Project Manager that the Works are ready for any other Tests on Completion, including performance tests to demonstrate whether the Works conform with criteria specified in the Employer's Requirements and with the Schedule of Guarantees. Trial operation shall not constitute a taking-over under GCC 10 [Employer’s Taking Over]. Any product produced by the Works during trial operation shall be the property of the Employer. In considering the results of the Tests on Completion, the Project Manager shall make allowances for the effect of any use of the Works by the Employer on the performance or other characteristics of the Works. As soon as the Works, or a Section, have passed any Tests on Completion, the Contractor shall submit a certified report of the results of these Tests to the Project Manager. |
| 9.2 Delayed Tests | If the Tests on Completion are being unduly delayed by the Employer, GCC 7.4 [Testing] (fifth paragraph) and/or GCC 10.3 [Interference with Tests on Completion] shall be applicable. If the Tests on Completion are being unduly delayed by the Contractor, the Project Manager may by notice require the Contractor to carry out the Tests within 21 days after receiving the notice. The Contractor shall carry out the Tests on such day or days within that period as the Contractor may fix and of which he shall give notice to the Project Manager. If the Contractor fails to carry out the Tests on Completion within the period of 21 days, the Employer’s Personnel may proceed with the Tests at the risk and cost of the Contractor. The Tests on Completion shall then be deemed to have been carried out in the presence of the Contractor and the results of the Tests shall be accepted as accurate. |
| 9.3 Retesting | If the Works, or a Section, fail to pass the Tests on Completion, GCC 7.5 [Rejection] shall apply, and the Project Manager or the Contractor may require the failed Tests, and Tests on Completion on any related work, to be repeated under the same terms and conditions. |
| 9.4 Failure to Pass Tests on Completion | If the Works, or a Section, fail to pass the Tests on Completion repeated under GCC 9.3 [Retesting], the Project Manager may: - order further repetition of Tests on Completion under GCC 9.3; - if the failure deprives the Employer of substantially the whole benefit of the Works or Section, reject the Works or Section (as the case may be), in which event the Employer shall have the same remedies as are provided in sub-paragraph (c) of GCC 11.4 [Failure to Remedy Defects]; or - issue a Taking-Over Certificate, if the Employer so requests. In the event of sub-paragraph (c), the Contractor shall proceed in accordance with all other obligations under the Contract, and the Contract Price shall be reduced by such amount as shall be appropriate to cover the reduced value to the Employer as a result of this failure. Unless the relevant reduction for this failure is stated (or its method of calculation is defined) in the Contract, the Employer may require the reduction to be: - agreed by both Parties (in full satisfaction of this failure only) and paid before this Taking-Over Certificate is issued, or (ii) determined and paid under GCC 2.5 [Employer’s Claims] and GCC 3.5 [Determinations]. |
| - Employer’s Taking Over |  |
| 10.1 Taking Over of the Works and Sections | Except as stated in GCC 9.4 [Failure to Pass Tests on Completion], the Works shall be taken over by the Employer when (i) the Works have been completed in accordance with the Contract, including the matters described in GCC 8.2 [Time for Completion] and except as allowed in sub-paragraph (a) below, and (ii) a Taking-Over Certificate for the Works has been issued, or is deemed to have been issued in accordance with this GCC. The Contractor may apply by notice to the Project Manager for a Taking-Over Certificate not earlier than 14 working days before the Works will, in the Contractor’s opinion, be complete and ready for taking over. If the Works are divided into Sections, the Contractor may similarly apply for a Taking-Over Certificate for each Section. The Project Manager shall, within 28 days after receiving the Contractor’s application: - issue the Taking-Over Certificate to the Contractor, stating the date on which the Works or Section were completed in accordance with the Contract, except for any minor outstanding work and defects which will not substantially affect the use of the Works or Section for their intended purpose (either until or whilst this work is completed and these defects are remedied); or - reject the application, giving reasons and specifying the work required to be done by the Contractor to enable the Taking-Over Certificate to be issued. The Contractor shall then complete this work before issuing a further notice under this GCC. If the Project Manager fails either to issue the Taking-Over Certificate or to reject the Contractor’s application within the period of 28 days, and if the Works or Section (as the case may be) are substantially in accordance with the Contract, the Taking-Over Certificate shall be deemed to have been issued on the last day of that period. |
| 10.2 Taking Over of Parts of the Works | The Project Manager may, at the sole discretion and written approval of the Employer, issue a Taking-Over Certificate for any part of the Permanent Works. The Employer shall not use any part of the Works (other than as a temporary measure which is either specified in the Contract or agreed by both Parties) unless and until the Project Manager has issued a Taking-Over Certificate for this part. However, unless otherwise agreed by the Parties, if the Employer does use any part of the Works before the Taking-Over Certificate is issued: - the part which is used shall be deemed to have been taken over as from the date on which it is used, - the Contractor shall cease to be liable for the care of such part as from this date, when responsibility shall pass to the Employer, and - if requested by the Contractor, the Project Manager shall issue a Taking-Over Certificate for this part. After the Project Manager has issued a Taking-Over Certificate for a part of the Works, the Contractor shall be given the earliest opportunity to take such steps as may be necessary to carry out any outstanding Tests on Completion. The Contractor shall carry out these Tests on Completion as soon as practicable before the expiry date of the relevant Defects Liability Period. If the Contractor incurs cost as a result of the Employer taking over and/or using a part of the Works, other than such use as is specified in the Contract or agreed by the Contractor, the Contractor shall - give notice to the Project Manager and - be entitled subject to GCC 20.1 [Contractor’s Claims] to payment of any such Cost plus profit, which shall be included in the Contract Price. After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine the matter. If a Taking-Over Certificate has been issued for a part of the Works (other than a Section), the Liquidated damages thereafter for completion of the remainder of the Works shall be reduced. Similarly, the Liquidated damages for the remainder of the Section (if any) in which this part is included shall also be reduced. |
|  | For any period of delay after the date stated in this Taking-Over Certificate, the proportional reduction in these delay damages shall be calculated as the proportion which the value of the part so certified bears to the value of the Works or Section (as the case may be) as a whole. The Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to agree or determine these proportions. The provisions of this paragraph shall only apply to the daily rate of Liquidated damages under GCC 8.7[Liquidated Damages], and shall not affect the maximum amount of these damages. |
| 10.3 Delay of Tests on Completion | If the Contractor is prevented, for more than 14 days, from carrying out the Tests on Completion by a cause for which the Employer is responsible and the suffers a delay, the Contractor shall give notice to the Project Manager and may be entitled subject to GCC 20.1 [Contractor’s Claims], to an extension of time and any associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion], and After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| ### 10.4 Surfaces Requiring Reinstatement | Except as otherwise stated in a Taking-Over Certificate, a certificate for a Section or part of the Works shall not be deemed to certify completion of any ground or other surfaces requiring reinstatement. |
| - Defects Liability |  |
| 11.1 Completion of Outstanding Work and Remedying Defects | In order that the Works and Contractor’s Documents, and each Section, shall be in the condition required by the Contract (fair wear and tear excepted) by the expiry date of the relevant Defects Liability Period or as soon as practicable thereafter, the Contractor shall: - complete any work which is outstanding on the date stated in a Taking-Over Certificate, within such reasonable time as is instructed by the Project Manager, and - execute all work required to remedy defects or damage, as may be notified by (or on behalf of) the Employer on or before the expiry date of the Defects Liability Period for the Works or Section (as the case may be). If a defect appears or damage occurs, the Contractor shall be notified accordingly, by (or on behalf of) the Employer. |
| 11.2 Cost of Remedying Defects | All work referred to in sub-paragraph (b) of GCC 11.1 [Completion of Outstanding Work and Remedying Defects] shall be executed at the risk and cost of the Contractor, if and to the extent that the work is attributable to: - any design for which the Contractor is responsible, - Plant, Materials or workmanship not being in accordance with the Contract, or - failure by the Contractor to comply with any other obligation. If and to the extent that such work is attributable to any other cause, the Contractor shall be notified promptly by (or on behalf of) the Employer and GCC 13.3 [Variation Procedure] shall apply. |
| 11.3 Extension of Defects Liability Period | The Employer shall be entitled subject to GCC 2.5 [Employer’s Claims] to an extension of the Defects Liability Period for the Works or a Section if and to the extent that the Works, Section or a major item of Plant (as the case may be, and after taking over) cannot be used for the purposes for which they are intended by reason of a defect or by reason of a damage attributable to the Contractor. However, that extension shall not exceed two years. If delivery and/or erection of Plant and/or Materials was suspended under GCC 8.8 [Suspension of Work] or GCC 16.1 [Contractor’s Entitlement to Suspend Work], the Contractor’s obligations under this Clause shall not apply to any defects or damage occurring more than two years after the Defects Liability Period for the Plant and/or Materials would otherwise have expired. |
| 11.4 Failure to Remedy Defects | If the Contractor fails to remedy any defect or damage within a reasonable time, a date may be fixed by (or on behalf of) the Employer, on or by which the defect or damage is to be remedied. The Contractor shall be given reasonable notice of this date. If the Contractor fails to remedy the defect or damage by this notified date and this remedial work was to be executed at the cost of the Contractor under GCC 11.2 [Cost of Remedying Defects], the Employer may (at his option): - carry out the work himself or by others, in a reasonable manner and at the Contractor’s cost, but the Contractor shall have no responsibility for this work; and the Contractor shall subject to GCC 2.5 [Employer’s Claims] pay to the Employer the costs reasonably incurred by the Employer in remedying the defect or damage; - require the Project Manager to determine a reasonable reduction in the Contract Price in accordance with GCC 3.5 [Determinations]; or - if the defect or damage deprives the Employer of substantially the whole benefit of the Works or any major part of the Works, terminate the Contract as a whole, or in respect of such major part which cannot be put to the intended use. Without prejudice to any other rights, under the Contract or otherwise, the Employer shall then be entitled to recover all sums paid for the Works or for such part (as the case may be), plus financing costs and the cost of dismantling the same, clearing the Site and returning Plant and Materials to the Contractor. |
| 11.5 Removal of Defective Work | If the defect or damage cannot be remedied expeditiously on the Site and the Employer gives written consent, the Contractor may remove from the Site for the purposes of repair such items of Plant as are defective or damaged. This consent may require the Contractor to increase the amount of the Performance Security by the full replacement cost of these items, or to provide other appropriate security. |
| 11.6 Further Tests | If the work of remedying of any defect or damage may affect the performance of the Works, the Project Manager may require the repetition of any of the tests described in the Contract. The requirement shall be made by notice within 14 working days after the defect or damage is remedied. These tests shall be carried out in accordance with the terms applicable to the previous tests, except that they shall be carried out at the risk and cost of the Party liable, under GCC 11.2 [Cost of Remedying Defects], for the cost of the remedial work. |
| 11.7 Right of Access | Until the Performance Certificate has been issued, the Contractor shall have the right of access to all parts of the Works and to records of the operation and performance of the Works, except as may be inconsistent with the Employer’s security restrictions. |
| 11.8 Contractor to Search | The Contractor shall, if required by the Project Manager, search for the cause of any defect, under the direction of the Project Manager. Unless the defect is to be remedied at the cost of the Contractor under GCC 11.2 [Cost of Remedying Defects], the Cost of the search plus profit shall be agreed or determined by the Project Manager in accordance with GCC 3.5 [Determinations] and shall be included in the Contract Price. |
| 11.9 Performance Certificate | Performance of the Contractor’s obligations shall not be considered to have been completed until the Project Manager has issued the Performance Certificate to the Contractor, stating the date on which the Contractor completed his obligations under the Contract. The Project Manager shall issue the Performance Certificate within 28 days after the latest of the expiry dates of the Defects Liability Periods, or as soon thereafter as the Contractor has supplied all the Contractor’s Documents and completed and tested all the Works, including remedying any defects. A copy of the Performance Certificate shall be issued to the Employer. Only the Performance Certificate shall be deemed to constitute acceptance of the Works. |
| 11.10 Unfulfilled Obligations | After the Performance Certificate has been issued, each Party shall remain liable for the fulfilment of any obligation which remains unperformed at that time. For the purposes of determining the nature and extent of unperformed obligations, the Contract shall be deemed to remain in force. |
| 11.11 Clearance of Site | Upon receiving the Performance Certificate, the Contractor shall remove any remaining Contractor’s Equipment, surplus material, wreckage, rubbish and Temporary Works from the Site. If all these items have not been removed within 28 days after receipt by the Contractor of the Performance Certificate, the Employer may sell or otherwise dispose of any remaining items. The Employer shall be entitled to be paid the costs incurred in connection with, or attributable to, such sale or disposal and restoring the Site. Any balance of the moneys from the sale shall be paid to the Contractor. If these moneys are less than the Employer’s costs, the Contractor shall pay the outstanding balance to the Employer. |
| - Tests after Completion |  |
| 12.1 Procedure for Tests after Completion | If Tests after Completion are specified in the SCC, this Clause shall apply. Unless otherwise stated in the SCC, the Employer shall: (a) provide all electricity, equipment, fuel, instruments, labour, materials, and suitably qualified and experienced staff, as are necessary to carry out the Tests after Completion efficiently, and (b) carry out the Tests after Completion in accordance with the manuals supplied by the Contractor under GCC 5.7 [Operation and Maintenance Manuals] and such guidance as the Contractor may be required to give during the course of these Tests; and in the presence of such Contractor's Personnel as either Party may reasonably request. The Tests after Completion shall be carried out as soon as is reasonably practicable after the Works or Section have been taken over by the Employer. The Employer shall give to the Contractor 21 days’ notice of the date after which the Tests after Completion will be carried out. Unless otherwise agreed, these Tests shall be carried out within 14 working days after this date, on the day or days determined by the Employer. If the Contractor does not attend at the time and place agreed, the Employer may proceed with the Tests after Completion, which shall be deemed to have been made in the Contractor’s presence, and the Contractor shall accept the readings as accurate. The results of the Tests after Completion shall be compiled and evaluated by both Parties. Appropriate account shall be taken of the effect of the Employer’s prior use of the Works. |
| 12.2 Delayed Test | If the Contractor incurs Cost as a result of any unreasonable delay by the Employer to the Tests after Completion, the Contractor shall - give notice to the Project Manager; and - be entitled subject to GCC 20.1 [Contractor’s Claims] to payment of any such Cost plus reasonable profit, which shall be included in the Contract Price. After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine this Cost and profit. If, for reasons not attributable to the Contractor, a Tests after Completion on the Works or any Section cannot be completed during the Defects Liability Period (or any other period agreed upon by both Parties), then the Parties to agree on the final date of completing the test. |
| 12.3 Retesting | If the Works, or a Section, fail to pass the Tests after Completion: (a) sub-paragraph (b) of GCC 11.1 [Completion of Outstanding Work and Remedying Defects] shall apply; and (b) either Party may then require the failed Tests, and the Tests after Completion on any related work, to be repeated under the same terms and conditions. If and to the extent that this failure and retesting are attributable to any of the matters listed in sub-paragraphs (a) to (d) of GCC 11.2 [Cost of Remedying Defects] and cause the Employer to incur additional costs, the Contractor shall subject to GCC 2.5 [Employer’s Claims] pay these costs to the Employer. |
| 12.4 Failure to Pass Tests after Completion | If the following conditions apply, namely: (a) the Works, or a Section, fail to pass any or all of the Tests after Completion, (b) the relevant sum payable as non-performance damages for this failure is stated (or its method of calculation is defined) in the Contract, and (c) the Contractor pays this relevant sum to the Employer during the Defects Liability Period, then the Works or Section shall be deemed to have passed these Tests after Completion. If the Works, or a Section, fail to pass a Test after Completion and the Contractor proposes to make adjustments or modifications to the Works or such Section, the Contractor may be instructed by (or on behalf of) the Employer that right of access to the Works or Section cannot be given until a time that is convenient to the Employer. The Contractor shall then remain liable to carry out the adjustments or modifications and to satisfy this Test, within a reasonable period of receiving notice by (or on behalf of) the Employer of the time that is convenient to the Employer. However, if the Contractor does not receive this notice during the relevant Defects Liability Period, the Contractor shall be relieved of this obligation. If the Contractor incurs additional Cost as a result of any unreasonable delay by the Employer in permitting access to the Works or Plant by the Contractor, either to investigate the causes of a failure to pass a Tests after Completion or to carry out any adjustments or modifications, the Contractor may: - give notice to the Project Manager; and - be entitled subject to GCC 20.1 [Contractor’s Claims] to payment of any such Cost plus reasonable profit, which shall be included in the Contract Price. After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine the matter. |
| - Variations and Adjustments |  |
| 13.1 Right to Vary | Variations may be initiated by the Project Manager at any time prior to issuing the Taking-Over Certificate for the Works, either by an instruction or by a request for the Contractor to submit a proposal. The Contractor shall execute and be bound by each Variation, unless the Contractor promptly gives notice to the Project Manager stating (with supporting particulars) that (i) the Contractor cannot readily obtain the Goods required for the Variation, or (ii) such Variation triggers a substantial change in the sequence or progress of the Works. Upon receiving this notice, the Project Manager shall cancel, confirm or vary the instruction. Variation may be in the form of: (a) changes to the quantities of any item of work included in the Contract; - changes to the quality and other characteristics of any item of work; - changes to the levels, positions and/or dimensions of any part of the Works; - omission of any Work unless it is to be carried out by others; - any additional Work, Plant, Materials or services necessary for the Permanent Works, including any associated Tests on Completion, boreholes and other testing and exploratory work; or - changes to the sequence or timing of the execution of the Works. The Contractor shall not make any alteration and/or modification of the Permanent Works, unless and until the Project Manager, with prior written approval of the Employer, instructs a Variation. |
| 13.2 Value Engineering | The Contractor may, at any time, submit to the Project Manager a written proposal which (in the Contractor’s opinion) will, if adopted, (i) accelerate completion, (ii) reduce the cost to the Employer of executing, maintaining or operating the Works, (iii) improve the efficiency or value to the Employer of the completed Works, or (iv) otherwise be of benefit to the Employer. The proposal shall be prepared at the cost of the Contractor and shall include the items listed in GCC 13.3 [Variation Procedure]. If a proposal, which is approved by the Project Manager, includes a change in the design of part of the Permanent Works, then unless otherwise agreed by both Parties: - the Contractor shall design this part, - sub-paragraphs (a) to (d) of GCC 4.1 [Contractor’s General Obligations] shall apply, and - if this change results in a reduction in the contract value of this part, the Project Manager shall upon Employer’s approval proceed in accordance with GCC 3.5 [Determinations] to determine a fee, which shall be included in the Contract Price. This fee shall be half (50%) of the difference between the following amounts: - such reduction in contract value, resulting from the change, excluding adjustments under GCC 13.7 [Adjustments for Changes in Legislation] and GCC 13.8 [Adjustments for Changes in Cost],and - the reduction (if any) in the value to the Employer of the varied works, taking account of any reductions in quality, anticipated life or operational efficiencies. However, if amount (i) is less than amount (ii), there shall not be a fee. |
| 13.3 Variation Procedure | If the Project Manager requests a proposal, prior to instructing a Variation, the Contractor shall respond in writing as soon as practicable, either by giving reasons why he cannot comply (if this is the case) or by submitting: - a description of the proposed work to be performed and a programme for its execution, - the Contractor’s proposal for any necessary modifications to the programme according to GCC 8.3 [Programme] and to the Time for Completion, and - the Contractor’s proposal for evaluation of the Variation. The Project Manager shall, as soon as practicable after receiving such proposal (under GCC 13.2 [Value Engineering] or otherwise), respond with approval, disapproval or comments. The Contractor shall not delay any work whilst awaiting a response. Each instruction to execute a Variation, with any requirements for the recording of Costs, shall be issued by the Project Manager to the Contractor, who shall acknowledge receipt. Upon instructing or approving a Variation, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to agree or determine adjustments to the Contract Price and the Schedule of Payments. These adjustments shall include reasonable profit, and shall take account of the Contractor’s submissions under GCC 13.2 [Value Engineering] if applicable. |
| 13.4 Payment in Applicable Currencies | If the Contract provides for payment of the Contract Price in more than one currency, then whenever an adjustment is agreed, approved or determined as stated above, the amount payable in each of the applicable currencies shall be specified. For this purpose, reference shall be made to the actual or expected currency proportions of the Cost of the varied work, and to the proportions of various currencies specified for payment of the Contract Price. |
| 13.5 Provisional Sums | Each Provisional Sum shall only be used, in whole or in part, in accordance with the Project Manager’s instructions and the Contract Price shall be adjusted accordingly. The total sum paid to the Contractor shall include only such amounts, for the work, supplies or services to which the Provisional Sum relates, as the Project Manager shall have instructed. For each Provisional Sum, the Project Manager may instruct: - work to be executed (including Plant, Materials or services to be supplied) by the Contractor and valued under GCC 13.3 [Variation Procedure]; and/or - Plant, Materials or services to be purchased by the Contractor, for which there shall be included in the Contract Price: - the actual amounts paid (or due to be paid) by the Contractor, and - a sum for overhead charges and profit, calculated as a percentage of these actual amounts by applying the relevant percentage rate (if any) stated in the appropriate Schedule. If there is no such rate, the percentage rate stated in the Appendix to Bid shall be applied. The Contractor shall, when required by the Project Manager, produce quotations, invoices, vouchers and accounts or receipts in substantiation. |
| 13.6 Daywork | For work of a minor or incidental nature, the Project Manager may instruct that such work be executed on a daywork basis. The work shall then be valued in accordance with the Daywork Schedule included in the Contract, and the following procedure shall apply. If a Daywork Schedule is not included in the Contract, this GCC shall not apply. Before ordering Goods for the work, the Contractor shall submit quotations to the Project Manager. When applying for payment, the Contractor shall submit invoices, vouchers and accounts or receipts for any Goods. Except for any items for which the Daywork Schedule specifies that payment is not due, the Contractor shall deliver each day to the Project Manager accurate statements in duplicate which shall include the following details of the resources used in executing the previous day’s work: - the names, occupations and time of Contractor’s Personnel, - the identification, type and time of Contractor’s Equipment and Temporary Works, and - the quantities and types of Plant and Materials used. One copy of each statement will, if correct, or when agreed, be signed by the Project Manager and returned to the Contractor. The Contractor shall then submit priced statements of these resources to the Project Manager, prior to their inclusion in the next Statement under GCC 14.3 [Application for Interim Payment Certificates]. |
| 13.7 Adjustments for Changes in Legislation | The Contract Price shall be adjusted to take account of any increase or decrease in Cost resulting from a change in the Laws of Tanzania (including the introduction of new Laws and the repeal or modification of existing Laws) or in the judicial or official governmental interpretation of such Laws, made after the Base Date, which affect the Contractor in the performance of obligations under the Contract. If the Contractor suffers (or will suffer) delay and/or incurs (or will incur) additional Cost as a result of these changes in the Laws or in such interpretations, made after the Base Date, the Contractor shall give notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion], and After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. Notwithstanding the foregoing, the Contractor shall not be entitled to such an extension of time if the same shall already have been taken into account in determining an extension and such Cost shall not be separately paid if the same shall already have been taken into account in the indexing of any inputs to the table of adjustment data in accordance with the provisions of GCC 13.8. |
| 13.8 Adjustments for Changes in Cost | In this GCC, “table of adjustment data” means the completed table of adjustment data for local and foreign currencies included in the Schedules. If there is no such table of adjustment data, this GCC shall not apply. If this GCC applies, the amounts payable to the Contractor shall be adjusted for rises or falls in the cost of labour, Goods and other inputs to the Works, by the addition or deduction of the amounts determined by the formulae prescribed in this GCC. To the extent that full compensation for any rise or fall in Costs is not covered by the provisions of this or other Clauses, the Accepted Contract Amount shall be deemed to have included amounts to cover the contingency of other rises and falls in costs. The adjustment to be applied to the amount otherwise payable to the Contractor, as valued in accordance with the appropriate Schedule and certified in Payment Certificates, shall be determined from formulae for each of the currencies in which the Contract Price is payable. No adjustment is to be applied to work valued on the basis of Cost or current prices. The formulae shall be of the following general type: Pn = a + b Ln/ Lo + c En/Eo + d Mn/Mo + ...... where: “Pn” is the adjustment multiplier to be applied to the estimated contract value in the relevant currency of the work carried out in period “n”, this period being a month unless otherwise stated in the SCC ; “a” is a fixed coefficient, stated in the relevant table of adjustment data, representing the non-adjustable portion in contractual payments; “b”, “c”, “d”, … are coefficients representing the estimated proportion of each cost element related to the execution of the Works, as stated in the relevant table of adjustment data; such tabulated cost elements may be indicative of resources such as labour, equipment and materials; “Ln”, “En”, “Mn”, … are the current cost indices or reference prices for period “n”, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the date 49 days prior to the last day of the period (to which the particular Payment Certificate relates); and “Lo”, “Eo”, “Mo”, … are the base cost indices or reference prices, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the Base Date. The cost indices or reference prices stated in the table of adjustment data shall be used. If their source is in doubt, it shall be determined by the Project Manager. For this purpose, reference shall be made to the values of the indices at stated dates (quoted in the fourth and fifth columns respectively of the table) for the purposes of clarification of the source; although these dates (and thus these values) may not correspond to the base cost indices. In cases where the “currency of index” (stated in the table) is not the relevant currency of payment, each index shall be converted into the relevant currency of payment at the selling rate, established by the central bank of the Country, of this relevant currency on the above date for which the index is required to be applicable. Until such time as each current cost index is available, the Project Manager shall determine a provisional index for the issue of Interim Payment Certificates. When a current cost index is available, the adjustment shall be recalculated accordingly. If the Contractor fails to complete the Works within the Time for Completion, adjustment of prices thereafter shall be made using either (i) each index or price applicable on the date 49 days prior to the expiry of the Time for Completion of the Works, or (ii) the current index or price: whichever is more favourable to the Employer. The weightings (coefficients) for each of the factors of cost stated in the table(s) of adjustment data shall only be adjusted if they have been rendered unreasonable, unbalanced or inapplicable, as a result of Variations. |
| - Contract Price and Payment |  |
| 14.1 The Contract Price | Unless otherwise stated in the SCC: - the Contract Price shall be the lumpsum contract amount agreed or determined under GCC 12.3 [Evaluation] and be subject to adjustments in accordance with the Contract; - the Contractor shall pay all taxes, duties and fees required to be paid by him under the Contract, and the Contract Price shall not be adjusted for any of these costs except as stated in GCC 13.7 [Adjustments for Changes in Legislation]; - any quantities which may be set out in the Bill of Quantities or other Schedule are estimated quantities and are not to be taken as the actual and correct quantities: - of the Works which the Contractor is required to execute, or - for the purposes of GCC 12 [Measurement and Evaluation]; and the Contractor shall submit to the Project Manager, within 28 days after the Commencement Date, a proposed breakdown of each lump sum price in the Schedules. The Project Manager may take account of the breakdown when preparing Payment Certificates, but shall not be bound by it. |
| 14.2 Advance Payment | If stated in the SCC the Employer shall make advance payment to the Contractor of the amounts stated in the SCC by the manner stated in the SCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment. The Contractor shall use the advance payment to pay for mobilization and design expenses required specifically for design and execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. Unless and until the Employer receives this guarantee, or if the total advance payment is not stated in the SCC, this GCC shall not apply. The Project Manager shall deliver to the Employer and to the Contractor an Interim Payment Certificate for the advance payment or its first instalment after receiving a Statement (under GCC 14.3 [Application for Interim Payment Certificates]) and after the Employer receives - the Performance Security in accordance with GCC 4.2 [Performance Security]; and - a guarantee in amounts and currencies equal to the advance payment. This guarantee shall be issued by an entity and from within a country (or other jurisdiction) approved by the Employer, and shall be in the form annexed to the SCC or in another form approved by the Employer. The Contractor shall ensure that the guarantee is valid and enforceable until the advance payment has been repaid, but its amount shall be progressively reduced by the amount repaid by the Contractor as indicated in the Payment Certificates. If the terms of the guarantee specify its expiry date, and the advance payment has not been repaid by the date 28 days prior to the expiry date, the Contractor shall extend the validity of the guarantee until the advance payment has been repaid. Unless otherwise stated in the SCC, the advance payment shall be repaid through percentage deductions from the interim payments determined by the Project Manager in accordance with GCC 14.6 [Issue of Interim Payment Certificates], as follows:. - deductions shall commence in the next interim Payment Certificate following that in which the total of all certified interim payments (excluding the advance payment and deductions and repayments of retention) exceeds 30 percent of the Accepted Contract Amount less Provisional Sums; and - deductions shall be made at the amortisation rate stated in the SCC of the amount of each Interim Payment Certificate (excluding the advance payment and deductions for its repayments as well as deductions for retention money) in the currencies and proportions of the advance payment until such time as the advance payment has been repaid; provided that the advance payment shall be completely repaid prior to the time when eighty per cent (80%) of the Accepted Contract Amount less Provisional Sums has been certified for payment. If the advance payment has not been repaid prior to the issue of the Taking-Over Certificate for the Works or prior to termination under GCC 15 [Termination by Employer], GCC 16 [Suspension and Termination by Contractor] or GCC 19 [Force Majeure] (as the case may be), the whole of the balance then outstanding shall immediately become due and in case of termination under GCC 15 [Termination by Employer] and GCC 19.6 [Optional Termination, Payment and Release], payable by the Contractor to the Employer. |
| 14.3 Application for Interim Payment Certificates | The Contractor shall submit a Statement in six copies to the Project Manager after the end of each month, in a form approved by the Project Manager, showing in detail the amounts to which the Contractor considers himself to be entitled, together with supporting documents which shall include the report on the progress during this month in accordance with GCC 4.21 [Progress Reports]. The Statement shall include the following items, as applicable, which shall be expressed in the various currencies in which the Contract Price is payable, in the sequence listed: - the estimated contract value of the Works executed and the Contractor’s Documents produced up to the end of the month (including Variations but excluding items described in sub-paragraphs (b) to (g) below); - any amounts to be added and deducted for changes in legislation and changes in cost, in accordance with GCC 13.7 [Adjustments for Changes in Legislation] and GCC 13.8 [Adjustments for Changes in Cost]; - any amount to be deducted for retention, calculated by applying the percentage of retention stated in the SCC to the total of the above amounts, until the amount so retained by the Employer reaches the limit of Retention Money (if any) stated in the SCC; - any amounts to be added for the advance payment and (if more than one instalment) and to be deducted for its repayments in accordance with GCC 14.2 [Advance Payment]; - any amounts to be added and deducted for Plant and Materials in accordance with GCC 14.5 [Plant and Materials intended for the Works]; - any other additions or deductions which may have become due under the Contract or otherwise, including those under GCC 20 [Claims, Disputes and Arbitration]; and - the deduction of amounts certified in all previous Payment Certificates. |
| 14.4 Schedule of Payments | If the Contract includes a schedule of payments specifying the instalments in which the Contract Price will be paid, then unless otherwise stated in this schedule: - the instalments quoted in this schedule of payments shall be the estimated contract values for the purposes of sub-paragraph (a) of GCC 14.3 [Application for Interim Payment Certificates]; - GCC 14.5 [Plant and Materials intended for the Works] shall not apply; and - if these instalments are not defined by reference to the actual progress achieved in executing the Works, and if actual progress is found to be less or more than that on which this schedule of payments was based, then the Project Manager may proceed in accordance with GCC 3.5 [Determinations] to agree or determine revised instalments, which shall take account of the extent to which progress is less than that on which the instalments were previously based. If the Contract does not include a schedule of payments, the Contractor shall submit non-binding estimates of the payments which he expects to become due during each quarterly period. The first estimate shall be submitted within 42 days after the Commencement Date. Revised estimates shall be submitted at quarterly intervals, until the Taking-Over Certificate has been issued for the Works. |
| 14.5 Plant and Materials intended for the Works | If this GCC applies, Interim Payment Certificates shall include, under sub-paragraph (e) of GCC 14.3, - an amount for Plant and Materials which have been sent to the Site for incorporation in the Permanent Works, and - a reduction when the contract value of such Plant and Materials is included as part of the Permanent Works under sub-paragraph (a) of GCC 14.3 [Application for Interim Payment Certificates]. If the lists referred to in sub-paragraphs (b)(i) or (c)(i) below are not included in the SCC, this GCC shall not apply. The Project Manager shall determine and certify each addition if the following conditions are satisfied: - the Contractor has: - kept satisfactory records (including the orders, receipts, Costs and use of Plant and Materials) which are available for inspection, and - submitted a statement of the Cost of acquiring and delivering the Plant and Materials to the Site, supported by satisfactory evidence; and either: (b) the relevant Plant and Materials: - are those listed in the Schedules for payment when shipped, - have been shipped to the Country, en route to the Site, in accordance with the Contract; and - are described in a clean shipped bill of lading or other evidence of shipment, which has been submitted to the Project Manager together with evidence of payment of freight and insurance, any other documents reasonably required, and a bank guarantee in a form and issued by an entity approved by the Employer in amounts and currencies equal to the amount due under this GCC: this guarantee may be in a similar form to the form referred to in GCC 14.2 [Advance Payment] and shall be valid until the Plant and Materials are properly stored on Site and protected against loss, damage or deterioration; or (c) the relevant Plant and Materials: - are those listed in the Schedules for payment when delivered to the Site, and - have been delivered to and are properly stored on the Site, are protected against loss, damage or deterioration, and appear to be in accordance with the Contract. The additional amount to be certified shall be the equivalent of eighty percent of the Project Manager’s determination of the cost of the Plant and Materials (including delivery to Site), taking account of the documents mentioned in this GCC and of the contract value of the Plant and Materials. The currencies for this additional amount shall be the same as those in which payment will become due when the contract value is included under sub-paragraph (a) of GCC 14.3 [Application for Interim Payment Certificates]. At that time, the Payment Certificate shall include the applicable reduction which shall be equivalent to, and in the same currencies and proportions as, this additional amount for the relevant Plant and Materials. |
| 14.6 Issue of Interim Payment Certificates | No amount will be certified or paid until the Employer has received and approved the Performance Security. Thereafter, the Project Manager shall, within 28 days after receiving a Statement and supporting documents, deliver to the Employer and to the Contractor an Interim Payment Certificate which shall state the amount which the Project Manager fairly determines to be due, with all supporting particulars for any reduction or withholding made by the Project Manager on the Statement. However, prior to issuing the Taking-Over Certificate for the Works, the Project Manager shall not be bound to issue an Interim Payment Certificate in an amount which would (after retention and other deductions) be less than the minimum amount of Interim Payment Certificates (if any) pursuant to GCC 14.2. In this event, the Project Manager shall give notice to the Contractor accordingly. An Interim Payment Certificate shall not be withheld for any other reason, although: - if any thing supplied or work done by the Contractor is not in accordance with the Contract, the cost of rectification or replacement may be withheld until rectification or replacement has been completed; and/or - if the Contractor was or is failing to perform any work or obligation in accordance with the Contract, and had been so notified by the Project Manager, the value of this work or obligation may be withheld until the work or obligation has been performed. The Project Manager may in any Payment Certificate make any correction or modification that should properly be made to any previous Payment Certificate. A Payment Certificate shall not be deemed to indicate the Project Manager’s acceptance, approval, consent or satisfaction. |
| 14.7 Payment and Currency | The Employer shall pay to the Contractor: - the amount certified in each Interim Payment Certificate within 56 days after the Project Manager receives the Statement and supporting documents or, at a time when the funds or credit (from which part of the payments to the Contractor is being made) is suspended, the amount shown on any statement submitted by the Contractor, within 14 days after such statement is submitted. Any discrepancy shall be rectified in the next payment to the Contractor; and - the amount certified in the Final Payment Certificate within 56 days after the Employer receives this Payment Certificate or, at a time when the Government’s fund (from which part of the payments to the Contractor is being made) is suspended, the undisputed amount shown in the Final Statement, within 56 days after the date of notification of the suspension in accordance with GCC 16.2. Payment of the amount due in each currency shall be made into the bank account, nominated by the Contractor, in the payment country (for this currency) specified in the Contract. The currency of payment shall be stated in the SCC. Where payments are to be made in currencies other than the Tanzania Shillings, the exchange rates to be used for calculating such amounts shall be the Bank of Tanzania exchange rate prevailing on the date of 28 days before the date of deadline of submisiion of the bid. |
| 14.8 Delayed Payment | If the Employer makes a late payment the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest issued by the Bank of Tanzania on the date of signing the Contract for each of the currencies in which payments are made. |
| 14.9 Payment of Retention Money | When the Taking-Over Certificate has been issued for the Works, the first half of the Retention Money shall be certified by the Project Manager for payment to the Contractor. If a Taking-Over Certificate is issued for a Section or part of the Works, a proportion of the Retention Money shall be certified and paid. This proportion shall be half (50%) of the proportion calculated by dividing the estimated contract value of the Section or part, by the estimated final Contract Price. Promptly after the latest of the expiry dates of the Defects Liability Periods, the outstanding balance of the Retention Money shall be certified by the Project Manager for payment to the Contractor. If a Taking-Over Certificate was issued for a Section, a proportion of the second half of the Retention Money shall be certified and paid promptly after the expiry date of the Defects Liability Period for the Section. This proportion shall be half (50%) of the proportion calculated by dividing the estimated contract value of the Section by the estimated final Contract Price. However, if any work remains to be executed under GCC 11 [Defects Liability], the Project Manager shall be entitled to withhold certification of the estimated cost of this work until it has been executed. When calculating these proportions, no account shall be taken of any adjustments under GCC 13.7 [Adjustments for Changes in Legislation] and GCC 13.8 [Adjustments for Changes in Cost]. |
| 14.10 Statement at Completion | Within 84 days after receiving the Taking-Over Certificate for the Works, unless otherwise stated in the SCC, the Contractor shall submit to the Project Manager six copies of a Statement at completion with supporting documents, in accordance with GCC 14.3 [Application for Interim Payment Certificates], showing: - the value of all work done in accordance with the Contract up to the date stated in the Taking-Over Certificate for the Works, - any further sums which the Contractor considers to be due, and - an estimate of any other amounts which the Contractor considers will become due to him under the Contract. Estimated amounts shall be shown separately in this Statement at completion. The Project Manager shall then certify in accordance with GCC 14.6 [Issue of Interim Payment Certificates]. |
| 14.11 Application for Final Payment Certificate | Within 56 days after receiving the Performance Certificate, unless otherwise stated in the SCC, the Contractor shall submit to the Project Manager, six copies of a final statement with supporting documents showing in detail in a form approved by the Project Manager: - the value of all work done in accordance with the Contract, and - any further sums which the Contractor considers to be due to him under the Contract or otherwise. If the Project Manager disagrees with or cannot verify any part of the final statement, the Contractor shall submit such further information as the Project Manager may reasonably require within 28 days from receipt of the said draft and shall make such changes in the draft as may be agreed between them. The Contractor shall then prepare and submit to the Project Manager the final statement as agreed. This agreed statement is referred to in these Conditions as the “Final Statement”. However if, following discussions between the Project Manager and the Contractor and any changes to the final statement which are agreed, it becomes evident that a dispute exists, the Project Manager shall deliver to the Employer (with a copy to the Contractor) an Interim Payment Certificate for the agreed parts of the draft final statement. Thereafter, if the dispute is finally resolved under GCC 20.4 [Obtaining Dispute Board’s Decision] or GCC 20.5 [Amicable Settlement], the Contractor shall then prepare and submit to the Employer (with a copy to the Project Manager) a Final Statement. |
| 14.12 Discharge | When submitting the Final Statement, the Contractor shall submit a discharge which confirms that the total of the Final Statement represents full and final settlement of all moneys due to the Contractor under or in connection with the Contract. This discharge may state that it becomes effective when the Contractor has received the Performance Security and the outstanding balance of this total, in which event the discharge shall be effective on such date. |
| 14.13 Issue of Final Payment Certificate | Within 28 days after receiving the Final Statement and a written discharge in accordance with GCC 14.11 [Application for Final Payment Certificate] and GCC 14.12 [Discharge], the Project Manager shall deliver to the Employer and to the Contractor, the Final Payment Certificate which shall state: - the amount which he fairly determines is finally due, and - after giving credit to the Employer for all amounts previously paid by the Employer and for all sums to which the Employer is entitled, the balance (if any) due from the Employer to the Contractor or from the Contractor to the Employer, as the case may be. If the Contractor has not applied for a Final Payment Certificate in accordance with GCC 14.11 [Application for Final Payment Certificate] and GCC 14.12 [Discharge], the Project Manager shall request the Contractor to do so. If the Contractor fails to submit an application within a period of 28 days, the Project Manager shall issue the Final Payment Certificate for such amount based on his determination of final Statement submitted by the Contractor. |
| 14.14 Cessation of Employer’s Liability | The Employer shall not be liable to the Contractor for any matter or thing under or in connection with the Contract or execution of the Works, except to the extent that the Contractor shall have included an amount expressly for it: - in the Final Statement and also - (except for matters or things arising after the issue of the Taking-Over Certificate for the Works) in the Statement at completion described in GCC 14.10 [Statement at Completion]. However, this GCC shall not limit the Employer’s liability under his indemnification obligations, or the Employer’s liability in any case of fraud, deliberate default or reckless misconduct by the Employer. |
| - Termination by Employer |  |
| 15.1 Notice to Correct | If the Contractor fails to carry out any obligation under the Contract, the Project Manager may by notice require the Contractor to make good the failure and to remedy it within a specified reasonable time. |
| 15.2 Termination by Employer | The Employer may terminate the Contract if the Contractor: - fails to comply with GCC 4.2 [Performance Security] or with a notice under GCC 15.1 [Notice to Correct], - abandons the Works or otherwise plainly demonstrates the intention not to continue performance of his obligations under the Contract, - without reasonable excuse fails: (i) to proceed with the Works in accordance with GCC 8 [Commencement, Delays and Suspension], or (ii) to comply with a notice issued under GCC 7.5 [Rejection] or GCC 7.6 [Remedial Work], within 28 days after receiving it, - subcontracts the whole of the Works or assigns the Contract without the required agreement, - becomes bankrupt or insolvent, goes into liquidation, has a receiving or administration order made against him, compounds with his creditors, or carries on business under a receiver, trustee or manager for the benefit of his creditors, or if any act is done or event occurs which (under applicable Laws) has a similar effect to any of these acts or events, or - gives or offers to give (directly or indirectly) to any person any bribe, gift, gratuity, commission or other thing of value, as an inducement or reward: - for doing or forbearing to do any action in relation to the Contract, or - for showing or for bearing to show favour or disfavour to any person in relation to the Contract, or if any of the Contractor’s Personnel, agents or Subcontractors gives or offers to give (directly or indirectly) to any person any such inducement or reward as is described in this sub-paragraph (f). However, lawful inducements and rewards to Contractor’s Personnel shall not entitle termination. In any of these events or circumstances, the Employer may, upon giving 14 working days’ notice to the Contractor, terminate the Contract and expel the Contractor from the Site. However, in the case of sub-paragraph (e) or (f), the Employer may by notice terminate the Contract immediately. The Employer’s choice to terminate the Contract shall not prejudice any other rights of the Employer, under the Contract or otherwise. The Contractor shall then leave the Site and deliver any required Goods, all Contractors’ Documents, and other design documents made by or for him, to the Project Manager. However, the Contractor shall use his best efforts to comply immediately with any reasonable instructions included in the notice - for the assignment of any subcontract, and - for the protection of life or property or for the safety of the Works. After termination, the Employer may complete the Works and/or arrange for any other entities to do so. The Employer and these entities may then use any Goods, Contractor’s Documents and other design documents made by or on behalf of the Contractor. The Employer shall then give notice that the Contractor’s Equipment and Temporary Works will be released to the Contractor at or near the Site. The Contractor shall promptly arrange their removal, at the risk and cost of the Contractor. However, if by this time the Contractor has failed to make a payment due to the Employer, these items may be sold by the Employer in order to recover this payment. Any balance of the proceeds shall then be paid to the Contractor. |
| 15.3 Valuation at Date of Termination | As soon as practicable after a notice of termination under GCC 15.2 [Termination by Employer] has taken effect, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine the value of the Works, Goods and Contractor’s Documents, and any other sums due to the Contractor for work executed in accordance with the Contract. |
| 15.4 Payment after Termination | After a notice of termination under GCC 15.2 [Termination by Employer] has taken effect, the Employer may: - proceed in accordance with GCC 2.5 [Employer’s Claims], - withhold further payments to the Contractor until the costs of execution, completion and remedying of any defects, damages for delay in completion (if any), and all other costs incurred by the Employer, have been established, and/or - recover from the Contractor any losses and damages incurred by the Employer and any extra costs of completing the Works, after allowing for any sum due to the Contractor under GCC 15.3 [Valuation at Date of Termination]. After recovering any such losses, damages and extra costs, the Employer shall pay any balance to the Contractor. |
| 15.5 Employer’s Entitlement to Termination for Convenience | The Employer shall be entitled to terminate the Contract, at any time for the Employer’s convenience, by giving notice of such termination to the Contractor. The termination shall take effect 28 days after the later of the dates on which the Contractor receives this notice or the Employer returns the Performance Security. The Employer shall not terminate the Contract under this GCC in order to execute the Works himself or to arrange for the Works to be executed by another contractor or to avoid a termination of the Contract by the Contractor under GCC 16.4 [Payment on Termination]. After this termination, the Contractor shall proceed in accordance with GCC 16.3 [Cessation of Work and Removal of Contractor’s Equipment] and shall be paid in accordance with GCC 19.6 [Optional Termination, Payment and Release]. |
| 15.6 Corrupt or Fraudulent Practices | If the Contractor is determined by Competent Authority that he has engaged in corrupt, fraudulent, collusive or coercive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of GCC 15 shall apply as if such expulsion had been made under GCC 15.2 [Contractor’s Personnel]. For the purposes of this GCC: (i) “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the procurement process or in contract execution; (ii) “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement process or the execution of a contract; (iii) “collusive practices” means a scheme or arrangement between two or more bidders, with or without the knowledge of the Borrower, designed to establish bid prices at artificial, non-competitive levels; (iv) “coercive practices” means harming or threatening to harm, directly or indirectly, persons, or their property to influence their participation in a procurement process, or affect the execution of a contract. |
| - Suspension and Termination by the Contractor |  |
| 16.1 Contractor’s Entitlement to Suspend Work | If the Project Manager fails to certify in accordance with GCC 14.6 [Issue of Interim Payment Certificates] or the Employer fails to comply with GCC 2.4 [Employer’s Financial Arrangements] or GCC 14.7 [Payment], the Contractor may, after giving not less than 28 days’ notice to the Employer, suspend work (or reduce the rate of work) unless and until the Contractor has received the Payment Certificate, reasonable evidence or payment, as the case may be and as described in the notice. Notwithstanding the above, if the Government has suspended disbursements, which finances in whole or in part the execution of the Works, and no agreement has been reached by the parties pursuant to GCC 2.8, the Contractor may by notice suspend work or reduce the rate of work at any time, but not less than 14 working days after the Employer having received the suspension notification from the Government. The Contractor’s action shall not prejudice his entitlements to interest under GCC 14.8 [Delayed Payment] and to termination under GCC 16.2 [Termination by Contractor]. If the Contractor subsequently receives such Payment Certificate, evidence or payment (as described in the relevant GCC and in the above notice) before giving a notice of termination, the Contractor shall resume normal working as soon as is reasonably practicable. If the Contractor suffers delay and/or incurs Cost as a result of suspending work (or reducing the rate of work) in accordance with this GCC, the Contractor shall give notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion], and After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| 16.2 Termination by Contractor | The Contractor may terminate the Contract if: - the Contractor does not receive the reasonable evidence within 42 days after giving notice under GCC 16.1 [Contractor’s Entitlement to Suspend Work] in respect of a failure to comply with GCC 2.4 [failure to reach agreement upon Government suspension of financing] - the Employer substantially fails to perform his obligations under the Contract in such manner as to materially and adversely affect the execution of the Contract; - the Employer fails to comply with GCC 1.6 [Contract]; - a prolonged suspension affects the whole of the Works as described in GCC 8.11 [Prolonged Suspension], or - the Employer becomes bankrupt or insolvent, goes into liquidation, has a receiving or administration order made against him, compounds with his creditors, or carries on business under a receiver, trustee or manager for the benefit of his creditors, or if any act is done or event occurs which (under applicable Laws) has a similar effect to any of these acts or events. - In the event the Government suspends the funds from which part of the payments to the Contractor are being made and the time agreed for future event pursuant to GCC 2.4 has expired. - the Contractor does not receive the Project Manager’s instruction recording the agreement of both Parties on the fulfilment of the conditions for the Commencement of Works under GCC 8.1 [Commencement of Works]. In any of these events or circumstances, the Contractor may, upon giving 14 working days notice to the Employer, terminate the Contract. However, in the case of sub-paragraph (g), the Contractor may by notice terminate the Contract immediately. The Contractor’s election to terminate the Contract shall not prejudice any other rights of the Contractor, under the Contract or otherwise. |
| 16.3 Cessation of Work and Removal of Contractor’s Equipment | After a notice of termination under GCC 15.5 [Employer’s Entitlement to Termination for Convenience], GCC 16.2 [Termination by Contractor] or GCC 19.6 [Optional Termination, Payment and Release] has taken effect, the Contractor shall promptly: - cease all further work, except for such work as may have been instructed by the Project Manager for the protection of life or property or for the safety of the Works, - hand over Contractor’s Documents, Plant, Materials and other work; and - remove all other Goods which are property of the Contractor from the Site, except as necessary for safety, and leave the Site. |
| 16.4 Payment on Termination | After a notice of termination under GCC 16.2 [Termination by Contractor] has taken effect, the Employer shall promptly: - pay the Contractor in accordance with GCC 19.6 [Optional Termination, Payment and Release], and - return the Performance Security to the Contractor provided that all performance obligation of the Contractor have been fulfilled. |
| - Risk and Responsibility |  |
| 17.1 Indemnities | The Contractor shall indemnify and hold harmless the Employer, the Employer’s Personnel, and their respective agents, against and from all claims, damages, losses and expenses (including legal fees and expenses) in respect of: - bodily injury, sickness, disease or death, of any person whatsoever arising out of or in the course of or by reason of the Contractor’s design (if any), the execution and completion of the Works and the remedying of any defects, unless attributable to any negligence, wilful act or breach of the Contract by the Employer, the Employer’s Personnel, or any of their respective agents, and - damage to or loss of any property, real or personal (including works), to the extent that such damage or loss arises out of or in the course of or by reason of the Contractor’s design, the execution and completion of the Works and the remedying of any defects, unless and to the extent that any such damage or loss is attributable to any negligence, Fraud, wilful act or omissions by the Employer, the Employer’s Personnel, their respective agents. - The Employer shall indemnify and hold harmless the Contractor, the Contractor’s Personnel, and their respective agents, against and from all claims, damages, losses and expenses (including legal fees and expenses) in respect of (1) bodily injury, sickness, disease or death, which is attributable to any negligence, fraud, wilful act or omission by the Employer, the Employer’s Personnel, or any of their respective agents, and (2) the matters for which liability may be excluded from insurance cover, as described in sub-paragraphs (d)(i), (ii) and (iii) of GCC 18.3 [Insurance Against Injury to Persons and Damage to Property]. |
| 17.2 Contractor’s Care of the Works | Notwithstanding GCC 11 [Defects Liability], the Contractor shall take full responsibility for the care of the Works and Goods from the Commencement Date until the Taking-Over Certificate is issued (or is deemed to be issued under GCC 10.1 [Taking Over of the Works and Sections]) for the Works, when responsibility for the care of the Works shall pass to the Employer. If a Taking-Over Certificate is issued (or is so deemed to be issued) for any Section or part of the Works, responsibility for the care of the Section or part shall then pass to the Employer. After responsibility has accordingly passed to the Employer, the Contractor shall take responsibility for the care of any work which is outstanding on the date stated in a Taking-Over Certificate, until this outstanding work has been completed. If any loss or damage happens to the Works, Goods or Contractor’s Documents during the period when the Contractor is responsible for their care, from any cause not listed in GCC 17.3 [Employer’s Risks], the Contractor shall rectify the loss or damage at the Contractor’s risk and cost, so that the Works, Goods and Contractor’s Documents conform with the Contract. The Contractor shall be liable for any loss or damage caused by any actions performed by the Contractor after a Taking-Over Certificate has been issued. The Contractor shall also be liable for any loss or damage which occurs after a Taking-Over Certificate has been issued and which arose from a previous event for which the Contractor was liable. |
| 17.3 Employer’s Risks | The risks referred to in GCC 17.4 below, insofar as they directly affect the execution of the Works in the Country, are: (a) use or occupation by the Employer of any part of the Permanent Works, except as may be specified and agreed under the Contract, (b) design of any part of the Works by the Employer’s Personnel or by others for whom the Employer is responsible, (c) Other Employer’s obligations under the Contract. |
| 17.4 Consequences of Employer’s Risks | If and to the extent that any of the risks listed in GCC 17.3 above results in loss or damage to the Works, Goods or Contractor’s Documents, the Contractor shall promptly give notice to the Project Manager and shall rectify this loss or damage to the extent required by the Project Manager. If the Contractor suffers delay and/or incurs Cost from rectifying this loss or damage, the Contractor shall give a further notice to the Project Manager and shall be entitled subject to GCC 20.1 [Contractor’s Claims] to an extension of time and any associated costs (if any) for such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion] In the case of sub-paragraphs (a) and (b) of GCC 17.3 [Employer 's Risks], Cost plus profit shall be payable. After receiving this further notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| 17.5 Intellectual and Industrial Property Rights | In this GCC, “infringement” means an infringement (or alleged infringement) of any patent, registered design, copyright, trade mark, trade name, trade secret or other intellectual or industrial property right relating to the Works; and “claim” means a claim (or proceedings pursuing a claim) alleging an infringement. Whenever a Party does not give notice to the other Party of any claim within 90 days of receiving the claim, the first Party shall be deemed to have waived any right to indemnity under this GCC. The Employer shall indemnify and hold the Contractor harmless against and from any claim alleging an infringement which is or was: - an unavoidable result of the Contractor’s compliance with the Contract, or - a result of any Works being used by the Employer: - for a purpose other than that indicated by, or reasonably to be inferred from, the Contract, or - in conjunction with any thing not supplied by the Contractor, unless such use was disclosed to the Contractor prior to the Base Date or is stated in the Contract. The Contractor shall indemnify and hold the Employer harmless against and from any other claim which arises out of or in relation to (i) the manufacture, use, sale or import of any Goods, or (ii) any design for which the Contractor is responsible. If a Party is entitled to be indemnified under this GCC, the indemnifying Party may (at its cost) conduct negotiations for the settlement of the claim, and any litigation or arbitration which may arise from it. The other Party shall, at the request and cost of the indemnifying Party, assist in contesting the claim. |
| 17.6 Limitation of Liability | Neither Party shall be liable to the other Party for loss of use of any Works, loss of profit, loss of any contract or for any indirect or consequential loss or damage which may be suffered by the other Party in connection with the Contract, other than as specifically provided in GCC 8.7 [Liquidated Damages]; GCC 11.2 [Cost of Remedying Defects]; GCC 15.4 [Payment after Termination]; GCC 16.4 [Payment on Termination]; GCC 17.1 [Indemnities]; GCC 17.4 (b) [Consequences of Employer’s Risks] and GCC 17.5 [Intellectual and Industrial Property Rights]. The total liability of the Contractor to the Employer, under or in connection with the Contract other than under GCC 4.19 [Electricity, Water and Gas], GCC 4.20 [Employer’s Equipment and Free-Issue Material], GCC 17.1 [Indemnities] and GCC 17.5 [Intellectual and Industrial Property Rights], shall not exceed the sum resulting from the application of a multiplier (greater than one) to the Contract Sum, as stated in the SCC, or (if such multiplier or other sum is not so stated), the Contract Sum. This Clause shall not limit liability in any case of fraud, deliberate default or reckless misconduct by the defaulting Party. |
| 17.7 Use of Employer’s Accomodation/Facilities | The Contractor shall take full responsibility for the care of the Employer provided accommodation and facilities, if any, as detailed in the Employer’s Requirement, from the respective dates of hand-over to the Contractor until cessation of occupation (where hand-over or cessation of occupation may take place after the date stated in the Taking-Over Certificate for the Works). If any loss or damage happens to any of the above items while the Contractor is responsible for their care arising from any cause whatsoever other than those for which the Employer is liable, the Contractor shall, at his own cost, rectify the loss or damage to the satisfaction of the Employer. |
| - Insurance |  |
| 18.1 General Requirements for Insurances | In this Clause, “insuring Party” means, for each type of insurance, the Party responsible for effecting and maintaining the insurance specified in the relevant GCC. Wherever the Contractor is the insuring Party, each insurance shall be effected with insurers and in terms approved by the Employer. These terms shall be consistent with any terms agreed by both Parties before the date of the Letter of Acceptance. This agreement of terms shall take precedence over the provisions of this Clause. Wherever the Employer is the insuring Party, each insurance shall be effected with insurers and in terms acceptable to the Contractor. These terms shall be consistent with any terms provided in the Biding documents except as otherwise agreed by both Parties as stipulated in the SCC. This agreement of terms shall take precedence over the provisions of this Clause. If a policy is required to indemnify joint insured, the cover shall apply separately to each insured as though a separate policy had been issued for each of the joint insured. Each policy insuring against loss or damage shall provide for payments to be made in the currencies required to rectify the loss or damage. Payments received from insurers shall be used for the rectification of the loss or damage. The relevant insuring Party shall, within the respective periods stated in the SCC (calculated from the Commencement Date), submit to the other Party: - evidence that the insurances described in this Clause have been effected, and - copies of the policies for the insurances described in GCC 18.2 [Insurance for Works and Contractor’s Equipment] and GCC 18.3 [Insurance against Injury to Persons and Damage to Property]. When each premium is paid, the insuring Party shall submit evidence of payment to the other Party. Whenever evidence or policies are submitted, the insuring Party shall also give notice to the Project Manager. Each Party shall comply with the conditions stipulated in its respective insurance policy. The insuring Party shall keep the insurers informed of any relevant changes to the execution of the Works and ensure that insurance is maintained in accordance with this Clause. Neither Party shall make any material alteration to the terms of any insurance without the prior approval of the other Party. If the insuring Party fails to effect and keep in force any of the insurances it is required to effect and maintain under the Contract, or fails to provide satisfactory evidence and copies of policies in accordance with this GCC, the other Party may (at its option and without prejudice to any other right or remedy) effect insurance for the relevant coverage and pay the premiums due. The insuring Party shall pay the amount of these premiums to the other Party, and the Contract Price shall be adjusted accordingly. Nothing in this Clause limits the obligations, liabilities or responsibilities of the Contractor or the Employer, under the other terms of the Contract or otherwise. Any amounts not insured or not recovered from the insurers shall be borne by the Contractor and/or the Employer in accordance with these obligations, liabilities or responsibilities. However, if the insuring Party fails to effect and keep in force an insurance which is available and which it is required to effect and maintain under the Contract, and the other Party neither approves the omission nor effects insurance for the coverage relevant to this default, any moneys which should have been recoverable under this insurance shall be paid by the insuring Party. Payments by one Party to the other Party shall be subject to GCC 2.5 [Employer’s Claims] or GCC 20.1 [Contractor’s Claims], as applicable. The Contractor shall be entitled to place all insurance relating to the Contract (including, but not limited to the insurance referred to GCC 18) with insurers from any eligible source country specified in the SCC. |
| 18.2 Insurance for Works and Contractor’s Equipment | The Contractor shall insure the Works, Plant, Materials and Contractor’s Documents for not less than the full reinstatement cost including the costs of demolition, removal of debris and professional fees and profit. The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Commencement Date to the end of the Defects Liability Period. The Contractor shall maintain this insurance to provide cover until the date of issue of the Performance Certificate, for loss or damage for which the Contractor is liable arising from a cause occurring prior to the issue of the Taking-Over Certificate, and for loss or damage caused by the Contractor in the course of any other operations (including those under GCC 11 [Defects Liability]). The Contractor shall insure the Contractor’s Equipment for not less than the full replacement value, including delivery to Site. For each item of Contractor’s Equipment, the insurance shall be effective while it is being transported to the Site and until it is no longer required as Contractor’s Equipment. Unless otherwise stated in the SCC, insurances under this GCC: - shall be effected and maintained by the Contractor as insuring Party, - shall be in the joint names of the Parties, who shall be jointly entitled to receive payments from the insurers, payments being held or allocated to the Party actually bearing the costs of rectifying the loss or damage; - shall cover all loss and damage from any cause not specifically stated under the contract to be Employer’s Risks; - shall also cover, to the extent specifically specified in the SCC, loss or damage to a part of the Works which is attributable to the use or occupation by the Employer of another part of the Works, and loss or damage from the risks listed in GCC 19 [Force Majeure], excluding (in each case) risks which are not insurable at commercially reasonable terms; and - may however exclude loss of, damage to, and reinstatement of: - a part of the Works which is in a defective condition due to a defect in its design, materials or workmanship (but cover shall include any other parts which are lost or damaged as a direct result of this defective condition and not as described in sub-paragraph (ii) below), - a part of the Works which is lost or damaged in order to reinstate any other part of the Works if this other part is in a defective condition due to a defect in its design, materials or workmanship |
| 18.3 Insurance against Injury to Persons and Damage to Property | The insuring Party shall insure against each Party’s liability for any loss, damage, death or bodily injury which may occur to any physical property (except things insured under GCC 18.2 [Insurance for Works and Contractor’s Equipment]) or to any person (except persons insured under GCC 18.4 [Insurance for Contractor’s Personnel]), which may arise out of the Contractor’s performance of the Contract and occurring before the issue of the Performance Certificate. Unless otherwise stated in the SCC, the insurances specified in this GCC: (a) shall be effected and maintained by the Contractor as insuring Party, (b) shall be in the joint names of the Parties, (c) shall be extended to cover liability for all loss and damage to the Employer’s property (except things insured under GCC 18.2) arising out of the Contractor’s performance of the Contract, and (d) may however exclude liability to the extent that it arises from: - the Employer’s right to have the Permanent Works executed on, over, under, in or through any land, and to occupy this land for the Permanent Works, - damage which is an unavoidable result of the Contractor’s obligations to execute the Works and remedy any defects, and - a cause listed in GCC 19 [Force Majeure], except to the extent that cover is available at commercially reasonable terms. |
| 18.4 Insurance for Contractor’s Personnel | The Contractor shall effect and maintain insurance against liability for claims, damages, losses and expenses (including legal fees and expenses) arising from injury, sickness, disease or death of any person employed by the Contractor or any other of the Contractor’s Personnel. The insurance shall cover the Employer and the Project Manager against liability for claims, damages, losses and expenses (including legal fees and expenses) arising from injury, sickness, disease or death of any person employed by the Contractor or any other of the Contractor’s Personnel, except that this insurance may exclude losses and claims to the extent that they arise from wilful acts and omissions, neglect of the Employer or of the Employer’s Personnel. The insurance shall be maintained and be in effect during the whole time that these personnel are assisting in the execution of the Works. For a Subcontractor’s employees, the insurance may be effected by the Subcontractor, but the Contractor shall be responsible for compliance with this Clause. |
| - Force Majeure |  |
| 19.1 Definition of Force Majeure | In this , “Force Majeure” means an exceptional event or circumstance: - which is beyond a Party’s control; - which such Party could not reasonably have provided against before entering into the Contract; - which, having arisen, such Party could not reasonably have avoided or overcome, and - which is not substantially attributable to the other Party. Force Majeure may include, but is not limited to, exceptional events or circumstances of the kind listed below, so long as conditions (a) to (d) above are satisfied: - war, hostilities (whether war be declared or not), invasion, act of foreign enemies, - rebellion, by persons other than the Contractor’s Personnel, revolution, insurrection, military or usurped power, or civil war, - riot, commotion, disorder, strike or lockout by persons other than the Contractor’s Personnel, - munitions of war, explosive materials, ionising radiation or contamination by radio-activity, except as may be attributable to the Contractor’s use of such munitions, explosives, radiation or radio-activity, and - natural catastrophes such as earthquake, hurricane, typhoon or volcanic activity. |
| ### 19.2 Notice of Force Majeure | If a Party is or will be prevented from performing its substantial obligations under the Contract by Force Majeure, then it shall give notice to the other Party of the event or circumstances constituting the Force Majeure and shall specify the obligations, the performance of which is or will be prevented. The notice shall be given within 14 working days after the Party became aware, or should have become aware, of the relevant event or circumstance constituting Force Majeure. The Party shall, having given notice, be excused from performance of its obligations for so long as such Force Majeure prevents it from performing them. Notwithstanding any other provision of this Clause, Force Majeure shall not apply to obligations of either Party to make payments to the other Party under the Contract. |
| 19.3 Duty to Minimize Delay | Each Party shall at all times use all reasonable endeavours to minimise any delay in the performance of the Contract as a result of Force Majeure. A Party shall give notice to the other Party when it ceases to be affected by the Force Majeure. |
| 19.4 Consequences of Force Majeure | If the Contractor is prevented from performing its substantial obligations under the Contract by Force Majeure of which notice has been given under GCC 19.2 [Notice of Force Majeure], and suffers delay and/or incurs Cost by reason of such Force Majeure, the Contractor may be entitled subject to GCC 20.1 [Contractor’s Claims] to: - an extension of time for any such delay, if completion is or will be delayed, under GCC 8.4 [Extension of Time for Completion], and - if the event or circumstance is of the kind described in sub-paragraphs (i) to (iv) of GCC 19.1 [Definition of Force Majeure] and, in the case of sub-paragraphs (ii) to (iv), occurs in the Country, payment of any such Cost, including the costs of rectifying or replacing the Works and/or Goods damaged or destructed by Force Majeure, to the extent they are not indemnified through the insurance policy referred to in GCC 18.2 [Insurance for Works and Contractor’s Equipment]. After receiving this notice, the Project Manager shall proceed in accordance with GCC 3.5 [Determinations] to determine these matters. |
| 19.5 Force Majeure Affecting Subcontractor | If any Subcontractor is entitled under any contract or agreement relating to the Works to relief from force majeure on terms additional to or broader than those specified in this Clause, such additional or broader force majeure events or circumstances shall not excuse the Contractor’s non-performance or entitle him to relief under this Clause. |
| 19.6 Optional Termination, Payment and Release | If the execution of substantially all the Works in progress is prevented for a continuous period of 84 days by reason of Force Majeure of which notice has been given under GCC 19.2 [Notice of Force Majeure], or for multiple periods which total more than 140 days due to the same notified Force Majeure, then either Party may give to the other Party a notice of termination of the Contract. In this event, the termination shall take effect 14 working days after the notice is given, and the Contractor shall proceed in accordance with GCC 16.3 [Cessation of Work and Removal of Contractor’s Equipment]. Upon such termination, the Project Manager upon written approval of the Employer shall, determine the value of the work done and issue a Payment Certificate which shall include: - the amounts payable for any work carried out for which a price is stated in the Contract; - the Cost of Plant and Materials ordered for the Works which have been delivered to the Contractor, or of which the Contractor is liable to accept delivery: this Plant and Materials shall become the property of (and be at the risk of) the Employer when paid for by the Employer, and the Contractor shall place the same at the Employer’s disposal; - other Costs or liabilities which in the circumstances were reasonably and necessarily incurred by the Contractor in the expectation of completing the Works; - the Cost of removal of Temporary Works; and |
| 19.7 Release from Performance | Notwithstanding any other provision of this Clause, if any event or circumstance outside the control of the Parties (including, but not limited to, Force Majeure) arises which makes it impossible or unlawful for either or both Parties to fulfil its or their contractual obligations or which, under the law governing the Contract, entitles the Parties to be released from further performance of the Contract, then upon notice by either Party to the other Party of such event or circumstance: - the Parties shall be discharged from further performance, without prejudice to the rights of either Party in respect of any previous breach of the Contract, and - the sum payable by the Employer to the Contractor shall be the same as would have been payable under GCC 19.6 [Optional Termination, Payment and Release] if the Contract had been terminated under GCC 19.6. |
| - Claims, Disputes and Arbitration |  |
| 20.1 Contractor’s Claims | If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall give notice to the Project Manager, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than 28 days after the Contractor became aware, or should have become aware, of the event or circumstance. If the Contractor fails to give notice of a claim within such period of 28 days, the Time for Completion shall not be extended, the Contractor shall not be entitled to additional payment, and the Employer shall be discharged from all liability in connection with the claim. Otherwise, the following provisions of this GCC shall apply. The Contractor shall also submit any other notices which are required by the Contract, and supporting particulars for the claim, all as relevant to such event or circumstance. The Contractor shall keep such records as may be necessary to substantiate any claim, either on the Site or at another location acceptable to the Project Manager. Without admitting the Employer’s liability, the Project Manager may, after receiving any notice under this Clause, monitor the record-keeping and/or instruct the Contractor to keep further records. The Contractor shall permit the Project Manager to inspect all these records, and shall submit copies to the Project Manager. Within 14 days after the Contractor submission of Notice, or within such other period as may be approved by the Project Manager, the Contractor shall send to the Project Manager a fully detailed claim which includes full supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed. Within 28 days after receiving a claim or any further particulars supporting a claim, the Project Manager shall respond with approval, or with disapproval and detailed comments. He may also request any necessary further particulars, but shall nevertheless give his response on the principles of the claim within the above defined time period. Within the above defined period of 28 days, the Project Manager upon written approval of the Employer shall proceed in accordance with GCC 3.5 [Determinations] to determine (i) the extension (if any) of the Time for Completion (before or after its expiry) in accordance with GCC 8.4 [Extension of Time for Completion], and/or (ii) the additional payment (if any) to which the Contractor is entitled under the Contract. If the Project Manager does not respond within the timeframe defined in this Clause, either Party may consider that the claim is rejected by the Project Manager and any of the Parties may refer it to the other Party for Amicable settlement in accordance with GCC 20.2 The requirements of this Clause are in addition to those of any other Clause which may apply to a claim. If the Contractor fails to comply with this or another Clause in relation to any claim, any extension of time and/or additional payment shall take account of the extent (if any) to which the failure has prevented or prejudiced proper investigation of the claim, unless the claim is excluded under the second paragraph of this Clause. |
| 20.2 Amicable Settlement | In the event of any dispute arising out of this contract, either party shall issue a notice of dispute to settle the dispute amicably. The parties hereto shall, within twenty eight (28) days from the notice date, use their best efforts to settle the dispute amicably through mutual consultations and negotiation. Any unsolved dispute may be referred to a Dispute Adjudication Panel (DAP) nominated by the appointing Authority specified in the SCC. |
| 20.3 Appointment of the Dispute Adjudication Panel | Disputes shall be referred to a Dispute Adjudication Panel (DAP) for decision in accordance with GCC 20.4 [Obtaining Dispute Adjudication Panel’s Decision]. The Appointing Authority of the DAP shall appoint the DAP members when the Dispute arises. The DAP shall comprise, as stated in the SCC, either one or three suitably qualified persons (“the members”), each of whom shall be fluent in the language for communication defined in the Contract and shall be a professional experienced in the type of construction involved in the Works and with the interpretation of contractual documents. If the number is not so stated in the SCC, the DAP shall comprise three persons, one of whom shall serve as chairman. The terms of the remuneration of either the sole member or each of the three members, including the remuneration of any expert where Parties mutually approve, whom the DAP consults, shall be in accordance with the rules of the Appointing Authority. Each Party shall be responsible for paying one-half of this remuneration. If a member declines to act or is unable to act as a result of death, disability, resignation or termination of appointment, a replacement shall be appointed in the same manner as the replaced person was required to have been Appointed, as described in this Sub-Clause. Unless otherwise agreed by both Parties, the appointment of the DAP (including each member) shall expire when the DAP issues a decision. |
| 20.4 Obtaining Dispute Board’s Decision | If a dispute (of any kind whatsoever) arises between the Parties in connection with, or arising out of, the Contract or the execution of the Works, including any dispute as to any certificate, determination, instruction, opinion or valuation of the Project Manager, and the Parties have failed to resolve through amicable settlement, either Party may notify in writing the other Party and the Appointing Authority for appointment of the DAP. Upon Appointment of the DAP by the Appointing Authority, the notifying Party may refer the dispute in writing to the DAP for its decision, with copies to the other Party and the Project Manager. Such reference shall state that it is given under this Sub-Clause. For a DAP of three persons, the DAP shall be deemed to have received such reference on the date when it is received by the chairman of the DAP. Both Parties shall promptly make available to the DAP all such additional information, further access to the Site, and appropriate facilities, as the DAP may require for the purposes of making a decision on such dispute. The DAP shall be deemed to be not acting as arbitrator(s). Within 60 days after receiving such reference, or within such other period as may be proposed by the DAP and approved by both Parties, the DAP shall give its decision, which shall be reasoned and shall state that it is given under this Sub-Clause. The decision shall be binding on both Parties, who shall promptly give effect to it unless and until it shall be revised in an arbitral award as described below. Unless the Contract has already been abandoned, repudiated or terminated, the Contractor shall continue to proceed with the Works in accordance with the Contract. If either Party is dissatisfied with the DAP’s decision, then the dissatisfied Party may, within 14 working days after receiving the decision, give notice to the other Party of its dissatisfaction and intention to commence arbitration. If the DAP fails to give its decision within the period of 60 days (or as otherwise approved) after receiving such reference, then either Party may, within 14 working days after this period has expired, give notice to the other Party of its dissatisfaction and intention to commence arbitration. In either event, this notice of dissatisfaction shall state that it is given under this Sub-Clause, and shall set out the matter in dispute and the reason(s) for dissatisfaction. Except as stated in GCC 20.7 [Failure to Comply with Dispute Adjudication Panel’s Decision], neither Party shall commence arbitration of a dispute unless a notice of dissatisfaction to the other Party has been given in accordance with this Sub-Clause. If the DAP has given its decision as to a matter in dispute to both Parties, and no notice of dissatisfaction has been given by either Party within 14 working days after it received the DAP’s decision, then the decision shall become final and binding upon both Parties. |
| 20.5 Arbitration | Any dispute not settled amicably and in respect of which the DAP’s decision (if any) has not become final and binding shall be finally settled by arbitration. Unless otherwise agreed by both Parties: - For contracts with foreign contractors: (i) international arbitration with proceedings administered by the international arbitration institution stated in the SCC, in accordance with the rules of arbitration of the appointed institution; Provided that Parties may agree in the SCC to resolve their dispute in accordance with provisions of paragraph (b) of this GCC. (ii) the place of arbitration shall be stated in the SCC or such other place selected in accordance with the applicable arbitration rules; and (iii) the arbitration shall be conducted in the language for communications defined in GCC 5.3; and - For contracts with domestic contractors, arbitration with proceedings conducted in accordance with the laws of Tanzania. The arbitrators shall have full power to open up, review and revise any certificate, determination, instruction, opinion or valuation of the Project Manager, and any decision of the DAP, relevant to the dispute. Nothing shall disqualify representatives of the Parties and the Project Manager from being called as a witness and giving evidence before the arbitrators on any matter whatsoever relevant to the dispute. Neither Party shall be limited in the proceedings before the arbitrators to the evidence or arguments previously put before the DAP to obtain its decision, or to the reasons for dissatisfaction given in its notice of dissatisfaction. Any decision of the DAP shall be admissible in evidence in the arbitration. Arbitration may be commenced prior to or after completion of the Works. The obligations of the Parties, the Project Manager and the DAP shall not be altered by reason of any arbitration being conducted during the progress of the Works. |
| 20.6 Failure to Comply with Dispute Board’s Decision | In the event that a Party fails to comply with a DAP decision which has become final and binding, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration |

# SECTION VI # SPECIAL CONDITIONS OF CONTRACT (SCC)

The following Special Conditions Contract (SCC) shall supplement the GCC. Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

Special Conditions of Contract

| SCC Clause | GCC Clause | Conditions | Description |
| --- | --- | --- | --- |
| 1. | 1.1.2 & 1.3 | Employer’s name and address |  |
| 2. | 1.1.2 & 1.3 | Project Manager’s name and address |  |
| 3. | 1.1.3 | Time for Completion |  |
| 4. | 1.1.3 | Defects Liability Period |  |
| 5. | 1.1.5 | Section |  |
| 6 | 1.1.6 | Site |  |
| 7 | 1.5 (j) | Other documents forming part of the Contract |  |
| 8 | 1.7 | Supply of Documents |  |
| 9 | 1.12 | Compliance with the Law |  |
| 10 | 1.13 | Taxes and Duties |  |
| 11 | 1.15 | Inspections and Audits |  |
| 12 | 2.1 | Right of Access and Possession of the Site |  |
| 13 | 3.1 | Employer’s approval |  |
| 14 | 3.1 (d) | Response by the Project Manager |  |
| 15 | 4.2 & 8.6 | Performance Security |  |
| 16 | 4.4 | Sub-contractors |  |
| 17 | 4.16 | Transport of Goods |  |
| 18 | 4.21 | Progress Reports |  |
| 19 | 4.22 | Security of the Site |  |
| 20 | 5.1 | General design obligations |  |
| 21 | 8.1 | Commencement of the works |  |
| 22 | 8.6 & 14.15(b) | Liquidated damages for delay of the Works |  |
| 23 | 8.6 | Liquidated Damage |  |
| 24 | 9.1 | Tests on Completion |  |
| 25 | 12.1 | Tests after Completion |  |
| 26 | 13.5 | Provisional Sums |  |
| 27 | 13.8 | Adjustments for Changes in Cost |  |
| 28 | 14.1 | The Contract Price |  |
| 29. | 14.1 | The Contract Price |  |
| 30 | 14.2 | Advance payment |  |
| 31 | 14.2 | Repayment of advance payment |  |
| 32 | 14.2(b) | Repayment amortization rate of advance payment |  |
| 33 | 14.3 | Percentage of Retention Money |  |
| 34 | 14.3 | Limit of Retention Money |  |
| 35 | 14.5(b)(i) | Plant and Materials |  |
|  | 14.5(c)(i) |  |  |
| 36 | 14.7 | Payment and Currency |  |
| 37 | 14.10 | Submission of Statement of Completion |  |
| 38 | 14.11 | Final Statement |  |
| 39 | 17.6 | Maximum total liability of the Contractor to the Employer |  |
| 40. 41. 42. | 18.1 | Terms of Insurance by the Employer |  |
|  |  | Periods for submission of insurance: |  |
|  |  | Eligible Countries for Insurance |  |
| 43 | 18.2 | Insurance for Works and Equipment by the Contractor |  |
| 44 | 18.2(d) | Maximum amount to be covered by insurance of the Employer's risks |  |
| 45 | 18.3 | Insurance against Injury to Persons and Damage to Property by the Contractor |  |
| 46 | 20.2 | Appointing Authority of DAP |  |
| 47 | 20.3 | Composition of DAP |  |
| 48 | 20.5(a) (i) | International Institution and Rules of arbitration |  |
| 49 | 20.5(a) (ii) | Place of Arbitration |  |
| 50 | 20.5(a) | Disputes with Foreign Contractors Resolved through Local Arbitration |  |

Table 1: Summary of Sections

| Section Name/Description (GCC 1.1.5.6) | Time for Completion (GCC 1.1.3.3) | Damages for Delay (GCC 8.7) |
| --- | --- | --- |

Table 2: Contractor’s Comments on the Special Conditions Contract

| SCC Clause | GCC Clause | Condition | Description by the Employer | Comments by the Contractor |
| --- | --- | --- | --- | --- |
| 20 | 5.1 | General design obligations | Period for notifying unforeseeable errors, faults and defects in the Employer’s Requirements: [insert days] Note: should not exceed 28 days |  |
| 26 | 13.5 | Provisional Sums | Percentage for adjustment of Provisional Sums [insert percentage] |  |

# Section VII

# Forms of security

## Forms of Bid Security, Performance Security, Advance Payment Guarantee and Retention Money Guarantee

Samples of acceptable forms of Bid Security, Performance Security, the Advance Payment Guarantee and the Retention Money Guarantee follow. Apart from Bid Security Forms, Bidders should not complete these forms at the time of Biding . Only the successful Bidder will be required to provide Performance Security and a Bank Guarantee for Advance Payment. All forms shall be submitted in accordance with the samples or in similar forms acceptable to the Procuring Entity.

In the case where these guarantees are issued by a bank located outside the United Republic of Tanzania, the issuer shall have a corresponding financial institution located in Tanzania and acceptable to the Procuring Entity, confirm the guarantees to make it enforceable in the United Republic of Tanzania.

###### Form of Bid Security (Bank Guarantee)

_______________________[Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	___________________ [Name and Address of Employer]

Date:	________________

BID GUARANTEE No.:	_________________

We have been informed that [name of the Bidder](hereinafter called the “Bidder”) has submitted to you its Bid dated (hereinafter called "the Bid") for the execution of .............................................. under Invitation for Bids No.  .......................... (the “IFB”).

Furthermore, we understand that, according to your conditions, Bids must be supported by a Bid guarantee.

At the request of the Bidder, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures] ([amount in words]) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the Bid conditions, because the Bidder:

(a) 	has withdrawn its Bid during the period of Bid validity specified by the Bidder in the Form of Bid; or

(b) 	having been notified of the acceptance of its Bid by the Employer during the period of Bid validity, (i) fails or refuses to execute the Contract, or (ii) fails or refuses to furnish the Performance Security, in accordance with the Instructions to Bidders and the Contract.

This guarantee will expire: (a) if the Bidder is the successful Bidder, upon our receipt of copies of the Contract signed by the Bidder and the Performance Security issued to you upon the instruction of the Bidder; or (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification to the Bidder of the name of the successful Bidder; or (ii) twenty-eight (28) days after the expiration of the Bidder’s Bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

_____________________________[Signature(s)]

Form of Performance Bank Guarantee

_____________________________[Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	___________________ [Name and Address of Employer]

Date:	________________

PERFORMANCE GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called the “Contractor”) has entered into Contract No. [Insert reference number of the contract] dated [insert date] with you, for the execution of [name of contract and brief description of Works] (hereinafter called the “Contract”).

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures][amount in words], such sum being payable in the currency in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire no later than twenty-eight (28) days from the date of issuance of the Taking-Over Certificate, calculated based on a copy of such Certificate which shall be provided to us, or on the ___ day of ______, 2___, whichever occurs first.  The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed six months in response to the Employer's written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, 2010 Revision, ICC Publication No. 758, except that Article 15 is hereby excluded.

_____________________

[signature(s)]

Form of Bank Guarantee for Advance Payment

_____________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	___________________ [Name and Address of Employer]

Date:	________________

ADVANCE PAYMENT GUARANTEE No.:	_________________

We have been informed that [name of Contractor] (hereinafter called the “Contractor”) has entered into Contract No. [insert reference number of the Contract]dated [insert date] with you, for the execution of [name of contract and brief description of Works] (hereinafter called the “Contract”).

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum [amount in figures][amount in words] is to be made against an advance payment guarantee.

At the request of the Contractor, we [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [amount in figures][amount in words] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the advance payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Contractor on its account number ___________ at _________________ [name and address of Bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the Interim Payment Certificate indicating that [ ] percent of the Contract Price has been certified for payment, or on the ___ day of _____, 2___, whichever is earlier.  The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed six months in response to the Employer's written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

_____________________

[signature(s) ]

Form of Bank Guarantee for Payment of Second Half of the Retention Money

Retention Money Security

Demand Guarantee

________________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:	___________________ [Name and Address of Employer]

Date:	________________

RETENTION MONEY GUARANTEE No.:	_________________

We have been informed that ________________ [name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. _____________ [reference number of the contract] dated ____________ with you, for the execution of _____________________ [name of contract and brief description of Works] (hereinafter called "the Contract") and wishes to receive early payment of the second half of the Retention Money for which the Contract requires him to provide a guarantee.

At the request of the Contractor, we _______________ [name of Bank]  hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________ [amount in figures] () [amount in words] upon receipt by us of your first demand in writing accompanied by a written statement stating:

(a)	that the Contractor has failed to carry out his obligation(s) to rectify defect(s) for which he is responsible under the Contract, and

(b)	the nature of such defect(s).

Any demand for payment must contain your signature(s) which must be authenticated by your bankers or by a notary public.  The authenticated demand and statement must be received by us at this office on or before (the date 70 days after the expected expiry of the Defects Notification Period for the Works) _____________________________ (the "expiry date"), when this guarantee shall expire and shall be returned to us.

We have been informed that the Employer may require the Contractor to extend this guarantee if the Performance Certificate under the Contract has not been issued by the date 28 days prior to such expiry date.  We undertake to pay you such guaranteed amount upon receipt by us, within such period of 28 days, of you demand in writing and your written statement that the performance certificate has not been issued, for reasons attributable to the Contractor, and that this guarantee has not been extended.

This guarantee shall be governed by the laws of Tanzania and is subject to the Uniform Rules for Demand Guarantees, 2010 Revision, ICC Publication No. 758, except that Article 15 is hereby excluded.

____________________

[signature(s)]

Part III

WORKS REQUIREMENTS

# Section VIII

# Price Offer form

Form of Letter of Price Offer

Name of Contract:

Design and Construction of………………………………………………………………………………..

To:

………………………………………..

………………………………………..

………………………………………..

Gentlemen:

We, the undersigned, declare that:

1.	We have examined and we have no reservations to the Biding Documents, including addenda thereto issued in accordance with the Instructions to Bidders.

2.	In accordance with the Conditions of Contract, Employer’s Requirements, Basic Site Information and Price Offer and Addenda Nos. [insert Addenda Nos.]for the execution of the above-named Works, we offer to design, construct and install such Works and remedy any defects therein in conformity with the Conditions of Contract, Employer’s Requirements, Basic Site Information and Price Offer, and Addenda for the sum of Tanzania Shillings.................................(amount in words) or such other sums as may be ascertained in accordance with the conditions.

3.	We acknowledge that the Appendix to Bid forms part of our Bid.

4.	Our Financial Offer shall be binding upon us subject to the modifications resulting from Contract negotiations, up to expiration of the validity period of the Bid, i.e. the Bid Validity Period specified in the ITB Clause  18.

5.	Commissions and gratuities, if any, paid or to be paid by us to agents relating to this Bid and Contract execution, if we are awarded the Contract, are listed as follows:

| Name and Address of Agents | Amount | Purpose of commission or gratuity |
| --- | --- | --- |

6.	We certify that we and any subcontractors and suppliers for any part of the Contract comply with the requirements of ITB  3 of the Biding Documents. By that, we mean that we, including any subcontractors or suppliers for any part of the Contract, do not have any conflict of interest in accordance with ITB  4.1; have not been declared ineligible as described in ITB  4.2; and have not been excluded as a result of the laws of Tanzania or official Regulations, or by an act of compliance with a decision of the United Nations Security Council.

7.	We understand you are not bound to accept any Bid you receive.

8.	We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in bribery.

Dated this 	 day of 	 20

Name of the Signatory of the Bid___________________________________________

Signature 	 In the capacity of

Duly authorized to sign Bids for and on behalf of

[in block capitals or typed]

Address:

Witness:

Address:

Occupation:

| PRICE OFFER FORM |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ……………………………………………………………………….. |  |  |  |  |  |
| (This Price Offer Form covers items as described in the Employer’s Requirements and All other Contractor’s Obligations) |  |  |  |  |  |
| PROJECT TITLE: ……………………………………………………………………………. |  |  |  |  |  |
| THE LIST CONTAINS MINIMUM ITEMS ONLY (INDICATIVE); IT MUST BE ADJUSTED BY THE BIDDER TO INCLUDE ALL PRICEABLE ITEMS REFERRED FROM THEIR DESIGN AND BUILD SOLUTION AS PER EMPLOYER’S REQUIREMENTS |  |  |  |  |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT(T.SHS) |
| 1.0 | Site Preparation |  |  |  |  |
|  |  |  | Sum |  |  |
| 2.0 | Measured Works |  |  |  |  |
| 2.12 | Electrical Installations |  |  |  |  |
|  |  |  |  | CF |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT (T.SHS) |
|  |  |  |  | B/F |  |
| 2.15 | Mechanical Engineering Installations:- |  |  |  |  |
| 3.0 | Preliminaries and General Matters |  |  |  |  |
|  | * Allow for all Preliminaries to be spent in the project upon approval by the Contract Administrator |  | Sum |  |  |
| 4.0 | Prime Cost Sums |  |  |  |  |
|  | The following PC Sums are for the works to be carried out by Statutory Authorities, Nominated Sub-contractors and Public Undertakers: Amounts inserted shall include costs for attendance, Contractors’ profits and Builder’s Works in connection thereof to be required by the Bidder |  | Sum |  |  |
| 5.0 | External Electrical Works |  |  |  |  |
| 6.0 | External Plumbing Works |  | Item |  |  |
| 6.1 | Clean water main connections (including meters) |  | Item |  |  |
|  |  |  |  | CF |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT (T.SHS) |
|  |  |  |  | B/F |  |
| 7.0 | Other works |  |  |  |  |
| 8.0 | Contingency Sum |  |  |  |  |
|  | Contingency sums for unforeseen works; to be expended at the discretion of the Contract administrator and the Employer only |  | Sum |  |  |
|  | SUB TOTAL-1 |  |  |  |  |
|  | ADD: Insurances and Bonds as per requirements |  | Sum |  |  |
|  | SUB TOTAL-2 |  |  |  |  |
|  | ADD: TAXES (15% VAT) | % |  |  |  |
|  | TOTAL BID PRICE |  |  | CF |  |
|  |  |  |  | B/F |  |
|  | OTHER RELEVANT INFORMATION FORMING PART OF THIS PRICE OFFER FORM |  |  |  |  |
| A | Total Built up area (Gross Floor Area) |  |  |  |  |
| B | Overall Cost per Square meter |  |  |  |  |
| C | Detailed consultancy rates – monthly/hourly (list to include all consultancies that will be involved in this project) |  |  |  |  |
|  |  |  |  | C/F |  |
| ITEM | DESCRIPTION | QTY | UNIT | RATE | AMOUNT (T.SHS) |
|  |  |  |  | B/F |  |
| 9.0 | Design and Build as per Clause 17.3 of the General Conditions of the Contract |  |  |  |  |
|  | Allow Provision for Design and Build to be expended at the discretion of the Project Manager and the Employer |  | Sum |  |  |
|  | GUARANTEED MAXIMUM PRICE (between TZS………………………. per square meter of gross floor area VAT Inclusive) |  |  |  |  |
|  | GUARANTEED MAXIMUM PRICE |  |  |  |  |

NOTES:

- This Price Offer Form contains minimum information only. The Bidder MUST adjust and fill-in his/her own Price Offer Form bearing all price-able contents of his/her design solution as per the Employer’s Requirements.

- GUARANTEED MAXIMUM PRICE filled/ priced must include all costs associated with the project

- Contractor must price in full all prime cost and provisional sums elements as per his design solution and Employer’s Requirements. Such costs shall be considered sufficient to execute the works under PC and PS sums. In summary, THERE SHALL NOT be additional amount from the Employer to execute the works under PC and PS sums.

- This Price Offer Form contains minimum information only. The Bidder MUST adjust and fill-in his/her own Price Offer Form bearing all price-able contents of his/her design solution as per the Employer’s Requirements.

- The Bidder is required to Bid in Tanzanian Shillings Only. Submission of the Bid (in part or full) in other currencies will automatically disqualify the Bidder.

- Cost of Designs and/or Consultancy fees shall be as guided by the relevant Professional Regulatory bodies of Tanzania BUT the bidder’s price shall be INCLUSIVE of the design costs and obligations.

- Cash Flow Projection (To be submitted in the Financial Proposal Only)

Each Bidder shall set out details of the Cash Flow Projection indicating quarterly projected expenditure throughout the duration of the Contract, both the percent of the Accepted Contract Amount and the cumulative percentage of the Accepted Contract Amount by quarter. The Cash Flow Projection shall address the following, taking into consideration payment of the Advance Payment, amortization of the Advance Payment, withholding of the Retention, and release of the Retention:

(i).	The periodic payments by milestones for the construction of the Works.

(ii).	The periodic payments based on measurement for the construction of the Works, as applicable.

These milestones shall be proposed by the Bidder in accordance with the Bidder’s proposed work methodology and program. The Employer reserves the right to negotiate with the successful Bidder on the Cash Flow Projection contained in the Bid paying specific attention to Bid unbalancing and the Employer’s risk exposure.

Bidder’s Proposed Milestone Payment Schedule

| Milestone | % | Cumulative % |
| --- | --- | --- |

# Section IX

# Specifications

(General and Particular Specifications )

# Section X

# EMPLOYER’S REQUIREMENTS

Part IV

FORMS OF INTEGRITY

# SECTION XII:  FORMS - INTEGRITY

UNDERTAKING BY BIDDER ON ANTI – BRIBERY POLICY / CODE OF CONDUCT AND COMPLIANCE PROGRAMME

(1)	Each Bidder must submit a statement, as part of the Bid documents, in either of the two given formats which must be signed personally by the Chief Executive Officer or other appropriate senior corporate officer of the Biding  company and, where relevant, of its subsidiary in the United Republic of Tanzania. If a Bid is submitted by a subsidiary, a statement to this effect will also be required of the parent company, signed by its Chief Executive Officer or other appropriate senior corporate officer.

(2)	Bidders will also be required to submit similar No-bribery commitments from their subcontractors and consortium partners; the Bidder may cover the subcontractors and consortium partners in its own statement, provided the Bidder assumes full responsibility.

(3)	(a)	Payment to agents and other third parties shall be limited to appropriate compensation for legitimate services.

(b)	Each Bidder will make full disclosure in the Bid documentation of the  beneficiaries and amounts of all payments made, or intended to be made, to agents or other third parties (including political parties or electoral candidates) relating to the Bid and, if successful, the implementation of the contract.

(c)	The successful Bidder will also make full disclosure [quarterly or semi- annually] of all payments to agents and other third parties during the execution of the contract.

(d)	Within six months of the completion of the performance of the contract, the successful Bidder will formally certify that no bribes or other illicit commissions have been paid. The final accounting shall include brief details of the goods and services provided that are sufficient to establish the legitimacy of the payments made.

(e)	Statements required according to subparagraphs (b) and (d) of this paragraph will have to be certified by the company's Chief Executive Officer, or other appropriate senior corporate officer.

(4)	Bids which do not conform to these requirements shall not be 	considered.

(5)	If the successful Bidder fails to comply with its No-bribery commitment, significant sanctions will apply. The sanctions may include all or any of the following:

- Cancellation of the contract;

- Liability for damages to the public authority and/or the unsuccessful competitors in the Biding possibly in the form of a lump sum representing a pre-set percentage of the contract value (liquidated).

(6)	Bidders shall make available, as part of their Bid, copies of their anti-Bribery Policy/Code of Conduct, if any, and of their-general or project - specific - Compliance Program.

(7)	The Government of the United Republic of Tanzania has made special arrangements for adequate oversight of the procurement process and the execution of the contract, and has invited civil society and other competent Government Departments to participate in the oversight. Those charged with the oversight responsibility will have full access to all documentation submitted by Bidders for this contract, and to which in turn all Bidders and other parties involved or affected by the project shall have full access (provided, however, that no proprietary information concerning a Bidder may be disclosed to another Bidder or to the public).

MEMORANDUM (Format 1)

(Regulation 100(2) of the Public Procurement (Goods, Works, Non-Consultant Services and Disposal of Public Assets by Bid) Regulations, 2005 - Government Notice No. 97 of 15th April, 2005

This company _____________________(name of company) places importance on competitive Biding  taking place on a basis that is free, fair, competitive and not open to abuse. It is pleased to confirm that it will not offer or facilitate, directly or indirectly, any improper inducement or reward to any public officer their relations or business associates, in connection with its Bid, or in the subsequent performance of the contract if it is successful.

This company has an Anti-Bribery Policy/Code of Conduct and a Compliance Program which includes all reasonable steps necessary to assure that the No-bribery commitment given in this statement will be complied with by its managers and employees, as well as by all third parties working with this company on the public sector projects, or contract including agents, consultants, consortium partners, sub- contractors and suppliers. Copies of our Anti-Bribery Policy/Code of Conduct and Compliance Program are attached

Authorized Signature:

Name and Title of Signatory:

Name of Bidder:

Address:

MEMORANDUM (Format 2)

(Regulation 100(2) of the Public Procurement (Goods, Works, Non-Consultant Services and Disposal of Public Assets by Bid) Regulations, 2005 - Government Notice No. 97 of 15th April, 2005

This company _____________________(name of company) has issued, for the purposes of this Bid, a Compliance Program copy attached -which includes all reasonable steps necessary to assure that the No-bribery commitment given in this statement will be complied with by its managers and employees, as well as by all third parties working with this company on the public sector projects or contract including agents, consultants, consortium partners, subcontractors and suppliers')"

Authorized Signature:

Name and Title of Signatory:

Name of Bidder:

Address:

For purposes of this submission the project(s) must be completed by at least 80% of the value of work done.

For purposes of this submission the project(s) must be completed by at least 80% of the value of work done.

Biders should note that, Alternative Technical Offer is Not Applicable

Biders should note that, Alternative Completion Time is Not Applicable

This form must be filled by the Bider. and in case of joint venture, consortium or association, the Lead Member must fill this form.

This form must be filled by all partners under the joint venture, consortium or association.

Must be provided

If project is still on going the Bider must insert the percentage value of works completed at the time of Biding .

The required value to be demonstrated here must be the total value of the constructed facility and not value of the design fees or contract value.

Must be provided

If project is still on going the Bider must insert the percentage value of works completed at the time of Biding .

The required value to be demonstrated here must be the total value of the constructed facility and not value of the design fees or contract value.

Must be provided

If project is still on going the Bider must insert the percentage value of works completed at the time of Biding .

The required value to be demonstrated here must be the total value of the constructed facility and not value of the service or contract value.

Must be provided

If project is still on going the Bider must insert the percentage value of works completed at the time of Biding .

The required value to be demonstrated here must be the total value of the constructed facility and not value of the service or contract value.